## April 2024 Projections
Engineering Number | Designer Name | Town | Anticipated Release Month | Anticipated Cost | Anticipated Fee
SC21051 | Taylor Lierow | OLYMPIA FIELDS | 2024-05-01 | 1000000 | 100000
N13624 | Eric Dina | PALATINE | 2024-05-01 | 444000 | 44400
SC23749 | Tim Purtell/Matt Hopkins | MANTENO | 2024-05-01 | 800000 | 80000
SC23762 | Randy Castellon | LOCKPORT | 2024-05-01 | 0 | 0
N18054-1 | Taylor Lierow | HOFFMAN ESTATES | 2024-05-01 | 200000 | 20000
N16431 | Conner Chamernik | ROCK FALLS | 2024-05-01 | 1000000 | 100000
SC24208 | Conner Chamernik | LOCKPORT | 2024-05-01 | 200000 | 20000
N16291 | Conner Chamernik | PROSPECT HEIGHTS | 2024-05-01 | NA | 45000
N13257 | Joey Betland | ELGIN | 2024-05-01 | NA | 7000
N15462 | Taylor Lierow | LAKE IN THE HILLS | 2024-05-01 | NA | 26000
N16541 | Conner Chamernik | ROCKFORD | 2024-05-01 | NA | 20000
SC23448 | Tim Purtell | PEOTONE | 2024-06-01 | 500000 | 50000
M15635 | Randy Castellon | BRIDGEVIEW | 2024-06-01 | 600000 | 60000
SC23750 | Joey Betland/Matt Hopkins | DOWNERS GROVE | 2024-06-01 | 30000 | 3000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-06-01 | NA | 10000
SC21396 | Randy Castellon | NEW LENOX | 2024-07-01 | 1250000 | 125000
N14793 | Camille Corbi | WOODSTOCK | 2024-07-01 | 8000000 | 800000
N13601-1 | Tim Purtell | ROCKFORD | 2024-07-01 | 500000 | 50000
N14915 | Randy Castellon | CRYSTAL LAKE | 2024-06-01 | NA | 15000
N16379 | Camille Corbi | CHICAGO |  | NA
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter in estimated amount for hourly tasks
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy i know this is TM - I want to see an hourly estimate as to what we'll be charging them, per my email Reply: i seeee. i updated this based on rte and anticipated effort

## May 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee
N15193 | Eric Dina | STREAMWOOD | 2024-06-01 | 2950000 | 295000
SC23448 | Tim Purtell | PEOTONE | 2024-06-01 | 500000 | 50000
N16431 | Conner Chamernik | ROCK FALLS | 2024-06-01 | 1500000 | 150000
SC23749 | Tim Purtell/Matt Hopkins | MANTENO | 2024-06-01 | 700000 | 70000
SC24208 | Conner Chamernik | LOCKPORT | 2024-06-01 | 250000 | 25000
SC23750 | Matt Hopkins | DOWNERS GROVE | 2024-06-01 | 30000 | 3000
SC23762 | Randy Castellon | LOCKPORT | 2024-06-01 | 700000 | 70000
N14793 | Camille Corbi | WOODSTOCK | 2024-08-01 | 8000000 | 800000
SC23103 | Camille Corbi/Ethan Ekstrom | NORMAL | 2024-06-01 | 70000 | 7000
SC21396 | Randy Castellon | NEW LENOX | 2024-07-01 | 700000 | 70000
SC21396-1 | Randy Castellon | NEW LENOX | 2024-07-01 | 984000 | 98400
M15635 | Randy Castellon | BRIDGEVIEW | 2024-06-01 | 600000 | 60000
N17175 | Conner Chamernik | CRYSTAL LAKE | 2024-07-01 | 50000 | 5000
M15844 | Camille Corbi/Ethan Ekstrom | JUSTICE | 2024-07-01 | 70000 | 7000
SC24292 | Camille Corbi | PLAINFIELD | 2024-07-01 | 450000 | 45000
N13601-1 | Tim Purtell | ROCKFORD | 2024-06-01 | 500000 | 50000
N14915 | Randy Castellon | CRYSTAL LAKE | 2024-07-01 | Hourly | #VALUE!
N15837 | Nick Watt | ROCKFORD | 2024-07-01 | Hourly | 40000
N15837-1 | Nick Watt | ROCKFORD | 2024-07-01 | Hourly | 12000
N15462 | Taylor Lierow | LAKE IN THE HILLS | 2024-06-01 | Hourly | 24000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-08-01 | Hourly | 12000
N15193 | Eric Dina | STREAMWOOD | 2024-06-01 | Hourly | 6000
N18718 | Eric Dina | ELK GROVE VILLAGE | 2024-06-01 | Hourly | 12000
SC21701 | Joey Betland | JOLIET | 2024-06-01 | Hourly | 3000
SC21051 | Taylor Lierow | OLYMPIA FIELDS | 2024-06-01 | Hourly | 20000
SC18611-1 | Camille Corbi | NORMAL | 2024-06-01 | Hourly | 5000
M15209 | Randy Castellon | Lincolnwood | 2024-06-01 | Hourly | #VALUE!
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter in estimated amount for hourly tasks
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric since we'll be invoicing this in june could you please add

## Jun 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee
N17175 | Conner Chamernik | CRYSTAL LAKE | 2024-07-01 | 50000 | 5000
SC24292 | Camille Corbi | PLAINFIELD | 2024-07-01 | 600000 | 60000
SC21051 | Taylor Lierow | OLYMPIA FIELDS | 2024-07-01 | Hourly | 20000
N13601-1 | Tim Purtell | ROCKFORD | 2024-07-01 | 600000 | 60000
SC20556 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-08-01 | 500000 | 50000
SC20556-1 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-08-01 | 150000 | 15000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-08-01 | Hourly | 10000
M15635 | Randy Castellon | BRIDGEVIEW | 2024-08-01 | 900000 | 90000
SC23762 | Randy Castellon | LOCKPORT | 2024-08-01 | 700000 | 70000
N18337 | Tim Purtell | SCHAUMBURG | 2024-08-01 | 250000 | 25000
N14915 | Randy Castellon | CRYSTAL LAKE | 2024-08-01 | Hourly | 15000
N14793 | Camille Corbi | WOODSTOCK | 2024-09-01 | 8000000 | 800000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-09-01 | 2000000 | 200000
SC23070 | Taylor Lierow | AURORA | 2024-09-01 | 1500000 | 150000
SC21396 | Randy Castellon | NEW LENOX | 2024-09-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2024-09-01 | 980000 | 98000
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are combining this drawing with NBA10014004 so majority of the cost is on the NBA (sitting around $1M for NBA estimate).

## Jul 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee
N18056 | Conner Chamernik | BUFFALO GROVE | 2024-08-01 | Hourly | 0
N17175 | Conner Chamernik | CRYSTAL LAKE | 2024-08-01 | 50000 | 5000
SC24292 | Camille Corbi | PLAINFIELD | 2024-08-01 | 900000 | 90000
SC20556 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-08-01 | 500000 | 50000
SC20556-1 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-08-01 | 150000 | 15000
N17890 | Conner Chamernik | CHEMUNG | 2024-08-01 | 100000 | 10000
N18693 | Taylor Lierow | GENESEO | 2024-08-01 | 250000 | 25000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-08-01 | Hourly | 5000
N13601-1 | Tim Purtell | ROCKFORD | 2024-08-01 | 1049275.13 | 104927.513
N18337 | Tim Purtell | SCHAUMBURG | 2024-08-01 | 361570.86 | 36157.086
N18268 | Eric Dina | PALATINE | 2024-08-01 | Hourly | 3000
SC21396 | Randy Castellon | NEW LENOX | 2024-09-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2024-09-01 | 980000 | 98000
SC23762 | Randy Castellon | LOCKPORT | 2024-09-01 | 700000 | 70000
M15450 | Eric Dina | PROVISO TWP | 2024-09-01 | 200000 | 20000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-10-01 | 2000000 | 200000
N14793 | Camille Corbi | WOODSTOCK | 2024-10-01 | 8000000 | 800000
M11560 | Conner Chamernik | NORTHLAKE | 2024-10-01 | 250000 | 25000
N12987 | Taylor Lierow | SCHAUMBURG | 2024-11-01 | 150000 | 15000
SC23070 | Taylor Lierow | AURORA | 2024-11-01 | 1500000 | 150000
N10173 | Randy Castellon | HAWTHORN WOODS | 2024-12-01 | 3000000 | 300000
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Probably won't bill this due to low effort.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are combining this drawing with NBA10014004 so majority of the cost is on the NBA (sitting around $1M for NBA estimate).

## Aug 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Total
SC21396 | Randy Castellon | NEW LENOX | 2024-09-01 | 450000 | 45000 | 2024-09-01 | 285237.5
SC21396-1 | Randy Castellon | NEW LENOX | 2024-09-01 | 980000 | 98000 | 2024-10-01 | 226000
N14915 | Randy Castellon | CRYSTAL LAKE | 2024-09-01 | Hourly | 16237.5 | 2024-11-01 | 1275000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-09-01 | Hourly | 16000 | 2024-12-01 | 330000
N18056 | Conner Chamernik | BUFFALO GROVE | 2024-09-01 | Hourly | 0
SC18611 | Camille Corbi | NORMAL | 2024-10-01 | Hourly | 8000
SC21364 | Conner Chamernik | ST CHARLES | 2024-09-01 | Hourly | 0
SC20556-1 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-09-01 | 950000 | 95000 | `
SC20556 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-09-01 | 150000 | 15000
SC23762 | Randy Castellon | LOCKPORT | 2024-10-01 | 700000 | 70000
M11560 | Conner Chamernik | NORTHLAKE | 2024-10-01 | 260000 | 26000
M15450 | Mark Stanley | PROVISO TWP | 2024-10-01 | 300000 | 30000
N18640 | Eric Dina/Ethan Ekstrom | BUFFALO GROVE | 2024-10-01 | 800000 | 80000
M14194 | Taylor Lierow | SCHILLER PARK | 2024-10-01 | Hourly | 2000
SC17551 | Taylor Lierow/Ethan Ekstrom | BLOOMINGTON | 2024-10-01 | Hourly | 10000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-11-01 | 2000000 | 200000
N14793 | Camille Corbi | WOODSTOCK | 2024-11-01 | 8000000 | 800000
SC23070 | Taylor Lierow | AURORA | 2024-11-01 | 2750000 | 275000
SC23070-1 | Taylor Lierow | AURORA | 2024-11-01 | 0 | 0
N12987 | Taylor Lierow | SCHAUMBURG | 2024-12-01 | 300000 | 30000
N10173 | Randy Castellon | HAWTHORN WOODS | 2024-12-01 | 3000000 | 300000
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hopefully will be able to negotiate out of the second round of CCDOTH comments
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Calvin K said they will likely move forward with rock boring so I can see us not billing this for our support effort (currently at $2,735 but don't see it going up much).

## Sep 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee
SC20556-1 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-09-01 | 164327.13 | 16432.713
SC20556 | Eric Dina/Ethan Ekstrom | BLOOMINGTON | 2024-09-01 | 1054108.14 | 105410.814
M11560 | Conner Chamernik | NORTHLAKE | 2024-10-01 | 280000 | 28000
M15450 | Mark Stanley | PROVISO TWP | 2024-10-01 | 225000 | 22500
N18640 | Eric Dina/Ethan Ekstrom | BUFFALO GROVE | 2024-10-01 | 800000 | 80000
SC24952 | Conner Chamernik | BLOOMINGDALE | 2024-10-01 | Hourly | 3000
SC18611 | Camille Corbi | NORMAL | 2024-10-01 | Hourly | 8000
N18056 | Conner Chamernik | BUFFALO GROVE | 2024-10-01 | Hourly | 9000
SC19500 | Conner Chamernik | SHOREWOOD | 2024-10-01 | Hourly | 18000
N14915 | Randy Castellon | CRYSTAL LAKE | 2024-10-01 | Hourly | 16,237.50
N14359 | Randy Castellon | Barrington | 2024-10-01 | Hourly | 3000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-11-01 | 2000000 | 200000
N12987 | Taylor Lierow | SCHAUMBURG | 2024-11-01 | 150000 | 15000
SC23070 | Taylor Lierow | AURORA | 2024-11-01 | 2700000 | 270000
SC23070-1 | Taylor Lierow | AURORA | 2024-11-01 | 50000 | 5000
N14793 | Camille Corbi | WOODSTOCK | 2024-11-01 | 10000000 | 1000000
N12480 | Matt Hopkins | CARPENTERSVILLE | 2024-11-01 | 500000 | 50000
N18617 | Matt Hopkins | MT MORRIS | 2024-11-01 | 150000 | 15000
SC21364 | Conner Chamernik | ST CHARLES | 2024-11-01 | Hourly | 5000
SC23762 | Randy Castellon | LOCKPORT | 2024-12-01 | 700000 | 70000
SC21396 | Randy Castellon | NEW LENOX | 2024-12-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2024-12-01 | 980000 | 98000
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-02-01 | 6500000 | 650000
N17865 | Conner Chamernik | ELK GROVE VILLAGE | 2025-02-01 | 300000 | 30000
SC24631 | Conner Chamernik | ST CHARLES | 2025-02-01 | 150000 | 15000
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-04-01 | 7000000 | 700000
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending a meeting with Nicor on Monday. If they want to update the current design this could go up.
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Conservative Estimate based on anticipated conflicts
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Conservative Estimate based on anticipated conflicts

## Oct 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee
N18337 | Mark Stanley | SCHAUMBURG | 2024-10-01 | Hourly | 2985
N18640 | Eric Dina/Ethan Ekstrom | BUFFALO GROVE | 2024-11-01 | 1100000 | 110000
N18056 | Conner Chamernik | BUFFALO GROVE | 2024-11-01 | Hourly | 13457.5
SC19500 | Conner Chamernik | SHOREWOOD | 2024-11-01 | Hourly | 30952.5
N14359 | Randy Castellon | BARRINGTON | 2024-11-01 | Hourly | 6000
SC23070 | Taylor Lierow | AURORA | 2024-11-01 | 3100000 | 310000
SC23070-1 | Taylor Lierow | AURORA | 2024-11-01 | 300000 | 30000
N12480 | Matt Hopkins | CARPENTERSVILLE | 2024-11-01 | 500000 | 50000
N18692 | Randy Castellon/Caroline Kulach | MONROE CENTER | 2024-11-01 | 75000 | 7500
SC18611-1 | Camille Corbi | NORMAL | 2024-11-01 | Hourly | 15000
N13606 | Randy Castellon | STOCKTON | 2024-11-01 | Hourly | 4000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-12-01 | 2000000 | 200000
N12987 | Taylor Lierow | SCHAUMBURG | 2024-12-01 | 300000 | 30000
N14793 | Camille Corbi | WOODSTOCK | 2024-12-01 | 10000000 | 1000000
N18617 | Matt Hopkins | MT MORRIS | 2024-12-01 | 150000 | 15000
SC23762 | Randy Castellon | LOCKPORT | 2024-12-01 | 700000 | 70000
SC21396 | Randy Castellon | NEW LENOX | 2025-01-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2025-01-01 | 980000 | 98000
SC21364 | Conner Chamernik | ST CHARLES | 2025-01-01 | Hourly | 0
SC24631 | Conner Chamernik | ST CHARLES | 2025-01-01 | 200000 | 20000
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-02-01 | 6500000 | 650000
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-02-01 | 7000000 | 700000
N17865 | Conner Chamernik | ELK GROVE VILLAGE | 2025-03-01 | 400000 | 40000
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric @Ekstrom, Ethan FYI this ended up at 1.85M so quite a bit higher than anticipated. Please factor that in in future forecasts
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We just supported on this task due DOT delaying their construction. I can see this not being billed.

## Nov 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | JPB Notes
NA | Misc Completed Projects to be Billed | NA | 2024-11-01 | NA | 231000 | N18056 N18056 SC19500 N18640 M10905 M15450
N13606 | Randy Castellon | STOCKTON | 2024-11-01 | Hourly | 5500
N12480 | Matt Hopkins | CARPENTERSVILLE | 2024-11-01 | 650000 | 65000
N18692 | Randy Castellon/Caroline Kulach | MONROE CENTER | 2024-11-01 | 75000 | 7500
N17175 | Conner Chamernik | CRYSTAL LAKE | 2024-12-01 | Hourly | 12000
SC23070 | Taylor Lierow | AURORA | 2024-12-01 | 3100000 | 310000 | Reimbursable conversations happening now with Nicor/DOT but anticipating to release this before 12/15 to bill in December.
SC23070-1 | Taylor Lierow | AURORA | 2024-12-01 | 300000 | 30000
N17815 | Taylor Lierow | ROUND LAKE BEACH | 2024-12-01 | 2000000 | 200000
N12987 | Taylor Lierow | SCHAUMBURG | 2024-12-01 | 375000 | 37500
N14793 | Camille Corbi | WOODSTOCK | 2024-12-01 | 10000000 | 1000000 | There's a chance this pushes to being released after 12/15 so it'll be up to us when to fully bill.
N18617 | Matt Hopkins | MT MORRIS | 2024-12-01 | 150000 | 15000
SC18611-1 | Camille Corbi | NORMAL | 2025-01-01 | Hourly | 16000 | ENG wants to wait for adjacent NBA to be finalized. Customer has not given load requirements yet.
SC23762 | Randy Castellon | LOCKPORT | 2025-01-01 | 700000 | 70000
SC21396 | Randy Castellon | NEW LENOX | 2025-01-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2025-01-01 | 980000 | 98000
SC21364 | Conner Chamernik | ST CHARLES | 2025-01-01 | Hourly | 0 | We just supported on this task due DOT delaying their construction. I can see this not being billed.
SC24631 | Conner Chamernik | ST CHARLES | 2025-01-01 | 350000 | 35000
N14359 | Randy Castellon | BARRINGTON | 2025-03-01 | Hourly | 15000 | Per call wtih Chip on 10/30, regardless of design he confirmed to keep task open for construction support.
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-03-01 | 6500000 | 650000
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-03-01 | 7000000 | 700000
N17865 | Conner Chamernik | ELK GROVE VILLAGE | 2025-03-01 | 500000 | 50000
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt FYI this ended up at almost 1.1M, so significantly higher than the original estimate. Please factor that into future estimates.

## Dec 2024
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | JPB Notes
N17175 | Conner Chamernik | CRYSTAL LAKE | 2024-12-01 | Hourly | 8000 | We only have about $3,6000 of KH effort right now, I assume shactee will come in with another $3,000. After internal commments and PAFC, I anticipate another $1,000. | 2024-12-01 | 2035000
SC23070 | Taylor Lierow | AURORA | 2024-12-01 | 3000000 | 300000 | Reimburable convos are complete - should be released by mid-December. | 2025-01-01 | 48000
SC23070-1 | Taylor Lierow | AURORA | 2024-12-01 | 300000 | 30000 | Reimburable convos are complete - should be released by mid-December. | 2025-02-01 | 314000
N12987 | Taylor Lierow | SCHAUMBURG | 2024-12-01 | 670000 | 67000 |  | 2025-04-01 | 700000
M16177 | Matt Hopkins |  | 2024-12-01 | 600000 | 60000
N18617 | Matt Hopkins | MT MORRIS | 2024-12-01 | 350000 | 35000
SC19879 | Eric Dina | JOLIET | 2024-12-01 | Hourly | 10000
M10905 | Eric Dina | JUSTICE | 2024-12-01 | Hourly | 8000
N14793 | Camille Corbi | WOODSTOCK | 2024-12-01 | 15000000 | 1500000 | There's a chance this pushes to being released after 12/15 so it'll be up to us when to fully bill.
SC18611-1 | Camille Corbi | NORMAL | 2024-12-01 | Hourly | 17000 | ENG wants to wait for adjacent NBA to be finalized. Customer has not given load requirements yet. There is a chance this could go up due to coordination with muliple departments on sizing and adjustments of the proposed vault due to Rivian improvements.
SC21364 | Conner Chamernik | ST CHARLES | 2025-01-01 | Hourly | 0 | We just supported on this task due DOT delaying their construction. I can see this not being billed.
SC24047 | Conner Chamernik | JOLIET | 2025-01-01 | 80000 | 8000
N17081 | Randy Castellon | FREEPORT | 2025-01-01 | 300000 | 30000
M15904 | Marissa LaPorte | MAYWOOD | 2025-01-01 | 100000 | 10000
SC23762 | Randy Castellon | LOCKPORT | 2025-02-01 | 700000 | 70000
SC21396 | Randy Castellon | NEW LENOX | 2025-02-01 | 450000 | 45000
SC21396-1 | Randy Castellon | NEW LENOX | 2025-02-01 | 980000 | 98000
SC24631 | Conner Chamernik | ST CHARLES | 2025-02-01 | 500000 | 50000
SC18359 | Camille Corbi | OSWEGO | 2025-02-01 | 110000 | 11000
N14359 | Randy Castellon | BARRINGTON | 2025-03-01 | Hourly | 15000 | Per call wtih Chip on 10/30, regardless of design he confirmed to keep task open for construction support.
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-03-01 | 6500000 | 650000
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-04-01 | 7000000 | 700000
N17865 | Conner Chamernik | ELK GROVE VILLAGE | 2025-03-01 | 500000 | 50000
N18674 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 300000 | 30000
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-03-01 | TBD | TBD | Cannot say right now as we are pending the UCM.
M16016 | Matt Hopkins | CHICAGO HEIGHTS | 2025-02-01 | 200000 | 20000
N19002 | Taylor Lierow/Caroline Kulach | OREGON | 2025-03-01 | 700000 | 70000
SC25118 | Matt Hopkins | WESTMONT | 2025-02-01 | 200000 | 20000
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-03-01 | TBD | TBD
SC18498 | Randy Castellon | WILMINGTON | 2024-12-01 | TBD | TBD | May not be a revision

## Jan 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | JPB Notes
SC23070 | Taylor Lierow | AURORA | 2025-01-01 | 3070151.39 | 307015.139 | Joey: Need to discuss with Josh.
SC23070-1 | Taylor Lierow | AURORA | 2025-01-01 | 737185.09 | 73718.509 | Joey: Need to discuss with Josh.
N14793 | Camille Corbi | WOODSTOCK | 2024-12-01 | 21000000 | 2100000 | Joey: Need to discuss with Josh.
SC24047 | Conner Chamernik | JOLIET | 2025-01-01 | 300000 | 30000
M15904 | Marissa LaPorte | MAYWOOD | 2025-01-01 | 100000 | 10000
M16177 | Matt Hopkins | ROSEMONT | 2025-01-01 | 750000 | 75000
SC18359 | Camille Corbi | OSWEGO | 2025-01-01 | 170000 | 17000
SC23762 | Randy Castellon | LOCKPORT | 2025-02-01 | 300000 | 30000
N12987 | Taylor Lierow | SCHAUMBURG | 2025-01-01 | 750000 | 75000
N17081 | Randy Castellon | FREEPORT | 2025-02-01 | 350000 | 35000
SC24631 | Conner Chamernik | ST CHARLES | 2025-02-01 | 500000 | 50000
SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | Not anticipating updated plans until Fall 2025
SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | Not anticipating updated plans until Fall 2025
N19002 | Taylor Lierow/Caroline Kulach | OREGON | 2025-02-01 | 400000 | 40000
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-03-01 | 6500000 | 650000
M16089 | Ethan Ekstrom | OAK FOREST | 2025-02-01 | 500000 | 50000
N14298 | Taylor Lierow/Caroline Kulach | STERLING | 2025-02-01 | 700000 | 70000
N18674 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 350000 | 35000
M15450 | Mark Stanley | PROVISO TWP | 2025-01-01 | HOURLY | 6000
N14359 | Randy Castellon | BARRINGTON | 2025-09-01 | HOURLY | 35000 | Task to remain open during construction of project.
M10905 | Eric Dina | JUSTICE | 2025-01-01 | HOURLY | 21000 | Joey: Need to discuss with Josh.
SC19879 | Eric Dina | JOLIET | 2025-01-01 | HOURLY | 19000
SC18611-1 | Camille Corbi | NORMAL | 2025-01-01 | HOURLY | 15000
SC21364 | Conner Chamernik | ST CHARLES | 2025-05-01 | HOURLY | 0 | I don't see us billing this as we are just supporting coordination.
SC18498 | Randy Castellon | Wilmington | 2025-01-01 | HOURLY | 7000
N17865 | Conner Chamernik | ELK GROVE VILLAGE | 2025-04-01 | 500000 | 50000
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is looking closer to 15 mil
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille i did my best to get values entered but could you please fill the rest of your cells out?
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ekstrom, Ethan please fill these couple out Reply: Done

## Feb 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | JPB Notes
SC18359 | Camille Corbi | OSWEGO | 2025-02-01 | 170000 | 17000 | 14627.15 | 2372.85
N12987 | Taylor Lierow | SCHAUMBURG | 2025-02-01 | 750000 | 75000 | 43132.5 | 31867.5
SC18611-1 | Camille Corbi | NORMAL | 2025-02-01 | HOURLY | 25000 | 0 | 25000
SC18498 | Randy Castellon | WILMINGTON | 2025-02-01 | HOURLY | 9570 | 0 | 9570
M10905 | Eric Dina | JUSTICE | 2025-02-01 | HOURLY | 30655 | 0 | 30655
SC23762 | Randy Castellon | LOCKPORT | 2025-02-01 | 300000 | 30000 | 0 | 30000
N17081 | Randy Castellon | FREEPORT | 2025-02-01 | 350000 | 35000 | 0 | 35000
N14298 | Taylor Lierow/Caroline Kulach | STERLING | 2025-02-01 | 700000 | 70000 | 0 | 70000
N19002 | Taylor Lierow/Caroline Kulach | OREGON | 2025-03-01 | 400000 | 40000 | 0 | 40000
M16089 | Ethan Ekstrom | OAK FOREST | 2025-03-01 | 750000 | 75000 | 0 | 75000
SC24631 | Conner Chamernik | ST CHARLES | 2025-03-01 | 500000 | 50000 | 36735 | 13265
N18674 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 250000 | 25000 | 0 | 25000
SC20245 | Conner Chamernik | Carol Stream | 2025-03-01 | 250000 | 25000 | 0 | 25000
N14359-1 | Randy Castellon | BARRINGTON | 2025-03-01 | HOURLY | 26000 | 0 | 26000
M16016 | Matt Hopkins | CHICAGO HEIGHTS | 2025-03-01 | 100000 | 10000 | 0 | 10000
N18674-1 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 100000 | 10000 | 0 | 10000
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-04-01 | 6500000 | 650000 | 484740 | 165260
SC19879 | Eric Dina | JOLIET | 2025-04-01 | HOURLY | 17000 | 0 | 17000
N17865/-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-04-01 | 1500000 | 150000 | 0 | 150000 | Combining both WOs here
SC21364 | Conner Chamernik | ST CHARLES | 2025-05-01 | HOURLY | 3000 | 0 | 3000 | I don't see us billing this as we are just supporting coordination.
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-06-01 | 10000000 | 1000000 | 146400 | 853600 | Not scoped yet so hard to say
SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | 0 | 50000 | Not anticipating updated plans until Fall 2025
SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | 113895 | 56105 | Not anticipating updated plans until Fall 2025
| February | 234465.35
| March | 329265
| April | 332260
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan @Rojas, Taylor i tagged the wrong tab before....please update these red cells Reply: done
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan I correct this off the invoice, you had like 526k in here Reply: this had a previous amount billed when we billed ahead on this in the past. Reply: it was for 54,670

## Mar 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | JPB Notes
SC18359 | Camille Corbi | OSWEGO | 2025-03-01 | 170000 | 17000 | 14627.15 | 2372.85 |  | SC18359 | Camille Corbi | OSWEGO | 2025-02-01 | 170000 | 17000 | 14627.15 | 2372.85
SC18611-1 | Camille Corbi | NORMAL | 2025-03-01 | HOURLY | 25000 | 0 | 25000 |  | N12987 | Taylor Lierow | SCHAUMBURG | 2025-02-01 | 750000 | 75000 | 43132.5 | 31867.5
N14793 BID DOCS | Camille Corbi | WOODSTOCK | 2025-03-01 | HOURLY | 2600 | 0 | 2600 |  | SC18611-1 | Camille Corbi | NORMAL | 2025-02-01 | HOURLY | 25000 | 0 | 25000
N12987 | Taylor Lierow | SCHAUMBURG | 2025-03-01 | 750000 | 75000 | 43132.5 | 31867.5 |  | SC18498 | Randy Castellon | WILMINGTON | 2025-02-01 | HOURLY | 9570 | 0 | 9570
SC23762 | Randy Castellon | LOCKPORT | 2025-03-01 | 350000 | 35000 | 0 | 35000 |  | M10905 | Eric Dina | JUSTICE | 2025-02-01 | HOURLY | 30655 | 0 | 30655
SC19500 REV2 | Conner Chamernik | SHOREWOOD | 2025-03-01 | HOURLY | 6000 | 0 | 6000 | Hard to say the effort needed on this. I need to dive into this more and coordinate with Nicor/DOT but this is what I'm estimating for now. | SC23762 | Randy Castellon | LOCKPORT | 2025-02-01 | 300000 | 30000 | 0 | 30000
N19002 | Taylor Lierow/Caroline Kulach | OREGON | 2025-03-01 | 400000 | 40000 | 0 | 40000 |  | N17081 | Randy Castellon | FREEPORT | 2025-02-01 | 350000 | 35000 | 0 | 35000
M16089 | Ethan Ekstrom | OAK FOREST | 2025-03-01 | 1100000 | 110000 | 0 | 110000 |  | N14298 | Taylor Lierow/Caroline Kulach | STERLING | 2025-02-01 | 700000 | 70000 | 0 | 70000
SC24631 | Conner Chamernik | ST CHARLES | 2025-03-01 | 750000 | 75000 | 36735 | 38265 |  | N19002 | Taylor Lierow/Caroline Kulach | OREGON | 2025-03-01 | 400000 | 40000 | 0 | 40000
N18674 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 150000 | 15000 | 0 | 15000 |  | M16089 | Ethan Ekstrom | OAK FOREST | 2025-03-01 | 750000 | 75000 | 0 | 75000
SC20245 | Conner Chamernik | CAROL STREAM | 2025-03-01 | 250000 | 25000 | 0 | 25000 |  | SC24631 | Conner Chamernik | ST CHARLES | 2025-03-01 | 500000 | 50000 | 36735 | 13265
N14359-1 | Randy Castellon | BARRINGTON | 2025-03-01 | HOURLY | 38000 | 0 | 38000 |  | N18674 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 250000 | 25000 | 0 | 25000
M16016 | Matt Hopkins | CHICAGO HEIGHTS | 2025-03-01 | 150000 | 15000 | 0 | 15000 |  | SC20245 | Conner Chamernik | Carol Stream | 2025-03-01 | 250000 | 25000 | 0 | 25000
N18674-1 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 180000 | 18000 | 0 | 18000 |  | N14359-1 | Randy Castellon | BARRINGTON | 2025-03-01 | HOURLY | 26000 | 0 | 26000
SC25418 | Camille Corbi | NORMAL | 2025-03-01 | 275000 | 27500 | 0 | 27500 |  | M16016 | Matt Hopkins | CHICAGO HEIGHTS | 2025-03-01 | 100000 | 10000 | 0 | 10000
SC19879 REV3 | Eric Dina | JOLIET | 2025-03-01 | HOURLY | 22000 | 0 | 22000 |  | N18674-1 | Ethan Ekstrom | PROSPECT HEIGHTS | 2025-03-01 | 100000 | 10000 | 0 | 10000
N18592 | Conner Chamernik | MCHENRY | 2025-04-01 | 100000 | 10000 | 0 | 10000 |  | N10173 | Randy Castellon | HAWTHORN WOODS | 2025-04-01 | 6500000 | 650000 | 484740 | 165260
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-04-01 | 6500000 | 650000 | 484740 | 165260 |  | SC19879 | Eric Dina | JOLIET | 2025-04-01 | HOURLY | 17000 | 0 | 17000
N17865/-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-04-01 | 1500000 | 150000 | 0 | 150000 | Combining both WOs here | N17865/-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-04-01 | 1500000 | 150000 | 0 | 150000
N13645 | Ethan Ekstrom | BUFFALO GROVE | 2025-04-01 | 0 | 0 | 0 | 0 | Pending UCM response. | SC21364 | Conner Chamernik | ST CHARLES | 2025-05-01 | HOURLY | 3000 | 0 | 3000
SC25118 | Matt Hopkins | WESTMONT | 2025-05-01 | 300000 | 30000 | 0 | 30000 | I anticipate IDOT not being able to confirm no conflict, so I think we'll have jumpers at 5 various locations. 300K is a rough estimate | N16744 | Mark Stanley | CRYSTAL LAKE | 2025-06-01 | 10000000 | 1000000 | 146400 | 853600
SC25031 | Randy Castellon | ROCKDALE | 2025-05-01 | 300000 | 30000 | 0 | 30000 |  | SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | 0 | 50000
N18492 | Taylor Lierow | LONG GROVE | 2025-05-01 | 75000 | 7500 | 0 | 7500 |  | SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | 113895 | 56105
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-05-01 | 0 | 0 | 0 | 0 | Still pending UCM response, hard to say right now.
SC21364 | Conner Chamernik | ST CHARLES | 2025-05-01 | HOURLY | 4000 | 0 | 4000 | I can likely see us not billing this as we are just supporting coordination.
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-07-01 | 10000000 | 1000000 | 146400 | 853600 | Not scoped yet so hard to say
SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | 0 | 50000 | Not anticipating updated plans until Fall 2025
SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | 113895 | 56105 | Not anticipating updated plans until Fall 2025
Billing Month | Anticipated Fee | Anticipated Net Fee
2025-03-01 | 546100 | 451605.35
2025-04-01 | 810000 | 325260
2025-05-01 | 71500 | 71500
2025-06-01 | 0 | 0
2025-07-01 | 1000000 | 853600
2025-08-01 | 220000 | 106105
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Bruce, Logan can you please update this column if there have been any changes? Reply: this is all we have billed for this site Reply: Can you confirm the values for the entire column G? Reply: this matches what was billed ahead in December. Reply: great, thanks
Note on Q2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan @Rojas, Taylor i tagged the wrong tab before....please update these red cells Reply: done
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric aren't we almost done with this one? do we not think it'll be invoiced in march? Reply: You're right. Updated.
Note on Q18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan I correct this off the invoice, you had like 526k in here Reply: this had a previous amount billed when we billed ahead on this in the past. Reply: it was for 54,670
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric Not sure I feel comfortable with an anticipated cost yet. We've been pending a UCM response since November '24, so this still may not become a project. Reply: good w/ me to leave as 0
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric @Stanley, Mark i pushed this a month...i really don't think that this is going out in may, let's keep an eye on the date extension Reply: July works for me. Also, make sure you're using the Apr 2025 SS

## Apr 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | JPB Notes
M16089 | Ethan Ekstrom | OAK FOREST | 2025-04-01 | 1300000 | 130000 | 0 | 130000
SC24631 | Conner Chamernik | ST CHARLES | 2025-04-01 | 1100000 | 110000 | 36735 | 73265
SC19879 REV3 | Eric Dina | JOLIET | 2025-04-01 | HOURLY | 34000 | 0 | 34000
N17865/-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-04-01 | 1500000 | 150000 | 0 | 150000 | Combining both WOs here
N13645 | Conner Chamernik | BUFFALO GROVE | 2025-04-01 | 600000 | 60000 | 0 | 60000 | DOT is getting potholes on this project so some relocation may go away.
M16177 REV1 | Matt Hopkins | ROSEMONT | 2025-04-01 | HOURLY | 15000 | 0 | 15000 | MWH - Updated Developer Linework & Reimbursable Estimate
SC18611-1 REV1 | Camille Corbi | NORMAL | 2025-05-01 | HOURLY | 30000 | 0 | 30000 | Pending roundabout plans.
SC19500 REV2 | Conner Chamernik | SHOREWOOD | 2025-05-01 | HOURLY | 10000 | 0 | 10000 | Going to need to redesign part of this project.
N18592 | Conner Chamernik | MCHENRY | 2025-05-01 | 100000 | 10000 | 0 | 10000
SC25031 | Randy Castellon | ROCKDALE | 2025-05-01 | 300000 | 30000 | 0 | 30000
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-05-01 | 0 | 0 | 0 | 0 | Still pending UCM response, hard to say right now.
SC25712 | Matt Hopkins | PONTIAC | 2025-05-01 | 200000 | 20000 | 0 | 20000 | Pending UCM response.
N18492 | Taylor Lierow | LONG GROVE | 2025-06-01 | 75000 | 7500 | 0 | 7500
SC23762 | Randy Castellon | LOCKPORT | 2025-06-01 | 350000 | 35000 | 0 | 35000
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-06-01 | 6500000 | 650000 | 484740 | 165260
SC25578 | Matt Hopkins | WILMINGTON | 2025-06-01 | 0 | 0 | 0 | 0 | MWH- I dont anticipate this being a conflict requiring relocation
N17141 | Randy Castellon | HUNTLEY | 2025-06-01 | 530000 | 53000 | 0 | 53000
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-06-01 | HOURLY | 14000 | 0 | 14000 | Marissa - I recommend entering RTE cost + $2k and entering a couple months out for the billing month.
N16744 | Mark Stanley | CRYSTAL LAKE | 2025-07-01 | 10000000 | 1000000 | 146400 | 853600 | Not scoped yet so hard to say
SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | 0 | 50000 | Not anticipating updated plans until Fall 2025
SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | 113895 | 56105 | Not anticipating updated plans until Fall 2025
Billing Month | Anticipated Fee | Anticipated Net Fee
2025-04-01 | 499000 | 462265
2025-05-01 | 100000 | 100000
2025-06-01 | 759500 | 274760
2025-07-01 | 1000000 | 853600
2025-08-01 | 220000 | 106105

## May 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments
M12594 | Caroline Kulach | NILES | 2025-06-01 | 380000 | 38000 | 0 | 38000 | Pending UCM Response
M15194 | Matt Hopkins | OAK PARK | 2025-06-01 | 0 | 0 | 0 | 0 | NOO.
M15242-T | Taylor Lierow | BERWYN | 2025-05-01 | HOURLY | 12000 | 0 | 12000
M15898-T | Mitchell Pohlman | GLENVIEW | 2025-07-01 | HOURLY | 21000 | 0 | 21000 | Negotiations, conflict analysis, close out
M16521-T | Matt Hopkins | BENSENVILLE | 2025-07-01 | HOURLY | 12000 | 0 | 12000 | Effort will be pothole coordination to negotiate out of conflict
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-07-01 | HOURLY | 630000 | 484740 | 145260 | This is estimated hourly effort including subconsultant costs
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-08-01 | HOURLY | 300000 | 146400 | 153600 | Will be scoped end of April. This is estimated hourly effort including subconsultant costs
N16744 NIS | Randy Castellon | Crystal Lake | 2025-07-01 | HOURLY | 300000 | 0 | 300000 | MR Portion of Crystal Lake (8" replacement)
N17019 | Ethan Ekstrom | MT PROSPECT | 2025-08-01 | 300000 | 30000 | 0 | 30000 | Will be scoped beginning of May
N17141 | Randy Castellon | HUNTLEY | 2025-07-01 | 530000 | 53000 | 0 | 53000 | Pending Reimbusrable Confirmation
N17865-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-05-01 | 873402.13 | 87340.213 | 0 | 87340.213
N17865-T | Conner Chamernik | ELK GROVE VILLAGE | 2025-05-01 | 2500000 | 250000 | 0 | 250000
N17925 | Randy Castellon | HOFFMAN ESTATES | 2025-08-01 | 350000 | 35000 | 0 | 35000
N18293-T | Mark Stanley | N BARRINGTON | 2025-06-01 | HOURLY | 21000 | 0 | 21000 | On hold.
N18492 | Taylor Lierow | LONG GROVE | 2025-06-01 | 400000 | 40000 | 0 | 40000 | ~3 sheets of PE jumpers, compared the cost to N16291
N18592 | Conner Chamernik | MCHENRY | 2025-05-01 | 100000 | 10000 | 0 | 10000 | ~300' of 4" PE
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-06-01 | 200000 | 20000 | 0 | 20000 | ~800' of 2" PE
N19216-T | Mark Stanley | ROCKFORD | 2025-08-01 | HOURLY | 25000 | 0 | 25000 | Ongoing access negotiations with Nicor depts. Pending PF plans.
N19472 | Caroline Kulach | HANOVER PARK | 2025-05-01 | 130000 | 13000 | 0 | 13000 | Currently working on UCM
N19637-T | Camille Corbi | ROCKFORD | 2025-05-01 | HOURLY | 9000 | 0 | 9000 | Pending potholes from ISTHA
N19731 | Taylor Lierow | MACHESNEY PARK | 2025-06-01 | 250000 | 25000 | 0 | 25000 | Pending Pre-final plans
SC18611-1 REV1 | Camille Corbi | NORMAL | 2025-06-01 | HOURLY | 35000 | 0 | 35000 | Pending roundabout plans.
SC19500 REV2 | Conner Chamernik | SHOREWOOD | 2025-05-01 | HOURLY | 10500 | 0 | 10500 | ReDesign no longer necessary.
SC21396 | Randy Castellon | NEW LENOX | 2025-06-01 | 500000 | 50000 | 0 | 50000 | Not anticipating updated plans until Spring 2025
SC21396-1 | Randy Castellon | NEW LENOX | 2025-06-01 | 1700000 | 170000 | 113895 | 56105 | Not anticipating updated plans until Spring 2025
SC23762 | Randy Castellon | LOCKPORT | 2025-06-01 | 350000 | 35000 | 0 | 35000
SC23843-T | Matt Hopkins | PILOT | 2025-08-01 | HOURLY | 15000 | 0 | 15000 | Effort will be coordinating with Land & Engineering on proposed crossing for Wind Development
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-06-01 | HOURLY | 14000 | 0 | 14000 | Marissa - I recommend entering RTE cost + $2k and entering a couple months out for the billing month.
SC24452-T | Mark Stanley | JOLIET | 2025-10-01 | HOURLY | 30000 | 0 | 30000 | Pending PF plans, potholes, locates.
SC25031 | Randy Castellon | ROCKDALE | 2025-05-01 | 350000 | 35000 | 0 | 35000
SC25259-T | Mark Stanley | ELWOOD | 2025-06-01 | HOURLY | 35000 | 0 | 35000 | Ongoing access negotiations with Nicor depts. Pending PF plans.
SC25330 | Caroline Kulach | GRANT PARK | 2025-06-01 | 340000 | 34000 | 0 | 34000 | Pending UCM Response
SC25337-T | Mark Stanley | SHOREWOOD | 2025-05-01 | HOURLY | 10000 | 0 | 10000 | Pending final NC items from developer.
SC25507-T | Mark Stanley | LOCKPORT | 2025-06-01 | HOURLY | 15000 | 0 | 15000 | Pending analysis path forward confirmation from Nicor.
SC25578 | Matt Hopkins | WILMINGTON | 2025-06-01 | 120000 | 12000 | 0 | 12000 | -500' of 2" STL
SC25712 | Matt Hopkins | PONTIAC | 2025-06-01 | 120000 | 12000 | 0 | 12000 | 400' of 4" PE
SC25811-T | Matt Hopkins | OAKBROOK TERRACE | 2025-05-01 | HOURLY | 8000 | 0 | 8000 | Effort will be coordinating with Land to review encroachment
SC25957 | Camille Corbi | GILMAN | 2025-07-01 | 250000 | 25000 | 0 | 25000 | Pending CAD files and initial information.
Billing Month | Anticipated Fee | Anticipated Net Fee
2025-05-01 | 444840.213 | 444840.213
2025-06-01 | 556000 | 442105
2025-07-01 | 1041000 | 556260
2025-08-01 | 405000 | 258600
2025-09-01 | 0 | 0
2025-10-01 | 30000 | 30000
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt releasing as NOO shortly, correct? Reply: correct, releasing this week
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Castellon, Randy this project is now running at T/M. Can you approximate the total invoice based on effort to date and the remainder of the work plan? Reply: I put my approx. Lookoing at RTE + final reviews for this project ot be released, this is what i approximate Reply: @Castellon, Randy can you please add in subconsultant costs to this?
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Castellon, Randy this project is now running at T/M. Can you approximate the total invoice based on effort to date and the remainder of the work plan? Reply: @Castellon, Randy can you please include subconsultant costs on this? Reply: I have to imagine that this is going to be greater than 300k in effort - let's bump up to like 500k for our forecasts please Reply: nvm ignore - i see we have 600k between the two tasks
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy @Dina, Eric we have another WO for a portion of this that is going under Nicor System Improvement, right? Have we nailed down how we intend on billing that yet and what that effort might be? I would try and estimate the hourly effort right now for it

## June 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments
N19637-T | Camille Corbi | ROCKFORD | 2025-06-01 | HOURLY | 12000 | 0 | 12000 | Pending locates
N12987 | Taylor Lierow | SCHAUMBURG | 2025-06-01 | HOURLY | 16000 | 0 | 16000 | Redesign, in depth coordination with Village
N18492 | Taylor Lierow | LONG GROVE | 2025-06-01 | 400000 | 40000 | 0 | 40000 | 3 small jumpers - 2 with proposed casing
N18592 | Conner Chamernik | MCHENRY | 2025-06-01 | 100000 | 20593 | 0 | 20593
SC18611-1 REV1 | Camille Corbi | NORMAL | 2025-06-01 | HOURLY | 45000 | 0 | 45000 | Pending
SC25330 | Caroline Kulach | GRANT PARK | 2025-06-01 | 340000 | 34000 | 0 | 34000 | Progressing WO
SC25578 | Matt Hopkins | WILMINGTON | 2025-06-01 | 275000 | 19190 | 0 | 19190 | Release end of May
N14793 | Camille Corbi | WOODSTOCK | 2025-06-01 | HOURLY | 105000 | 0 | 105000
M11560 | Conner Chamernik | Northlake | 2025-06-01 | HOURLY | 10000 | 0 | 10000
SC23749 | Matt Hopkins | Manteno | 2025-06-01 | HOURLY | 7000 | 0 | 7000
M16177 | Matt Hopkins | Rosemont | 2025-06-01 | HOURLY | 14000 | 0 | 14000
N17865-1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-06-01 | 873425.47 | 87342.547 | 0 | 87342.547
N17865-T | Conner Chamernik | ELK GROVE VILLAGE | 2025-06-01 | 3071698.32 | 307169.832 | 0 | 307169.832
N17865 REV 1 | Conner Chamernik | ELK GROVE VILLAGE | 2025-06-01 | HOURLY | 9912.5 | 0 | 9912.5
M12594 | Caroline Kulach | NILES | 2025-07-01 | 380000 | 38000 | 0 | 38000 | Pending UCM Response
M15984 | Matt Hopkins | Berwyn | 2025-07-01 | 650000 | 65000 | 0 | 65000 | 8" Jumpers, conservative estimate. Pending Locates
SC25507-T | Mark Stanley | LOCKPORT | 2025-07-01 | HOURLY | 15000 | 0 | 15000 | KH completing UCM to issue to DOT
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-08-01 | HOURLY | 630000 | 484740 | 145260
N15864 | Caroline Kulach | MCHENRY | 2025-07-01 | 130000 | 13000 | 0 | 13000 | Pending locates
M15242-T | Taylor Lierow | BERWYN | 2025-07-01 | HOURLY | 8500 | 0 | 8500 | Anticipate NOO
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-07-01 | 250000 | 25000 | 0 | 25000
N19534 | Randy Castellon | STERLING | 2025-07-01 | 150000 | 15000 | 0 | 15000
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-07-01 | HOURLY | 14000 | 0 | 14000
SC24663 | Conner Chamernik | OLYMPIA FIELDS | 2025-07-01 | 500000 | 50000 | 0 | 50000
SC25712 | Matt Hopkins | PONTIAC | 2025-07-01 | 110000 | 11000 | 0 | 11000 | Release beginning of June
SC25757 | Caroline Kulach | ST CHARLES | 2025-07-01 | 50000 | 5000 | 0 | 5000 | Pending locates
SC25775 | Marissa LaPorte | PLAINFIELD | 2025-07-01 | 100000 | 10000 | 0 | 10000
SC25832 | Taylor Lierow | BRADLEY | 2025-07-01 | 1000000 | 100000 | 0 | 100000 | 1,300' of proposed 8" relocation
SC25858 | Marissa LaPorte | PLAINFIELD | 2025-07-01 | 150000 | 15000 | 0 | 15000
SC25957 | Camille Corbi | GILMAN | 2025-07-01 | 150000 | 15000 | 0 | 15000
N18293-T | Mark Stanley | N BARRINGTON | 2025-08-01 | HOURLY | 21000 | 0 | 21000 | Pending updated PF plans from DOT
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-09-01 | HOURLY | 300000 | 146400 | 153600
N16744 NIS | Randy Castellon | Crystal Lake | 2025-09-01 | HOURLY | 300000 | 0 | 300000
N17019 | Ethan Ekstrom | MT PROSPECT | 2025-08-01 | 1500000 | 150000 | 0 | 150000 | Large relocation along cook county road
N17141 | Randy Castellon | HUNTLEY | 2025-08-01 | 530000 | 53000 | 0 | 53000
N17925 | Randy Castellon | HOFFMAN ESTATES | 2025-08-01 | 350000 | 35000 | 0 | 35000
N19472 | Caroline Kulach | HANOVER PARK | 2025-08-01 | 130000 | 13000 | 0 | 13000 | Pending UCM response
N19216-T | Mark Stanley | ROCKFORD | 2025-08-01 | HOURLY | 25000 | 0 | 25000 | Pending PF plans
N19731 | Taylor Lierow | MACHESNEY PARK | 2025-08-01 | 550000 | 55000 | 0 | 55000 | ~300'/400' of 8" relocation
SC21396 | Randy Castellon | NEW LENOX | 2025-08-01 | 500000 | 50000 | 0 | 50000
SC21396-1 | Randy Castellon | NEW LENOX | 2025-08-01 | 1700000 | 170000 | 113895 | 56105
SC23762 | Randy Castellon | LOCKPORT | 2025-08-01 | 450000 | 45000 | 0 | 45000
SC23843-T | Matt Hopkins | PILOT | 2025-08-01 | HOURLY | 15000 | 0 | 15000 | Anticipate coordination with Engineering, Land, & Corrosion to close project out
SC25259-T | Mark Stanley | ELWOOD | 2025-08-01 | HOURLY | 35000 | 0 | 35000 | Pending PF plans; KH coordinating reimbursable work with Nicor.
SC25188 | Ethan Ekstrom | BLOOMINGTON | 2025-08-01 | 750000 | 75000 | 0 | 75000 | Multiple jumpers with a lot of removal
SC25811-T | Matt Hopkins | OAKBROOK TERRACE | 2025-08-01 | HOURLY | 8000 | 0 | 8000 | Anticipate coordination with Engineering & Land to close out project
SC25745 | Caroline Kulach | FORD HEIGHTS | 2025-08-01 | 50000 | 5000 | 0 | 5000 | Pending locates
SC25777 | Taylor Lierow | WESTMONT | 2025-08-01 | 800000 | 80000 | 0 | 80000
M16521-T | Matt Hopkins | BENSENVILLE | 2025-09-01 | HOURLY | 8000 | 0 | 8000 | Anticpate NOO with Transmission Section
M15898-T | Mitchell Pohlman | GLENVIEW | 2025-09-01 | HOURLY | 10000 | 0 | 10000
SC24452-T | Mark Stanley | JOLIET | 2025-10-01 | HOURLY | 30000 | 0 | 30000 | Pending PF plans
Billing Month | Anticipated Fee | Anticipated Net Fee
2025-05-01 | 0 | 0
2025-06-01 | 727207.879 | 727207.879
2025-07-01 | 399500 | 399500
2025-08-01 | 1465000 | 866365
2025-09-01 | 618000 | 471600
2025-10-01 | 30000 | 30000
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt updated this per ompleted projects

## July 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments
M12594 | Caroline Kulach | NILES | 2025-09-01 | 380000 | 38000 | 0 | 38000 | Pending UCM Response
M15242-T | Taylor Lierow | BERWYN | 2025-08-01 | HOURLY | 10100 | 0 | 10100 | Anticipate NOO
M15898-T | Mitchell Pohlman | GLENVIEW | 2025-09-01 | HOURLY | 10000 | 0 | 10000
M15984 | Matt Hopkins | Berwyn | 2025-09-01 | 450000 | 45000 | 0 | 45000 | 3 2" Jumpers, conservative estimate.
M16521-T | Matt Hopkins | BENSENVILLE | 2025-09-01 | HOURLY | 8000 | 0 | 8000 | Anticpate NOO with Transmission Section, coordination needed for potholes.
N10173 | Randy Castellon | HAWTHORN WOODS | 2025-08-01 | HOURLY | 630000 | 484740 | 145260
N12987 | Taylor Lierow | SCHAUMBURG | 2025-07-01 | HOURLY | 20000 | 0 | 20000 | Redesign, in depth coordination with Village
N14793 | Camille Corbi | WOODSTOCK | 2025-07-01 | HOURLY | 105000 | 0 | 105000
N15864 | Caroline Kulach | MCHENRY | 2025-08-01 | 150000 | 15000 | 0 | 15000 | Phase 2 (800' of 2" PE relocation). Pending confirmation on 90' of 8" STL jumper
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-09-01 | HOURLY | 300000 | 146400 | 153600
N16744 NIS | Randy Castellon | Crystal Lake | 2025-09-01 | HOURLY | 300000 | 0 | 300000
N17019 | Ethan Ekstrom | MT PROSPECT | 2025-09-01 | 1500000 | 150000 | 0 | 150000 | Large relocation along cook county road
N17141 | Randy Castellon | HUNTLEY | 2025-08-01 | 530000 | 53000 | 0 | 53000 | This might be NOO. LMK if you want to change this cost
N17925 | Randy Castellon | HOFFMAN ESTATES | 2025-08-01 | 300000 | 30000 | 0 | 30000 | Minor conflicts. If unable to adjsut from UCM to be provided on 6/18, i anticipate this cost to be higher.
N18293-T | Mark Stanley | N BARRINGTON | 2025-08-01 | HOURLY | 21000 | 0 | 21000 | Pending updated PF plans from DOT
N18492 | Taylor Lierow | LONG GROVE | 2025-08-01 | 400000 | 40000 | 0 | 40000 | 3 small jumpers - 2 with proposed casing
N19030 | Conner Chamernik | ROUND LAKE BEACH | 2025-07-01 | 250000 | 25000 | 0 | 25000 | 2 sheet 2" PE relocation, releasing at EOM June.
N19216-T | Mark Stanley | ROCKFORD | 2025-11-01 | HOURLY | 25000 | 0 | 25000 | Pending PF plans; KH coordinating reimbursable work with Nicor.
N19472 | Caroline Kulach | HANOVER PARK | 2025-08-01 | 200000 | 20000 | 0 | 20000 | Smaller relocation scope
N19637-T | Camille Corbi | ROCKFORD | 2025-07-01 | HOURLY | 13000 | 0 | 13000 | Pending locates
N19731 | Taylor Lierow | MACHESNEY PARK | 2025-09-01 | 550000 | 55000 | 0 | 55000 | ~300'/400' of 8" relocation
SC18611-1 REV1 | Camille Corbi | NORMAL | 2025-07-01 | HOURLY | 45000 | 0 | 45000 | Pending finalized plans
SC21396 | Randy Castellon | NEW LENOX | 2025-07-01 | 1100000 | 110000 | 0 | 110000
SC21396-1 | Randy Castellon | NEW LENOX | 2025-07-01 | 1177325 | 117732.5 | 113895 | 3837.5
SC23749 | Matt Hopkins | Manteno | 2025-07-01 | HOURLY | 5000 | 0 | 5000 | Anticipating release in June
SC23762 | Randy Castellon | LOCKPORT | 2025-08-01 | 450000 | 45000 | 0 | 45000 | This may be NOO, however we may be able to make this hourly for the work done.
SC23843-T | Matt Hopkins | PILOT | 2025-08-01 | HOURLY | 15000 | 0 | 15000 | Anticipate coordination with Engineering, Land, & Corrosion to close project out
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-08-01 | HOURLY | 14000 | 0 | 14000 | Potential scope depends on SC25775 meeting
SC24452-T | Mark Stanley | JOLIET | 2025-11-01 | HOURLY | 22000 | 0 | 22000 | Pending PF plans, expected in late Summer or early Fall.
SC24663 | Conner Chamernik | OLYMPIA FIELDS | 2025-07-01 | 500000 | 50000 | 0 | 50000 | ~2,900' of 2" PE
SC25188 | Ethan Ekstrom | BLOOMINGTON | 2025-09-01 | 750000 | 75000 | 0 | 75000 | Multiple jumpers with a lot of removal
SC25259-T | Mark Stanley | ELWOOD | 2025-08-01 | HOURLY | 35000 | 0 | 35000 | Pending PF plans; KH coordinating reimbursable work with Nicor.
SC25330 | Caroline/Taylor | GRANT PARK | 2025-07-01 | 650000 | 65000 | 0 | 65000 | Cost estimate meeting 6/18
SC25507-T | Mark Stanley | LOCKPORT | 2025-07-01 | HOURLY | 11000 | 0 | 11000 | KH completing UCM to issue to DOT
SC25712 | Matt Hopkins | PONTIAC | 2025-07-01 | 190000 | 19000 | 0 | 19000 | Release beginning of June
SC25745 | Caroline Kulach/Matt Hopkins | FORD HEIGHTS | 2025-09-01 | 200000 | 20000 | 0 | 20000 | 1,000' 2" PE Relocation
SC25757 | Caroline Kulach | ST CHARLES | 2025-07-01 | 50000 | 5000 | 0 | 5000 | Pending locates
SC25775 | Marissa LaPorte | PLAINFIELD | 2025-09-01 | 100000 | 10000 | 0 | 10000 | Pending scope meeting scheduled for 6/16
SC25777 | Taylor Lierow | WESTMONT | 2025-10-01 | 800000 | 80000 | 0 | 80000
SC25811-T | Matt Hopkins | OAKBROOK TERRACE | 2025-08-01 | HOURLY | 8000 | 0 | 8000 | Anticipate coordination with Engineering & Land to close out project
SC25832 | Taylor Lierow | BRADLEY | 2025-07-01 | 800000 | 80000 | 0 | 80000 | 1,300' of proposed 8" relocation
SC25858 | Marissa LaPorte | PLAINFIELD | 2025-07-01 | 200000 | 20000 | 0 | 20000
SC25957 | Camille Corbi | GILMAN | 2025-08-01 | 150000 | 15000 | 0 | 15000 | Pending developer plans
Billing Month | Anticipated Fee | Anticipated Net Fee
2025-05-01 | 0 | 0
2025-06-01 | 0 | 0
2025-07-01 | 690732.5 | 576837.5
2025-08-01 | 951100 | 466360
2025-09-01 | 1011000 | 864600
2025-10-01 | 80000 | 80000
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt I see 650k as the number you had helped me enter previously - did that go down? Reply: yes, i really don't have a good grasp on this project until we get a UCM response. I know 3 separate 2" jumpers for direct conflicts discovered in the field. I am trying to overshoot since these forecasts are sent to Nicor, I thought 450,000 would be a conservative estimate in case we need to extend the jumpers compared to 650,000

## August 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments | Project Location Code
SC18611-1 | Camille Corbi (Matt Hopkins) | NORMAL | 2025-09-01 | HOURLY | 45000 | 0 | 45000 | T&M -Pending finalized drainage and grading plans. | 2 | Billing Month | Anticipated Fee | Anticipated Net Fee
SC25957 | Camille Corbi (Caroline Kulach) | GILMAN | 2025-12-01 | 150000 | 15000 | 0 | 15000 | Pending plans to know how much main is in conflict. | 1 | 2025-08-01 | 17666 | 17666
M12594 | Caroline Kulach | NILES | 2025-11-01 | 340000 | 34000 | 0 | 34000 | Pending final UCM confirmation | 1 | 2025-09-01 | 45000 | 45000
N19472 | #REF! | #REF! | Number not Found | 625000 | 62500 | 0 | 62500 | 8" and 6" install | 3 | 2025-10-01 | 61000 | 61000
SC25745 | Caroline Kulach | FORD HEIGHTS | 2025-11-01 | 350000 | 35000 | 0 | 35000 | 2" install | 1 | 2025-11-01 | 372043 | 372043
N17925 | Conner Chamernik | HOFFMAN ESTATES | 2025-10-01 | 250000 | 25000 | 0 | 25000 | Potential 2" Stream relocaiton | 1 | 2025-12-01 | 840000 | 693600
SC25188 | Ethan Ekstrom | BLOOMINGTON | 2025-11-01 | 750000 | 75000 | 0 | 75000 | Multiple jumpers with a lot of removal | 1
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-11-01 | 0 | 0 | 0 | 0 | No relocation - Nicor negotating reimbursment for prootection around vault. | 1
N18293-T | #REF! | #REF! | Number not Found | HOURLY | 24217 | 0 | 24217 | T&M - | 3
N19216-T | #REF! | #REF! | Number not Found | HOURLY | 24798 | 0 | 24798 | T&M - | 3
SC24452-T | #REF! | #REF! | 2025-11-01 | HOURLY | 21643 | 0 | 21643 | T&M - | 3
SC25259-T | #REF! | #REF! | Number not Found | HOURLY | 43346 | 0 | 43346 | T&M - | 3
SC25895-T | #REF! | #REF! | 2025-08-01 | HOURLY | 17666 | 0 | 17666 | T&M - | 3
SC26238 | Mark Stanley | PONTIAC | 2025-11-01 | 34000 | 3400 | 0 | 3400 | No relocation anticipated. Pending MAOP verification to complete final blas analysis. | 1
M15984 | Matt Hopkins | BERWYN | 2025-11-01 | 450000 | 45000 | 0 | 45000 | Pending UCM response, 3 2" PE jumpers at minimum | 1
M16521-T | #REF! | #REF! | Number not Found | HOURLY | 8900 | 0 | 8900 | T&M - | 3
SC23843-T | #REF! | #REF! | Number not Found | HOURLY | 14000 | 0 | 14000 | T&M - | 3
SC25811-T | #REF! | #REF! | Number not Found | HOURLY | 8000 | 0 | 8000 | T&M - | 3
N19953 | Matt Hopkins / Nick Watt | ELK GROVE VILLAGE | 2025-10-01 | 250000 | 25000 | 0 | 25000 | Anticipate 6" jumper required in addition to retirement. Pending potholes to confirm scope | 1
N19953-T | #REF! | #REF! | 2025-10-01 | HOURLY | 11000 | 0 | 11000 | T&M - Coordination for 20" TR line | 3
M15898-T | Number not Found | Number not Found | Number not Found | HOURLY | 21100 | 0 | 21100 | T&M - | 0
N10173 | Number not Found | Number not Found | Number not Found | HOURLY | 650000 | 484740 | 240000 | T&M - JPB UPDATED FEE NUMBER TO ACCOUNT FOR HOURLY CONVERSION | 0
N14793 | Number not Found | Number not Found | Number not Found | HOURLY | 122765 | 0 | 122765 | T&M - Finalizing for release. | 0
N15864 | Number not Found | Number not Found | Number not Found | 480000 | 48000 | 0 | 48000 | Large open cut section | 0
N17865-T/-1 | Number not Found | Number not Found | 2025-07-01 | HOURLY | 3750 | 0 | 3750 | T&M - We are only going to be able to bill ~20-25% of our effort | 0
N19637-T | Number not Found | Number not Found | Number not Found | HOURLY | 13000 | 0 | 13000 | T&M - Pending developer's confirmation on clearances, then release as NOO. | 0
SC23070 | Number not Found | Number not Found | Number not Found | HOURLY | 5500 | 0 | 5500 | T&M - pending Nicor confirmation to close. | 0
SC25775 | Number not Found | Number not Found | Number not Found | 0 | 0 | 0 | 0 | Closing out project as NOO. | 0
SC25858 | Number not Found | Number not Found | Number not Found | 800000 | 80000 | 0 | 80000 |  | 0
N14920 | Randy Castellon | HUNTLEY | 2025-11-01 | 250000 | 25000 | 0 | 25000 |  | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-12-01 | HOURLY | 300000 | 146400 | 153600 | T&M | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-12-01 | HOURLY | 300000 |  | 300000 | T&M - This is the NIS portion for Crystal Lake
N17141 | Randy Castellon | HUNTLEY | 2025-11-01 | 530000 | 53000 | 0 | 53000 | This will most likely be NOO. | 1
M15242-T | #REF! | #REF! | Number not Found | HOURLY | 9706 | 0 | 9706 | T&M - | 3
SC25777 | Taylor Lierow | WESTMONT | 2025-11-01 | 800000 | 80000 | 0 | 80000 | Pending Pre-Final plans, anticipated in September. | 1
N17019 | Taylor Lierow/Ethan Ekstrom | MT PROSPECT | 2025-12-01 | 1500000 | 150000 | 0 | 150000 | Large relocation along cook county road | 1
N18185 | Taylor Lierow/Michael Molloy | ELGIN | 2025-12-01 | 750000 | 75000 | 0 | 75000 | Anticipate releasing in December, will send date extension after UCM is sent. | 1
Note on J1: Number assigned to project based on which table the Engineering Number is found in. Uses unique Engineering numbers determined in the Engineering Numbers Ref sheet.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @LaPorte, Marissa have we discussed with Nicor to bill this hourly or is this an assumption? If we haven’t yet we should bring that up soon if we feel we have justification. Or if there’s likely going to be relocation we should have this be the 10% rate Reply: This was an assumption. I can discuss with Eric how we want to handle this with Nicor Reply: Typically if it's NOO we don't get to invoice it. However, if we had been told to move on design or something originally we could, but I didn't think that was the case here. We can discuss further but to be conservative i would assume no bill
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt @Stanley, Mark @Pohlman, Mitchell @Corbi, Camille @Chamernik, Conner @Lierow, Taylor can you all review these dates in yellow and if necessary, hard code them to the month you anticipate these projects being released? I have a hard time believing we’ll be releasing quite a few of them all in one month like we show in August?
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Stanley, Mark @Dina, Eric maybe i'm not familiar with this one and why it would be hourly? have we had that confirmed by nicor? Reply: No relo anticipated, shouldn’t that be zero anticipated cost then?
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @LaPorte, Marissa @Dina, Eric why do we think this would be hourly if we are negotiating out of it? Reply: This is still in detailed analysis. we are negotiating out of this project. I think the hourly was a mistake. Reply: This looks like a mistake. Updating to zero
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy @Molloy, Michael there should be an NIS portion associated with this project that I think got deleted from last month - not sure how that works with the formulas ya’ll have entered here so I’m bumping up the overall hourly fee

## Sep 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments | Project Location Code
SC21396 | Randy Castellon | New Lenox | 2025-08-01 | HOURLY | 7805 | 0 | 7805 | Released 8/12 | 0
SC25775 | Marissa LaPorte | Plainfield | 2025-08-01 | 0 | 0 | 0 | 0 | Negotiated Out Of on 8/13 | 0
N18674 | Ethan Ekstrom | Prospect Heights | 2025-08-01 | HOURLY | 1720 | 0 | 1720 | Released 8/12 | 0
N10173 | Randy Castellon | Hawthorn Woods | 2025-08-01 | HOURLY | 650000 | 484740 | 375000 | T&M - JPB UPDATED FEE NUMBER TO ACCOUNT FOR HOURLY CONVERSION
N19731 | Taylor Lierow | MACHESNEY PARK | 2025-10-01 | 400000 | 40000 | 0 | 40000 | Shactee to provide cost estimate | 1
SC18611-1 | Camille Corbi (Matt Hopkins) | NORMAL | 2025-09-01 | HOURLY | 61980 | 0 | 61980 |  | 2
SC25745 | Caroline Kulach | FORD HEIGHTS | 2025-11-01 | 300000 | 30000 | 0 | 30000 |  | 1
N17925 | Conner Chamernik | HOFFMAN ESTATES | 2025-10-01 | 175000 | 17500 | 0 | 17500 |  | 1
N17141 | Randy Castellon | HUNTLEY | 2025-11-01 | 380000 | 38000 | 0 | 38000 | Project might be NOO, or reduced scope. | 1
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-11-01 | 0 | 0 | 0 | 0 |  | 1
N17936 | Camille Corbi (Matt Hopkins) | ARLINGTON HEIGHTS | 2025-11-01 | 350000 | 35000 | 0 | 35000 | Locates due back EOD 8/14, locates to determine NOO or scope. | 1
M15984 | Matt Hopkins | BERWYN | 2025-11-01 | 450000 | 45000 | 0 | 45000 |  | 1
SC25188 | Ethan Ekstrom | BLOOMINGTON | 2025-11-01 | 800000 | 80000 | 0 | 80000 |  | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-11-01 | HOURLY | 325000 | 146400 | 178600 | Rate base. | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-11-01 | HOURLY | 325000 |  | 325000 | NIS. | 1
N18185 | Taylor Lierow/Michael Molloy | ELGIN | 2025-11-01 | 750000 | 75000 | 0 | 75000 |  | 1
N19953 | Matt Hopkins / Nick Watt | ELK GROVE VILLAGE | 2025-11-01 | 250000 | 25000 | 0 | 25000 |  | 1
N14920 | Randy Castellon | HUNTLEY | 2025-11-01 | 350000 | 35000 | 0 | 35000 | Pending UCM | 1
M12594 | Caroline Kulach | NILES | 2025-11-01 | 340000 | 34000 | 0 | 34000 |  | 1
SC26238 | Mark Stanley | PONTIAC | 2025-11-01 | 340000 | 34000 | 0 | 34000 |  | 1
SC25777 | Taylor Lierow | WESTMONT | 2025-11-01 | 800000 | 80000 | 0 | 80000 |  | 1
M16521 | Matt Hopkins | BENSENVILLE | 2025-12-01 | 250000 | 25000 | 0 | 25000 | Detailed Analysis phase pending plans, no cost yet. 20'' TR portion most likely to be NOO. | 1
M12980 | Randy Castellon | LAGRANGE PARK | 2025-12-01 | 450000 | 45000 | 0 | 45000 | Pending prefinal plans, assuming scope reduced as well. | 1
N17019 | Taylor Lierow/Ethan Ekstrom | MT PROSPECT | 2025-12-01 | 1500000 | 150000 | 0 | 150000 |  | 1
SC25957 | Camille Corbi (Caroline Kulach) | GILMAN | 2026-01-01 | 150000 | 15000 | 0 | 15000 | Pending developer plans to determine relocation scope. RGC Update: Truly unkown, most likely to be a relocation. No preliminary plans provided. | 1
SC20310 | Randy Castellon | SHERIDAN | 2026-01-01 | 0 | 0 | 0 | 0 | Pending Pre-final plans, 4" mop in potential conflict with box culvert. Helix locates showed deeper than culver though. | 1
SC24323 | Camille Corbi | NEW LENOX | 2026-02-01 | 800000 | 80000 | 0 | 80000 | Prefinal anticipated October 2025. | 1
SC25268 | Camille Corbi | NEW LENOX | 2026-02-01 | 800000 | 80000 | 0 | 80000 | Prefinal anticipated October 2025. | 1
N13882 | Randy Castellon | MUNDELEIN | 2026-03-01 | 500000 | 50000 | 0 | 50000 | Pending pre-final plans this fall/winter. This estiamte is based off 4" relo only, assuming the full true relocation may offset costs. | 1
SC18317 | Taylor Lierow | TROY | 2026-06-01 | 500000 | 50000 | 0 | 50000 | Pending Preliminary plans - gas main attached to bridge will need to be relocated. | 1
N14644 | Camille Corbi | WHEELING | 2026-09-01 | 700000 | 70000 | 0 | 70000 | Prelim 2 mi roadway reconstruction project/prefinal anticipated July 2026. | 1
N19472 | #REF! | #REF! | Number not Found | 625000 | 62500 | 0 | 62500 |  | 3
[10 empty] | September |  |  | August
[10 empty] | Billing Month | Anticipated Fee | Anticipated Net Fee | Billing Month | Anticipated Fee | Anticipated Net Fee
[10 empty] | 2025-08-01 | 659525 | 384525 | 2025-08-01 | 17666 | 17666
[10 empty] | 2025-09-01 | 61980 | 61980 | 2025-09-01 | 112563 | 112563
[10 empty] | 2025-10-01 | 57500 | 57500 | 2025-10-01 | 869206 | 722806
[10 empty] | 2025-11-01 | 1161000 | 1014600 | 2025-11-01 | 297841 | 297841
[10 empty] | 2025-12-01 | 220000 | 220000 | 2025-12-01 | 233900 | 233900 |  | Difference
[11 empty] | 2160005 | 1738605 |  | 1531176 | 1384776 |  | 628829 | 353829
Fee
[16 empty] | Increase | 50k CL | 50000 | Crystal Lake
[16 empty] | Increase | 15k | 15000
[16 empty] | Decrease | 12.5k | -12500
[16 empty] | Increase | 8750 | 8750
[16 empty] | Increase | 25k | 25000
[16 empty] | Decrease | 5k | -5000
[16 empty] | Increase | 45k | 45000 | LaGrange
[16 empty] | Decrease | 15k | -15000
[16 empty] | Increase | 7800 | 7800
[16 empty] | Increase | 40k | 40000 | Machesney
[18 empty] | 35000 | Arlington
194050
Note on J1: Number assigned to project based on which table the Engineering Number is found in. Uses unique Engineering numbers determined in the Engineering Numbers Ref sheet.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric @Castellon, Randy isn’t this more like $375k? Reply: Updated from 240 to 375 just for record

## October 2025
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments | Project Location Code
M12594 | Caroline Kulach | NILES | 2025-11-01 | 100000 | 10000 | 0 | 10000 | From PCTS estimate | 1
M12980 | Randy Castellon | LAGRANGE PARK | 2025-11-01 | 300000 | 30000 | 0 | 30000 |  | 1
M15984 | Matt Hopkins | BERWYN | 2025-11-01 | 150000 | 15000 | 0 | 15000 |  | 1
M16521 | Matt Hopkins | BENSENVILLE | 2026-02-01 | 250000 | 25000 | 0 | 25000 |  | 1
N13882 | Randy Castellon | MUNDELEIN | 2025-11-01 | 500000 | 50000 | 0 | 50000 |  | 1
N14644 | Camille Corbi | WHEELING | 2026-01-01 | 700000 | 70000 | 0 | 70000 |  | 1
N14920 | Randy Castellon | HUNTLEY | 2025-11-01 | 400000 | 40000 | 0 | 40000 |  | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-12-01 | 350000 | 35000 | 0 | 35000 | Rate Base | 1
N16744 | Randy Castellon | CRYSTAL LAKE | 2025-12-01 | HOURLY | 325000 |  | 325000 | NIS.
N17019 | Taylor Lierow/Ethan Ekstrom | MT PROSPECT | 2025-12-01 | 1500000 | 150000 | 0 | 150000 |  | 1
N17141 | Randy Castellon | HUNTLEY | 2025-11-01 | 380000 | 38000 | 0 | 38000 |  | 1
N17925 | Conner Chamernik | HOFFMAN ESTATES | 2025-10-01 | 175000 | 17500 | 0 | 17500 |  | 1
N17936 | Camille Corbi (Matt Hopkins) | ARLINGTON HEIGHTS | 2025-11-01 | 125000 | 12500 | 0 | 12500 | Filled out on behalf of Camille | 1
N18185 | Taylor Lierow/Michael Molloy | ELGIN | 2026-03-01 | 750000 | 75000 | 0 | 75000 | Design pending several items, including easement feasability. High level anticipated cost. Nicor isnt pushing on this one too much so anticipating this going into next year. | 1
N19472 | Caroline Kulach | Hanover Park | 2025-10-01 | 750000 | 75000 | 0 | 75000 | From PCTS estimate | 3
N19472 (ADA) | Caroline Kulach | Hanover Park | 2026-03-01 | Hourly | 3600 |  | 3600 | ADA | 0
N19731 | Taylor Lierow | MACHESNEY PARK | 2025-10-01 | 300000 | 30000 | 0 | 30000 | Reduced scope led to cost estimate decrease | 1
N19953 | Matt Hopkins / Nick Watt | ELK GROVE VILLAGE | 2025-10-01 | 100000 | 10000 | 0 | 10000 |  | 1
N20224 | Randy Castellon | ELGIN | 2025-11-01 | 150000 | 15000 | 0 | 15000 |  | 1
SC18317 | Taylor Lierow | TROY | 2025-06-01 | 500000 | 50000 | 0 | 50000 | Pending Preliminary plans - gas main attached to bridge will need to be relocated. | 1
SC18611-1 | Camille Corbi (Matt Hopkins) | NORMAL | 2025-10-01 | Hourly | 63000 |  | 63000 | Filled out on behalf of Camille | 2
SC20310 | Randy Castellon | SHERIDAN | 2025-11-01 | - | - | 0 | - |  | 1
SC23981 | Marissa LaPorte | WHEATLAND TWP | 2025-11-01 |  | 0 | 0 | 0 |  | 1
SC24323 | Camille Corbi | NEW LENOX | 2025-12-01 | 800000 | 80000 | 0 | 80000 |  | 1
SC25188 | Ethan Ekstrom | BLOOMINGTON | 2025-11-01 | 200000 | 20000 | 0 | 20000 | Non-reimbursable | 1
SC25188-1 | Ethan Ekstrom | BLOOMINGTON | 2025-11-01 | 500000 | 50000 | 0 | 50000 | Reimbursable, pending reimbursement coordination between Nicor and project owner (BNWRD) | 1
SC25268 | Camille Corbi | NEW LENOX | 2025-12-01 | 800000 | 80000 | 0 | 80000 |  | 1
SC25745 | Caroline Kulach | FORD HEIGHTS | 2025-11-01 | 400000 | 40000 | 0 | 40000 | From PCTS estimate | 1
SC25777 | Taylor Lierow | WESTMONT | 2025-11-01 | 600000 | 60000 | 0 | 60000 | A street of services no longer need to be transferred over - anticipated cost decreased from past months. | 1
SC25957 | Camille Corbi (Caroline Kulach) | GILMAN | 2025-12-01 | 150000 | 15000 | 0 | 15000 | Filled out on behalf of Camille | 1
SC26238 | Mark Stanley | PONTIAC | 2025-11-01 | 340000 | 34000 | 0 | 34000 | Project scope not confirmed, may not become a relocation. | 1
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  | 0 | 0 | 0 |  | 0
October
[10 empty] | Billing Month | Anticipated Fee | Anticipated Net Fee
[10 empty] | 2025-08-01 | 0 | 0
[10 empty] | 2025-09-01 | 0 | 0
[10 empty] | 2025-10-01 | 195500 | 195500
[10 empty] | 2025-11-01 | 414500 | 414500
[10 empty] | 2025-12-01 | 685000 | 685000
Note on J1: Number assigned to project based on which table the Engineering Number is found in. Uses unique Engineering numbers determined in the Engineering Numbers Ref sheet.

## Month Template (hidden)
Engineering Number | Designer Name | Town | Anticipated Billing Month | Anticipated Cost | Anticipated Fee | Amount previously billed | Net Fee | Comments | Project Location Code
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
| Number not Found | Number not Found | Number not Found |  |  |  | 0 |  | 0
Note on J1: Number assigned to project based on which table the Engineering Number is found in. Uses unique Engineering numbers determined in the Engineering Numbers Ref sheet.

## Engineering Numbers Ref (hidden)
This tab will produce an updated list of the unique engineering numbers listed in the referenced spreadsheets
1 | 2 | 3 | 4
Nicor DI Project Status DOT Projects | Nicor DI Project Status T&M | Nicor TR Project Status DOT TR | Nicor TR Project Status T&M
Engineering Number | Eng Number | Engineering Number | Engineering Number
SC24323 | COR1059-2/-3 | SC25259-T | TP645B
SC25268 | COR1060 | SC24452-T | TC571
N14644 | COR1073 | N18293-T | BS520
SC25957 | BS550-1 | N19216-T
N17936 | BS388 | SC25895-T
M12594 | BS588 | N20162-T
SC25745 | MR1926 | SC26684-T
N19472 | VW50 | SC25811-T
N17925 | MR1913 | SC23843-T
SC26438 | SC18611-1 | M16521-T
SC25188 | N19472 | N19953-T
SC25188-1 | NBA10015039 | M15242-T
SC23981 | RS988
SC26238 | -
M15984 | RS1218
M16521 | N14359-1
N19953-1 | RS939
N19953 | NBA10013465
N20224 | RS1213
SC20310
N17141
N13882
N16723
N14920
M12980
N16744
SC18317
SC25777
N19731
N17019
N18185