## Staffing
Project Type | Engineering Number | WO | Town | Project Lead | Service | Sheets | Anticipated NTP | NTP | Expected Completion | Deliverables Received | Debrief | Contractor Selected | Scope/Notes | LG Drawing [Y or N] | KH Billing # | Anticipated Fee | Anticipated Nicor Report Month | Billed/ Reported to Nicor?
DOT | N14793 | 1213270 | WOODSTOCK | Camille Corbi | BL/D QC | 53 | 2023-12-15 | 2023-12-15 | 2023-12-20 | 2023-12-20 | N/A | Shactee | 53 Sheets - BL/D QC - South | Y | 168777007.D.081 | 3582.5 | N/A | N | Avg $/Hr
DOT | M13270 | 1213483 | WESTERN SPRINGS | Camille Corbi | BL | 2 | 2024-01-09 | 2024-01-08 | 2024-01-16 | 2024-01-17 | 2024-01-23 | Shactee | 2 Sheets - 2" PE | N | 168777007.D.128 | N/A | N/A | N/A | #REF!
DOT | N16379 | 1213525 | CHICAGO | Camille Corbi | BL | 1 | 2024-01-19 | 2024-01-19 | 2024-01-23 | 2024-01-30 | 2024-02-06 | Shactee | 1 Sheet - 4" PE | N | 168777007.D.129 | N/A | N/A | N/A
DIMP MR | MR2BID5541 | 1214811 | Oak Park | Camille Corbi | BL/D Review | 12 | 2025-03-05 | 2025-03-05 | 2025-03-10 | 2025-03-10 | N/A | Shactee | Combined Review | N | 168777007.J.011 | 1757.81 | 2025-05-01 | N
DOT | N14793 | 1213271 | WOODSTOCK | Camille Corbi | BL/D QC | 22 | 2024-02-20 | 2024-02-20 | 2024-02-22 | 2024-02-22 | N/A | Shactee | 22 Sheets - BL/D QC - North | Y | 168777007.D.081 | 3665 | N/A | N
Non-DOT | MR2219-1 | 1314926 | AURORA | Camille Corbi | BL | 8 | 2025-06-03 | 2025-06-04 | 2025-06-13 | 2025-06-13 | TBD | Shactee | Pending Survey due back EOD 6/3 | N | 168777007.J.014 | 3000 | 2025-08-01
NBA | NBA10015039 | 1614145 | ELK GROVE VILLAGE | Camille Corbi | BL | 9 | 2024-10-10 | 2024-10-10 | 2024-10-25 | 2024-10-25 | 2024-11-05 | Shactee | 9 Sheets - 12" STL MOP - Pending Survey | N | 168777007.J.508
Non-DOT | MR2203 | 1414506 | WILMINGTON | Camille Corbi | D | 2 | 2024-12-18 | 2024-12-18 | 2025-01-03 | 2025-01-03 | 2024-01-07 | Shactee | 2 Sheets - 12" 60# |  | 168777007.J.007 |  |  | N
Non-DOT | MR2BID9647-2 |  | HOMETOWN | Camille Corbi | BL QC | 40 | 2025-03-24 | 2025-03-24 | 2025-03-26 | 2025-03-26 | N/A | Shactee | Baseline review | N | 168777007.J.303 | 5036.82 |  | N
DOT | SC24292 | 1413931 | PLAINFIELD | Camille Corbi | BL | 13 | 2024-04-29 | 2024-04-29 | 2024-05-08 | 2024-05-10 | 2024-06-11 | Shactee | 9 sheets - 2" PE | N | 168777007.D.150 | N/A | N/A | N/A
CRA | RS1333 | 1015589 | HARRISON | Camille Corbi | BL/D | 1 | 2025-08-20 | 2025-08-20 | 2025-09-10 |  |  | Shactee | Pending Survey due back EOD 8/19 | N | 16877007.G.422 | 6000 | 2025-10-01
DOT | SC24292 | 1413931 | PLAINFIELD | Camille Corbi | D | 13 | 2024-05-29 | 2024-05-29 | 2024-06-05 | 2024-06-05 | 2024-06-11 | Shactee | 13 sheets - 2" PE | N | 168777007.D.150 | N/A | N/A | N/A
DOT | N14793 | 1213270 | WOODSTOCK | Camille Corbi | LG/Permit | 2 | 2024-02-23 | 2024-02-22 | 3/6/2024 3/15/2024 | 2024-09-19 | 2024-10-08 | Shactee | 2 UP Railroad Crossings | Y | 168777007.D.087 | N/A | N/A | N/A
DOT | N14793 | 1213270 | WOODSTOCK | Camille Corbi | LG Drawings/Permit | 4 | 2024-08-27 | 2024-08-27 | 2024-09-23 | 2024-09-19 | 2024-10-08 | Shactee | 4 sheets - 4" STL and 12" STL | Y | 168777007.D.087 | N/A | N/A | N/A
CRA | RS1331 | 1015588 | GOODFIELD | Camille Corbi | BL/D | 1 | 2025-08-11 | 2025-08-11 | 2025-08-28 |  |  | Shactee | Pending Survey due back EOD 8/8 | N | 16877007.G.423 | 6000 | 2025-11-01
DOT | SC18359 | 1314544 | OSWEGO | Camille Corbi | BL | 2 | 2024-11-01 | 2024-11-01 | 2024-11-12 | 2024-11-12 | 2024-11-19 | Shactee | 2 Sheets - 4" - Creek Crossing | N | 168777007.M.032 | 4049 | 2025-03-25 | Y
DOT | SC25418 | 1414948 | NORMAL | Camille Corbi | BL | 2 | 2025-02-05 | 2025-02-05 | 2025-02-12 | 2025-02-12 | 2025-02-18 | Shactee | 2 Sheets - 8" STL | N | 168777007.M.051 | 4234.48 | 2025-03-25 | Y
DOT | SC25418 | 1414948 | NORMAL | Camille Corbi | BL | 2 | 2025-02-05 | 2025-02-05 | 2025-02-12 | 2025-02-12 | 2025-02-18 | Shactee | 2 Sheets - 8" STL | N | 168777007.M.051 | 60 | 2025-03-25 | Y
DOT | N17936 | 1215754 | ARLINGTON HEIGHTS | Camille Corbi | BL | 1 | 2025-08-18 | 2025-08-19 | 2025-08-25 |  |  | Shactee | Pending Nicor Scoping meeting 8/18. | N | 168777007.M.080 | 4500 | 2025-11-01
DOT | SC18359 | 1314544 | OSWEGO | Camille Corbi | D | 3 | 2024-11-13 | 2024-11-13 | 2024-11-21 | 2024-11-21 | 2024-11-26 | Shactee | 3 Sheets - 4" PE | N | 168777007.M.032 | 7174.75 | 2025-03-25 | Y
DOT | SC23103 | 1413899 | Normal | Camille Corbi/ Ethan Ekstrom | BL | 1 | 2024-05-06 | 2024-05-06 | 2024-05-10 | 2024-05-10 | 2024-05-14 | Shactee | 1 sheet - 2" PE | N | 168777007.D.149 | N/A | N/A | N/A
DOT | M15844 | 1213917 | JUSTICE | Camille Corbi/ Ethan Ekstrom | BL | 1 | 2024-05-09 | 2024-05-09 | 2024-05-16 | 2024-05-14 | 2024-05-21 | Shactee | 1 Sheet -2" STL | N | 168777007.D.153 | N/A | N/A | N/A
Non-DOT | MR2203 | 1414506 | WILMINGTON | Camille Corbi/Tom McTigue | BL | 3 | 2024-12-06 | 2024-12-06 | 2024-12-13 | 2024-12-16 | 2024-01-07 | Shactee | 3 Sheets - 12" STL | N | 168777007.J.007 | 9386.47 |  | N
DOT | N19002 | 1214698 | OREGON | Caroline Kulach | D | 4 | 2025-01-20 | 2025-01-13 | 2025-01-20 | 2024-01-20 | 2025-02-04 | Shactee | 4 sheets - 4" PE and 2" PE | N | 168777007.M.041 | 2467.75 | 2025-03-25 | Y
DOT | N19002 | 1214698 | OREGON | Caroline Kulach | BL | 4 | 2024-12-18 | 2024-12-10 | 2024-12-18 | 2024-12-18 | 2025-01-14 | Shactee | 4 sheets - 4" PE and 2" PE | N | 168777007.M.041 | 1567 | 2025-03-25 | Y
DOT | SC25330 | 1415389 | GRANT PARK | Caroline Kulach | BL/D | 3 | 2025-05-07 | 2025-05-07 | 2025-05-21 | 2025-05-21 | 2025-05-27 | Shactee | 3 design sheets - baseline and design | N | 168777007.M.046 | 7924.57 | 2025-07-01 | Y
DOT | N15864 | 1215530 | MCHENRY | Caroline Kulach | BL | 3 | 2025-05-21 | 2025-05-21 | 2025-06-04 | 2025-06-03 | 2025-06-24 | Shactee | 3 design sheets - BL only for now | N | 168777007.M.073 | 4601.39 | 2025-08-01 | N
DOT | SC25757 | 1215541 | ST CHARLES | Caroline Kulach | Service Analysis | N/A | 2025-06-05 | 2025-06-05 | 2025-06-12 | 2025-06-10 | 2025-06-24 | Shactee | Service Analysis | N | 168777007.M.071 | 1200.36 | 2025-07-01 | Y
DOT | N15864 | 1215530 | MCHENRY | Caroline Kulach | D | 3 | 2025-06-13 | 2025-06-13 | 2025-06-20 | 2025-06-20 | 2025-06-24 | Shactee | 3 design sheets | N | 168777007.M.073 | 2332 | 2025-08-01 | N
DOT | SC25745 | 1215541 | FORD HEIGHTS | Caroline Kulach | BL | 7 | 2025-06-17 | 2025-06-17 | 2025-06-27 | 2025-06-26 | 2025-07-15 | Shactee | 6 Sheets - 2" & 4" | N | 168777007.M.064 | 3102.97 | 2025-11-01 | N
DOT | M12594 | 1215629 | NILES | Caroline Kulach | BL | 4 | 2025-07-16 | 2025-07-16 | 2025-07-30 | 2025-07-30 | 2025-08-05 | Shactee | 2 design sheets | N | 168777007.M.054 | 5214.41 | 2025-12-01 | N
DOT | SC25745 | 1215541 | FORD HEIGHTS | Caroline Kulach | D | 5 | 2025-07-30 | 2025-07-31 | 2025-08-12 | 2025-08-07 | 2025-08-19 | Shactee | 5 design sheets | N | 168777007.M.064 | 1529.58 | 2025-11-01 | N
DOT | M12594 | 1215629 | NILES | Caroline Kulach | D | 3 | 2025-08-01 | 2025-08-01 | 2025-08-13 | 2025-08-12 | 2025-09-02 | Shactee | 3 design sheets | N | 168777007.M.054 | 5803.96 | 2025-12-01 | N
DOT | N16541 | 1213072 | ROCKFORD | Conner Chamernik | BL/D Review | 1 | N/A | 2023-12-14 | 2023-12-18 | 2023-12-18 | N/A | Shactee | 1 Sheet - 6" PE | N | 168777007.D.042 | N/A | N/A | N/A
DOT | SC17680 | 1313431 | WHEATON | Conner Chamernik | BL Review | 7 | N/A | 2023-12-14 | 2023-12-18 | 2023-12-18 | N/A | Shactee | 7 Sheets - 2" PE and 6" PE | N | 168777007.D.132 | N/A | N/A | N/A
DOT | SC23200 | 1313169 | WOODRIDGE | Conner Chamernik | BL/D Review | 1 | N/A | 2023-12-21 | 2023-12-27 | 2023-12-27 | N/A | Shactee | 1 Sheet - 2" PE and 6" PE | N | 168777007.D.103 | N/A | N/A | N/A
DOT | N15012 | 1213488 | E DUBUQUE | Conner Chamernik | BL/D Review | 2 | N/A | 2024-01-11 | 2024-01-17 | 2024-01-17 | N/A | Shactee | 2 Sheets - 2" PE and 6" PE | N | 168777007.M.006 | N/A | N/A | N/A
DOT | N18056 | 1213489 | BUFFALO GROVE | Conner Chamernik | BL | 8 | 2024-01-05 | 2024-01-05 | 2024-01-19 | 2024-01-22 | 2024-01-23 | Shactee | 8 Sheets- 2" and 4" PE | N | 168777007.D.127 | N/A | N/A | N/A
DOT | SC23728 | 1213487 | OTTAWA | Conner Chamernik | BL | 7 | 2024-01-09 | 2024-01-09 | 2024-01-19 | 2024-01-22 | 2024-01-30 | Shactee | 7 Sheets - 2" and 4" PE | N | 168777007.D.125 | N/A | N/A | N/A
DOT | N18056 | 1213489 | BUFFALO GROVE | Conner Chamernik | D | 8 | 2024-01-11 | 2024-01-11 | 2024-01-19 | 2024-01-22 | 2024-01-23 | Shactee | 8 Sheets- 2" and 4" PE | N | 168777007.D.127 | N/A | N/A | N/A
DOT | N16431 | 1213707 | ROCK FALLS | Conner Chamernik | BL | 12 | 2024-02-05 | 2024-02-05 | 2024-02-14 | 2024-02-14 | 2024-03-19 | Shactee | 13 Sheets- 2" STL, 4" STL, 4" PE, 6" PE, 12" MOP | N | 168777007.M.009 | N/A | N/A | N/A
DOT | N16291 | 1212843 | PROSPECT HEIGHTS | Conner Chamernik | BL | 7 | 2024-02-26 | 2024-02-27 | 2024-03-14 | 2024-03-20 | 2024-04-02 | Shactee | 7 sheets - 2 and 4" PE | N | 168777007.E.031 | N/A | N/A | N/A
DOT | N16291 | 1212843 | PROSPECT HEIGHTS | Conner Chamernik | D | 7 | 2024-03-25 | 2024-03-25 | 2024-04-08 | 2024-04-02 | 2024-04-02 | Shactee | 7 sheets - 2 and 4" PE | N | 168777007.E.031 | N/A | N/A | N/A
DOT | SC24208 | 1413807 | LOCKPORT | Conner Chamernik | BL | 3 | 2024-04-04 | 2024-04-04 | 2024-04-11 | 2024-04-10 | 2024-04-23 | Shactee | 3 Sheets - 2 and 4" PE | N | 168777007.M.010 | N/A | N/A | N/A
TW | TW4401073 | 1015198 | Ellsworth | Conner Chamernik | D | TBD | TBD |  | TBD |  |  | Shactee | 1 sheet - Tin whislte replacement Design | N | 168777007.H.137 | 5000 | 2025-09-25
DOT | SC24208 | 1413807 | LOCKPORT | Conner Chamernik | D | 3 | 2024-04-11 | 2024-04-11 | 2024-04-18 | 2024-04-18 | 2024-04-23 | Shactee | 3 Sheets - 2 and 4" PE | N | 168777007.M.010 | N/A | N/A | N/A
NON DOT | PRIM718 | 1315392 | GLENDALE HEIGHTS | Conner Chamernik | BL/D | 2 | 2025-05-21 | 2025-05-21 | 2025-06-04 | 2025-06-04 | 2025-06-10 | Shactee | 2 sheets - Install ~670' of 4" PE and ~180' of 2" PE | N | 168777007.J.600 | 7303.38 | 2025-08-25
RS | RS1311 | 1015193 | SYCAMORE | Conner Chamernik | BL/D | 2 | 2025-05-21 | 2025-05-21 | 2025-06-04 | 2025-06-09 | 2025-06-17 | Shactee | 2 sheets - retire TW and install ~300' | N | 168777007.H.147 | 4582.46 | 2025-08-25
DIMP MR | MR2261 | 1415304 | SAUNEMIN | Conner Chamernik | BL/D | 2 | 2025-06-02 | 2025-06-02 | 2025-06-16 | 2025-06-16 | 2025-06-24 | Shactee | 2 sheets- replace ~600' of 2" MOP | N | 168777007.G.001 | 6254.54 | 2025-08-25
NON DOT | PRIM718 | 1315392 | GLENDALE HEIGHTS | Conner Chamernik | BL/D | 2 | 2025-06-12 | 2025-06-17 | 2025-06-17 | 2025-06-20 | N/A | Shactee | 2 sheets - Install ~670' of 4" PE and ~180' of 2" PE | N | 168777007.J.600 | 4490.55 | 2025-08-25
DOT | N17175/ NBA10014004 | 1213141/1213904 | CRYSTAL LAKE | Conner Chamernik | BL/D | 18 | 2024-05-07 | 2024-05-07 | 2024-05-13 | 2024-05-21 | 2024-05-28 | Shactee | 18 sheets - 2" PE | N | 168777007.J.504 | N/A | N/A | N/A
DOT | M11560 | 1214095 | NORTHLAKE | Conner Chamernik | BL | 2 | 2024-06-25 | 2024-06-25 | 2024-07-01 | 2024-07-02 | 2024-07-16 | Shactee | 2 sheets - 6" MOP | N | 168777007.M.011 | N/A | N/A | N/A
DOT | N17890 | 1214109 | CHEMUNG | Conner Chamernik | BL/D | 1 | 2024-07-11 | 2024-07-11 | 2024-07-18 | 2024-07-22 | 2024-07-30 | Shactee | 1 sheet - 2" and 6" STL | N | 168777007.D.157 | N/A | N/A | N/A
DOT | M11560 | 1214095 | NORTHLAKE | Conner Chamernik | D | 3 | 2024-07-16 | 2024-07-16 | 2024-07-23 | 2024-07-23 | 2024-07-30 | Shactee | 3 sheets - 6" MOP | N | 168777007.M.011 | N/A | N/A | N/A
DOT | SC24631 | 1314540 | ST CHARLES | Conner Chamernik | BL | 5 | 2024-10-30 | 2024-10-30 | 2024-11-06 | 2024-11-06 | 2024-11-12 | Shactee | 5 sheets - 4" PE | N | 168777007.M.016 | 5713 | 2025-04-25 | Y
DOT | N17175/NBA10014004 | 1213141 | CRYSTAL LAKE | Conner Chamernik | Revision | 15 | 2024-11-07 | 2024-11-07 | 2024-11-15 | 2024-11-15 | 2024-11-19 | Shactee | 15 sheet- 2" and 4" PE | N | 168777007.E.073 | N/A | N/A | N/A
CRA | RS1249 | 1014139 | ROSELLE | Conner Chamernik | BL/D | 3 | 2025-08-19 | 2025-08-19 | 2025-09-02 | 2025-09-03 | 2025-09-16 | Shactee | Pending survey | N | 168777007.G.606 | 4987.91 | 2025-11-01
DOT | SC24047 | 1414578 | JOLIET | Conner Chamernik | BL | 1 | 2024-11-05 | 2024-11-05 | 2024-11-19 | 2024-11-20 | 2024-11-26 | Shactee | 1 sheet - 2" and 6" STL | N | 168777007.M.040 | N/A | N/A | N/A
DOT | SC24047 | 1414578 | JOLIET | Conner Chamernik | D | 1 | 2024-11-07 | 2024-11-07 | 2024-11-19 | 2024-11-20 | 2024-11-26 | Shactee | 1 sheet - 2" and 6" STL | N | 168777007.M.040 | N/A | N/A | N/A
CRA | RS1302 | 1014897 | DAVISJCT | Conner Chamernik | BL/D | 4 | 2025-07-22 | 2025-07-22 | 2025-07-29 | 2025-08-05 | N/A | Shactee | Scope revised | N | 168777007.G.819 | 4554.78 | TBD
TW | TW4101184 | 1015148 | Monee | Conner Chamernik | BL/D | TBD | TBD |  | TBD |  |  | Shactee | Pending sizing sheet prior to scoping call sent 4/24. | N | 168777007.H.156 | 6000 | TBD | N
DOT | SC24631 | 1314540 | ST CHARLES | Conner Chamernik | D | 7 | 2024-11-18 | 2024-11-18 | 2024-11-25 | 2024-11-25 | 2024-12-03 | Shactee | 7 sheets - 4" PE | N | 168777007.M.016 | 5812.5 | 2025-04-25 | Y
DOT | SC20245 | 1314784 | Carol Stream | Conner Chamernik | BL/D | 2 | 2024-12-20 | 2024-12-20 | 2025-01-10 | 2025-01-10 | 2025-01-21 | Shactee | 2 Sheets - 2" & 4" STL & PE | N | 168777007.M.024 | 6262.21 | 2025-03-25 | Y
DOT | N18592 | 1214908 | McHenry | Conner Chamernik | BL | 1 | 2025-01-24 | 2025-01-24 | 2025-02-03 | 2025-02-03 | 2025-02-04 | Shactee | 1 sheet - 4" PE and STL | N | 168777007.D.152 | 3965.76 | 2025-06-25 | Y
DOT | N13645 | 1215033 | BUFFALO GROVE | Conner Chamernik | BL Review/ D | 10 | 2025-03-03 | 2025-03-04 | 2025-03-14 | 2025-03-14 | N/A | Shactee | 10 Sheets - 2 and 4" | N | 168777007.M.049 | 10197.11 | 2025-04-25 | Y
DOT | N19030 | 1215152 | ROUND LAKE BEACH | Conner Chamernik | BL | 2 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-08 | 2025-04-22 | Shactee | 2 Sheets - 2" PE/STL | N | 168777007.M.027 | 5998.35 | 2025-07-25 | Y
DOT | N19030 | 1215152 | ROUND LAKE BEACH | Conner Chamernik | D | 2 | 2025-05-15 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-06-03 | Shactee | 2 Sheets - 2" PE/STL | N | 168777007.M.027 | 4929.94 | 2025-07-25 | Y
DOT | SC24663 | 1215435 | Olympia Fields | Conner Chamernik | BL | 3 | 2025-05-08 | 2025-05-08 | 2025-05-28 | 2025-06-03 | 2025-06-10 | Shactee | 6 sheets - 2,600' of 2" PE installation | N | 168777007.M.070 | 0 | 2025-07-25 | Y
DOT | SC24663 | 1215435 | Olympia Fields | Conner Chamernik | D | 3 | 2025-05-27 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-10 | Shactee | 6 sheets - 2,600' of 2" PE installation | N | 168777007.M.070 | 10457.03 | 2025-07-25 | Y
DOT | N17925 | 1215678 | HOFFMAN ESTATES | Conner Chamernik | BL/D | 1 | 2025-07-31 | 2025-07-31 | 2025-08-13 | 2025-08-15 | 2025-08-19 | Shactee | 1 sheet - 4" PE | N | 168777007.D.115 | 9420.15 | 2025-10-01 | N
CRA | RS1302 | 1014897 | DAVISJCT | Conner Chamernik | BL/D | 5 | 2025-09-02 | 2025-09-02 | 2025-09-23 |  |  | Shactee | Nicor revised Scope | N | 168777007.G.819 | 8000 | TBD
DOT | N15193 | 1213529 | STREAMWOOD | Eric Dina | BL | 14 | 2024-01-17 | 2024-01-17 | 2024-01-26 | 2024-01-29 | 2024-02-13 | Shactee | 14 Sheets - 8" STL | N | 168777007.D.117 | N/A | N/A | N/A
DOT | N13624 | 1213557 | PALATINE | Eric Dina | BL | 3 | 2024-01-30 | 2024-01-30 | 2024-02-21 | 2024-02-21 | 2024-03-19 | Shactee | 3 sheets - 6" PE culvert crossing | N | 168777007.D.092 | N/A | N/A | N/A
DOT | N13624 | 1213557 | PALATINE | Eric Dina | D | 3 | 2024-01-30 | 2024-03-07 | 2024-03-15 | 2024-03-14 | 2024-03-19 | Shactee | 3 sheets - 6" PE culvert crossing | N | 168777007.D.092 | N/A | N/A | N/A
DOT | N13624 | 1213557 | PALATINE | Eric Dina | Bore Profile | 1 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-02 | 2024-05-14 | Shactee | 1 bore profile | N | 168777007.D.092 | N/A | N/A | N/A
DOT | M10905 | 120585 | JUSTICE | Eric Dina | Revision | 3 | 2024-11-27 | 2024-11-27 | 2024-12-06 | 2024-12-06 | 2024-12-17 | Shactee | 3 sheets - 4" reroute | N | 168777007.E.072 | 2284.5 | 2025-02-25 | Y
DOT | SC20556 | 1413864 | BLOOMINGTON | Eric Dina/ Ethan Ekstrom | BL | 2 | 2024-05-28 | 2024-05-28 | 2024-06-05 | 2024-06-05 | 2024-06-11 | Shactee | 2 Sheets - Partially reimbursable | N | 168777007.D.148 | N/A | N/A | N/A
DOT | N18640 | 1214234 | BUFFALO GROVE | Ethan Ekstrom | BL | 9 | 2024-06-11 | 2024-06-12 | 2024-06-26 | 2024-06-26 | 2024-07-02 | Shactee | 9 sheets - 2", 4", 8" STL | N | 168777007.M.013 | N/A | N/A | N/A
DOT | SC20556 | 1413864/1413997 | BLOOMINGTON | Ethan Ekstrom | D | 1 | 2024-06-19 | 2024-06-19 | 2024-06-26 | 2024-06-26 | 2024-07-02 | Shactee | 1 Sheet - 4" PE & 12" STL TR - Partially Reimb | N | 168777007.D.148 | N/A | N/A | N/A
DOT | N18640 | 1214234 | BUFFALO GROVE | Ethan Ekstrom | D | 7 | 2024-08-16 | 2024-08-16 | 2024-08-23 | 2024-08-26 | 2024-09-17 | Shactee | 7 sheets - 2", 4" STL | N | 168777007.M.013 | N/A | N/A | N/A
DOT | M16089 | 1214808 | Oak Forest | Ethan Ekstrom | BL | 10 | 2024-12-17 | 2024-12-17 | 2025-01-03 | 2025-01-02 | 2025-01-14 | Shactee | 10 Sheets - 2" STL & 4" PE | N | 168777007.M.037 | 4107.36 | 2025-04-25 | Y
DOT | N18674 | 1214810 | Prospect Heights | Ethan Ekstrom | BL/D | 2 | 2024-12-17 | 2024-12-17 | 2025-01-08 | 2025-01-08 | 2025-01-21 | Shactee | 2 Sheets - 4" STL | N | 168777007.M.039 | 8069.8 | 2025-03-25 | Y
DOT | N17019 | 1215483 | MT PROSPECT | Ethan Ekstrom | BL | 17 | 2025-04-30 | 2025-04-30 | 2025-05-14 | 2025-05-14 | 2025-06-03 | Shactee |  | N | 168777007.M.034 | 7129.88 | 2026-01-01 | N
DOT | N17019 | 1215483 | MT PROSPECT | Ethan Ekstrom | D | 11 | 2025-06-17 | 2025-06-17 | 2025-07-09 | 2025-07-09 | 2025-07-15 | Shactee | 11 sheets - 2", 4", 6" PE | N | 168777007.M.034 | 12098.64 | 2026-01-01 | N
DOT | SC25188 | 1415542 | BLOOMINGTON | Ethan Ekstrom | BL | 4 | 2025-07-08 | 2025-07-08 | 2025-07-15 | 2025-07-15 | N/A | Shactee | 4 sheets - 2" PE and 8" STL | N | 168777007.M.068 | 3616.83 | 2025-12-01 | N
DOT | SC25188 | 1415542 | BLOOMINGTON | Ethan Ekstrom | D | 3 | 2025-07-17 | 2025-07-17 | 2025-07-31 | 2025-07-30 | 2025-08-26 | Shactee | 3 sheets - 2" PE and 8" STL | N | 168777007.M.068 | 5149.66 | 2025-12-01 | N
DOT | Leak Test Audit |  |  | Joey Betland | Leak Test Audit |  |  | 2025-08-12 | 2025-08-29 |  |  | Shactee | Leak tests of 2024/2025 projects. | N/A | 168777007.D.900 | 7000 | 2025-09-01 | N
DOT | Project Cost Audit 2022 |  |  | Joey Betland | Project Cost Audit |  |  | 2025-08-12 | 2025-08-29 |  |  | Shactee | PCTS Cost Documentation Recording | N/A | 168777007.D.900 | 9000 | 2025-09-01 | N
DOT | Sharepoint Folder Audit |  |  | Joey Betland | Sharepoint Audit |  |  | 2025-08-11 |  |  |  | Shactee | Audit of KH sharepoint folders | N/A | 168777007.D.900 | 10000 | 2025-09-01 | N
DOT | Project Cost Audit 2023 |  |  | Joey Betland | Project Cost Audit |  |  | 2025-08-12 | 2025-09-30 |  |  | Shactee | PCTS Cost Documentation Recording | N/A | 168777007.D.900 | 9000 | 2025-10-01 | N
DOT | Project Cost Audit 2024 |  |  | Joey Betland | Project Cost Audit |  |  | 2025-08-12 | 2025-10-30 |  |  | Shactee | PCTS Cost Documentation Recording | N/A | 168777007.D.900 | 9000 | 2025-11-01 | N
DOT | Project Cost Audit 2025 |  |  | Joey Betland | Project Cost Audit |  |  | 2025-08-12 | 2025-11-30 |  |  | Shactee | PCTS Cost Documentation Recording | N/A | 168777007.D.900 | 9000 | 2025-12-01 | N
CRA | RS1317 | 1015488 | HINSDALE | Julia Holstead | BL | 5 | 2025-07-31 | 2025-08-04 | 2025-08-15 | 2025-08-13 | N/A | Shactee | 2 sheets - baseline | N | 168777007.G.418 | 2487.05 | 2025-10-01 | N
CRA | RS1317 | 1015488 | HINSDALE | Julia Holstead | D | 2 | 2025-08-19 | 2025-08-22 | 2025-08-29 | 2025-09-05 |  | Shactee | 2 sheets - design | N | 168777007.G.418 | 7144.14 | 2025-10-01 | N
RS | RS1303 | 1014894 | CEDARVILLE | Julia Holstead | BL | 3 | 2025-05-21 | 2025-05-21 | 2025-06-06 | 2025-06-11 | N/A | Shactee | 3 sheets - baseline | N | 168777007.G.816 | 4167.94 | 2025-09-01 | N
RS | RS1303 | 1014894 | CEDARVILLE | Julia Holstead | D | 3 | 2025-07-14 | 2025-07-11 | 2025-07-23 | 2025-07-22 | N/A | Shactee | 3 sheets - design | N | 168777007.G.816 | 3418.8 | 2025-09-01 | N
TW | RS1213 | 1015226 | Elburn | Julia Holstead | BL | 11 | 2025-04-16 | 2025-04-17 | 2025-04-28 | 2025-05-01 | N/A | Shactee | 1 TW replacement & ~5,500' of main install | N | 168777007.G.611 | 6321.46 | 2025-10-01 | N
RS | RS1213 | 1015226 | ELBURN | Julia Holstead | BL/D | 14 | 2025-05-15 | 2025-05-15 | 2025-05-29 | 2025-06-04 | N/A | Shactee | 1 TW replacement & ~5,500' of main install, design, comments, incorporate survey | N | 168777007.G.611 | 5428.86 | 2025-10-01 | N
TW | RS1299 | 1014895 | E DUBUQUE | Julia Holstead | BL/D | 1 | 2025-06-02 | 2025-06-03 | 2025-06-18 | 2025-06-17 | N/A | Shactee | 1 sheet - tin whistle replacement & retrofit | N | 168777007.G.817 | 4207.86 | 2025-10-01 | N
TW | TW3401565 | 1015191 | BIG ROCK | Julia Holstead | BL/D | 2 | 2025-05-07 | 2025-05-07 | 2025-05-14 | 2025-05-19 | N/A | Shactee | 1 TW and main retirement | N | 168777007.H.145 | 3128.99 | TBD | N
CRA | RS1252 | 1014137 | MARENGO | Madie Roman | BL/D | 1 | 2024-09-03 | 2024-08-29 | 2024-09-18 | 2024-09-13 | 2024-09-24 | Shactee | 2 Sheets - TW | N | 168777007.G.604 | 4679.5 | 2024-11-01 | N
CRA | RS1238 | 1014138 | MT MORRIS | Madie Roman | BL | 6 | 2024-08-30 | 2024-08-29 | 2024-09-17 | 2024-09-17 | 2024-10-08 | Shactee | 6 Sheets - 4" STL main and TW | Y | 168777007.G.605 | 4460.75 | 2024-11-01 | N
CRA | RS1254 | 1014236 | GILBERTS | Madie Roman | BL | 4 | 2024-09-06 | 2024-09-06 | 2024-09-25 | 2024-09-24 | 2024-10-15 | Shactee | 4 Sheets - TW 2" PE | N | 168777007.G.609 | 5494.5 | 2024-12-01 | N
CRA | RS1266 | 1014237 | ELGIN | Madie Roman | BL/D | 2 | 2024-10-15 | 2024-10-15 | 2024-10-30 | 2024-10-30 | 2024-11-05 | Shactee | 2 Sheets - TW | N | 168777007.G.610 | 7514.25 | 2025-01-01 | N
CRA | RS1265 | 1014227 | WATSEKA | Madie Roman | BL/D | 5 | 2024-10-28 | 2024-10-25 | 2024-11-05 | 2024-11-05 | 2024-11-12 | Shactee | 2 Sheets - TW - Survey Pending | N | 168777007.G.607 | 6453.25 | 2025-01-01 | N
CRA | RS1266 | 1014237 | ELGIN | Madie Roman | IC | 2 | 2024-11-06 | 2024-11-06 | 2024-11-08 | 2024-11-08 | 2024-11-12 | Shactee | 2 Sheets - TW | N | 168777007.G.610 |  | 2025-01-01 | N
COR | COR1062 | 1214646 | GLENWOOD | Madie Roman | BL/D | 3 | 2024-12-02 | 2024-12-03 | 2024-12-17 | 2024-12-17 | 2025-01-14 | Shactee | 3 Sheets - 3 EDV jumpers | N | 168777007.H.804 | 4255.75 | 2025-03-01
COR | COR1071 | 1314774 | Glen Ellyn | Madie Roman | BL/D | 2 | 2025-01-20 | 2025-01-17 | 2025-02-07 | 2025-02-06 | 2025-02-25 | Shactee | 2 sheets - 2 EDV jumpers | N | 168777007.H.813 | 6752.5 | 2025-03-01
COR | COR1072 | 1314775 | Glen Ellyn | Madie Roman | BL/D | 2 | 2025-01-20 | 2025-01-17 | 2025-02-07 | 2025-02-06 | 2025-02-25 | Shactee | 2 sheets - 2 EDV jumpers | N | 168777007.H.814 | 7417.37 | 2025-03-01
COR | COR1073 | 1214777 | Desplaines | Madie Roman | BL/D | 6 | 2025-01-16 | 2025-01-17 | 2025-02-06 | 2025-02-07 | 2025-02-25 | Shactee | 6 sheets - 6 EDV Jumpers | N | 168777007.H.815 | 12619.93 | 2025-03-01
COR | COR1070 | 1414773 | Shorewood | Madie Roman | BL/D | 3 | 2025-01-22 | 2025-01-17 | 2025-02-10 | 2025-02-10 | 2025-02-25 | Shactee | 3 sheets - 3 EDV jumpers | N | 168777007.H.812 | 5681.63 | 2025-03-01
CRA | RS959 | 1011935 | GENESEO | Madie Roman | BL/D | 3 | 2024-10-02 | 2024-10-03 | 2024-10-17 | 2024-10-21 | 2024-10-29 | Shactee | 3 Sheets - Vault - Pending Survey | N | 168777007.G.500 | 10836.5 | 2025-03-01 | N
CRA | RS1280 | 1014643 | Streamwood | Madie Roman | BL/D | 5 | 2025-02-03 | 2025-01-31 | 2025-05-30 | 2025-06-02 | 2025-07-22 | Shactee | 5 Sheets - Vault relocation | N | 168777007.G.414 | 12000 | 2025-04-01
TW | RS1218 | 1015225 | Elburn | Madie Roman | BL | 14 | 2025-04-16 | 2025-04-16 | 2025-05-01 | 2025-05-01 | N/A | Shactee | 1 TW replacement & ~7,000' of main install | N | 168777007.G.612 | 8122.55 | 2025-10-01 | N
TW | RS1218 | 1015225 | Elburn | Madie Roman | D | 14 | 2025-06-10 | 2025-06-16 | 2025-07-07 | 2025-07-09 |  | Shactee | Running line was confirmed 6/11. | N | 168777007.G.612 | 12653.63 | 2025-10-01 | N
RS | RS829 | 1011061 | S Elgin | Madie Roman | D | 3 | 2025-06-09 | 2025-06-05 | 2025-06-23 | 2025-06-23 |  | Shactee | Pending BUE confirmation to confirm scope sent 4/16. | N | 168777007.G.416 | 6526.73 | 2025-10-01 | N
RS | RS1279 | 1014642 | Elgin | Madie Roman | BL | 4 | 2025-06-20 | 2025-06-23 | 2025-07-02 | 2025-07-02 | N/A | Shactee | Pending Nicor Survey approval sent 5/16. | Y | 168777007.G.413 | 5470.7 | 2025-10-01 | N
CRA | RS1238 | 1014138 | MT MORRIS | Madie Roman | D | 6 | 2024-09-13 | 2024-09-19 | 2024-09-30 | 2024-09-30 | 2024-10-08 | Shactee | 6 Sheets - 4" STL main and TW | Y | 168777007.G.605 | 4450 | 2025-11-01 | N
CRA | RS1254 | 1014236 | GILBERTS | Madie Roman | D | 4 | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-01 | 2024-10-15 | Shactee | 4 Sheets - TW 2" PE | N | 168777007.G.609 | 1672.5 | 2025-12-01 | N
TW | TW4101242 | 101546 | UNIVERSITY PARK | Madie Roman | BL/D | 1 | 2025-04-25 | 2025-04-25 | 2025-05-02 | 2025-05-02 | N/A | Shactee | 1 TW and main retirement | N | 168777007.H.138 | 3384.66 | TBD | N
TW | RS1302 | 1014897 | DAVISJCT | Madie Roman | BL/D | 2 | 2025-05-28 | 2025-05-28 | 2025-06-18 | 2025-06-25 | 2025-07-01 | Shactee | Survey deliverables due 5/28. | N | 168777007.G.819 | 5718.69 | TBD | N
CRA | TWV3701048 | 1014896 | Grand Detour | Madie Roman | BL/D | 1 | 2025-05-28 | N/A | 2025-06-04 |  | N/A | Shactee | Pending EDSR form, low priority | N | 168777007.H.117 | N/A | N/A | N
RS | RS1279 | 1014642 | Elgin | Madie Roman | D | 4 | 2025-08-04 | N/A | 2025-08-18 |  | N/A | Shactee | Anticipated confirmed running line 6/10. | Y | 168777007.G.413 | N/A | N/A | N
CRA | RS1316 | 1015489 | Glen Ellyn | Madie Roman | BL/D | 3 | 2025-09-25 |  | 2025-10-07 |  |  | Shactee | 3 Sheets - Vault replacement - pending survey | N | 168777007.G.417
CRA | RS1279 | 1014642 | Elgin | Madie Roman | BL/D | 5 | 2025-09-22 |  | 2025-10-06 |  |  | Shactee | Pending scope confirmation from Nicor, 9/16. | N | 168777007.G.413
CRA | RS1202 | 1013480 | WHEELING | Marissa LaPorte | D Review | 3 | 2024-02-26 | 2024-02-22 | 2024-03-05 | 2024-03-05 | N/A | Shactee |  | N | 168777007.G.410 | N/A | N/A | N/A
CRA | RS1201 | 1013481 | WILLOW SPRINGS | Marissa LaPorte | BL | 5 | 2024-03-05 | 2024-03-05 | 2024-03-15 | 2024-03-15 | N/A | Shactee |  | N | 168777007.G.409 | N/A | N/A | N/A
CRA | RS1234 | 1014093 | DIXON | Marissa LaPorte | BL/D | 2 | 2024-08-13 | 2024-08-13 | 2024-08-27 | 2024-08-23 | 2024-09-10 | Shactee | 2 Sheets - 16" MOP main and TW | N | 168777007.G.602 | N/A | N/A | N/A
CRA | RS1237 | 1014094 | STERLING | Marissa LaPorte | BL/D | 2 | 2024-08-20 | 2024-08-15 | 2024-09-03 | 2024-09-03 | 2024-09-17 | Shactee | 2 Sheets - 10" MOP main and TW | N | 168777007.G.600 | N/A | N/A | N/A
CRA | RS1233 | 1014092 | STILLMAN VALLEY | Marissa LaPorte | BL | 6 | 2024-08-28 | 2024-08-28 | 2024-09-10 | 2024-09-10 | 2024-10-15 | Shactee | 6 Sheets - main install, 3 TWs | N | 168777007.G.601 |  | 2024-12-01 | N
CRA | RS1244 | 1014110 | PLATO CENTER | Marissa LaPorte | BL/D | 2 | 2024-09-04 | 2024-09-04 | 2024-09-19 | 2024-09-23 | 2024-10-01 | Shactee | 2 Sheets - TW | N | 168777007.G.603 |  | 2024-11-01 | N
CRA | RS1233 | 1014092 | STILLMAN VALLEY | Marissa LaPorte | D | 6 | 2024-09-18 | 2024-09-20 | 2024-10-02 | 2024-10-01 | 2024-10-15 | Shactee | 6 Sheets - main and vault vault | N | 168777007.G.601 |  | 2024-12-01 | N
CRA | TWV1201443 | 1015173 | ST CHARLES | Marissa LaPorte | BL | 1 | 2025-05-27 | 2025-05-27 | 2025-06-03 | 2025-06-04 | 2025-07-08 | Shactee | 1 sheet - Tin whislte venting baseline | N | 168777007.H.140 | 1494.5 | 2025-08-01 | N
CRA | RS1321 & RS1322 | 1015615/1015616 | ROCHELLE | Marissa LaPorte | BL | 3 | 2025-08-15 | 2025-08-15 | 2025-09-02 |  |  | Shactee | 2 sheets - Vault replacement | N | 168777007.G.420 | 2000 | 2025-10-01 | N
CRA | RS1267 | 1014228 | WOODSTOCK | Marissa LaPorte | BL/D | 2 | 2024-10-09 | 2024-10-10 | 2024-10-24 | 2024-10-24 | 2024-10-29 | Shactee | 2 Sheets - TW | N | 168777007.G.608 |  | 2024-12-01 | N
COR | COR1063 | 1414647 | JOLIET | Marissa LaPorte | BL/D | 4 | 2024-12-02 | 2024-12-03 | 2024-12-17 | 2024-12-18 | 2025-01-14 | Shactee | 4 Sheets - 4 EDV jumpers | N | 168777007.H.805 |  | 2025-02-01
COR | COR1061 | 1414645 | KANKAKEE | Marissa LaPorte | BL/D | 1 | 2024-12-02 | 2024-12-02 | 2024-12-16 | 2024-12-16 | 2025-01-14 | Shactee | 1 Sheet - EDV jumper | N | 168777007.H.803 |  | 2025-03-01
CRA | COR1077 | 1314909 | Glen Ellyn | Marissa LaPorte | BL/D | 5 | 2025-02-12 | 2025-02-13 | 2025-02-26 | 2025-02-26 | N/A | Shactee | 5 sheets - 5 EDVs | N | 168777007.H.819 |  | 2025-04-01 | N
TWV | New Batch |  |  | Marissa LaPorte | BL | 1 | TBD |  | TBD |  |  | Shactee | 30 TWVs - Anticipated Sept 2025 |  |  | 30000 | 2025-12-01
RS | RS1318 | 1015485 | NILES | Marissa LaPorte | BL | 5 | 2025-08-06 | 2025-08-07 | 2025-08-20 | 2025-08-20 | TBD | Shactee | 3 sheets - Vault replacement |  | 16877007.G.419 | 5600 | TBD | N
DOT | M15904 | 1214609 | MAYWOOD | Marissa LaPorte | BL/D | 1 | 2024-11-25 | 2024-11-25 | 2024-12-09 | 2024-12-10 | 2024-12-17 | Shactee | 3 Sheets - 8" Jumper and 2" PE replacement | N | 168777007.M.030 | N/A | N/A | N/A
RS | RS1321 & RS1322 | 1015615/1015616 | ROCHELLE | Marissa LaPorte | D | 3 | 2025-09-10 | N/A | 2025-09-19 | N/A | N/A | Shactee | 2 sheets - Vault replacement | N | 168777007.G.420 |  | 2025-10-01
DIMP MR | MR1C15323_C15324 | 1213263 | NORTHLAKE | Marissa LaPorte | BL/D Review | 44 | N/A | N/A | N/A | N/A | N/A | Shactee |  | Y |  |  |  | N
RS | RS1186 | 1013162 | MAPLE PARK | Marissa LaPorte | BL/D Review | 1 | N/A | N/A | N/A | N/A | N/A | Shactee |  | N | N/A | N/A | N/A | N
TWV | 3401451 | 1015192 | HINKLEY | Marissa LaPorte | BL/D | 1 | 2025-04-09 | 2025-04-10 | 2025-04-17 | 2025-04-16 | N/A | Shactee | 1 Sheet - Baseline Drafting/Plansheet setup | N | 168777007.H.146 |  | TBD
TWV | 3401629 | 1014889 | HAMPSHIRE | Marissa LaPorte | BL/D | 1 | 2025-04-09 | 2025-04-10 | 2025-04-17 | 2025-04-16 | N/A | Shactee | 1 Sheet - Baseline Drafting/Plansheet setup | N | 168777007.H.121 |  | TBD
DOT | SC25858 | 1415469 | PLAINFIELD | Marissa LaPorte | BL | 4 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-12 | 2025-06-03 | Shactee | 4 sheets - baseline | N | 168777007.M.067 | 4229.96 | 2025-08-01 | N
DOT | SC25858 | 1415469 | PLAINFIELD | Marissa LaPorte | D | 4 | 2025-05-16 | 2025-05-16 | 2025-05-23 | 2025-05-23 | 2025-06-03 | Shactee | 2,000' of 4" main replacement | N | 168777007.M.067 | 5000 | 2025-08-01 | N
TWV | 3401394 | 1015194 | ELBURN | Marissa LaPorte | BL/D | TBD | TBD |  | TBD |  |  | Shactee | Pending scope confirmation, TWV vs full replacement |  | 168777007.H.148 |  | TBD
TWV | 3401451 | 1015192 | HINCKLEY | Marissa LaPorte | BL/D | TBD | TBD |  | TBD |  |  | Shactee | Pending scope confirmation, TWV vs full replacement |  | 168777007.H.146 |  | TBD
TWV | 3401457 | 1015190 | BIG ROCK | Marissa LaPorte | BL/D | TBD | TBD |  | TBD |  |  | Shactee | Pending scope confirmation, TWV vs full replacement |  | 168777007.H.144 |  | TBD
RS | RS1318 | 1015485 | NILES | Marissa LaPorte | D | 5 | TBD |  | TBD |  |  | Shactee | 3 sheets - Vault replacement | N | 16877007.G.419 | 5600.3 | TBD
TWV | Batch 3 |  | Varies | Marissa LaPorte | BL | 5 | 2025-04-14 | 2025-04-14 | 2025-04-21 | 2025-04-21 | 2025-05-27 | Shactee | 1 Sheet each project - Baseline Drafting | N
TWV | Batch 4 |  | Varies | Marissa LaPorte | BL | 8 | 2025-04-21 | 2025-04-22 | 2025-05-05 | 2025-05-05 | 2025-05-27 | Shactee | 1 Sheet each project - Baseline Drafting | N
DOT | M15450 | 1214113 | PROVISO TWP | Mark Stanley | BL | 1 | 2024-07-29 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-09-17 | Shactee | 1 sheet - 4" STL | N | 168777007.D.121 | N/A | N/A | N/A
DOT | M15450 | 1214113 | PROVISO TWP | Mark Stanley | D | 1 | 2024-07-30 | 2024-08-22 | 2024-08-29 | 2024-08-27 | 2024-09-17 | Shactee | 1 sheet - 4" STL | N | 168777007.D.121 | N/A | N/A | N/A
Non-DOT | BS588 | 1212413 | CICERO | Mark Stanley | WO Split | 108 | 2025-08-14 | 2025-08-14 | 2025-09-26 |  |  | Shactee | WO split drawings, estimate, and bid docs. | Y | 168777007.K.305 | 32500 | 2025-10-01
DOT | N16744 | 1214571 | CRYSTAL LAKE | Mark Stanley | BL | 96 | 2024-11-11 | 2024-11-11 | 2025-01-30 | 2025-01-30 | 2025-02-25 | Shactee | 96 sheets | N | 168777007.D.165 | 24217.2 | 2026-01-01 | N
NBA | NBA10016031 | 1913958 | JOLIET | Mark Stanley | BL | 3 | 2024-09-24 | 2024-09-25 | 2024-10-04 | 2024-10-04 | 2024-10-08 | Shactee | 3 Sheets - 8" STL | N | 168777007.J.511 | 3892.5
Non-DOT | BS588 | 1212413 | CICERO | Mark Stanley | Bid Docs | 0 | 2025-03-28 | 2025-03-28 | 2025-04-18 | 2025-04-14 | 2025-04-22 | Shactee | Bid docs for BS588 | Y | 168777007.2.314 | 578.68 |  | N
TIMP | TP645 | 1415055 | BOURBONNAIS | Mark Stanley | BL/D | 4 | 2025-03-04 | 2025-03-04 | 2025-03-27 | 2025-03-27 | 2025-04-22 | Shactee | Four (4) MAOP validation digs on Nicor's 711 Line - S of STA 337 to Route 17 | N | 168777008.1.033 | 7624.64 | 2025-05-01 | Y
TIMP | TP645A | 1415056 | BRADLEY | Mark Stanley | BL/D | 14 | 2025-03-04 | 2025-03-04 | 2025-04-11 | 2025-04-15 | 2025-05-06 | Shactee | Fourteen (14) MAOP validation digs on Nicor's 711 Line - S of STA 337 to Route 17 | N | 168777008.1.034 | 14648.91 | 2025-06-01 | N
DIMP MR | MR2216 | 1214785 | FREEPORT | Mark Stanley | Review | 1 | 2025-02-27 | 2025-02-27 | 2025-03-03 | 2025-02-28 | N/A | Shactee | Combined Review | N | 168777007.J.010 | 2291.24 | N/A | N/A
TIMP | TP645B | 1415058 | KANKAKEE | Mark Stanley | BL/D | 9 | 2025-03-04 | 2025-03-04 | 2025-04-24 | 2025-04-24 | 2025-05-06 | Shactee | Nine (9) MAOP validation digs on Nicor's 711 Line - S of STA 337 to Route 17 | N | 168777008.1.035 | 10515.89 | 2025-06-01 | N
DOT | SC26238 |  | Pontiac | Mark Stanley | [8 empty] | Not confirmed if its a real project |  |  | 9000 | 2025-11-01 | N
DOT | SC23750 | 1313812 | Downers Grove | Matt Hopkins | BL/D | 1 | 2024-04-03 | 2024-04-03 | 2024-04-17 | 2024-04-09 | 2024-04-16 | Shactee | 1 Sheet - 2" PE | N | 168777007.D.142 | N/A | N/A | N/A
DOT | N12480 |  | CARPENTERSVILLE | Matt Hopkins | BL | 4 | 2024-08-27 | 2024-08-28 | 2024-09-06 | 2024-09-06 | 2024-09-10 | Shactee | 4 Sheets - 2" STL and 4" STL | N | 168777007.M.020 | N/A | N/A | N/A
DOT | N12480 | 1214410 | CARPENTERSVILLE | Matt Hopkins | D | 5 | 2024-09-30 | 2024-09-30 | 2024-10-09 | 2024-10-09 | 2024-10-15 | Shactee | 5 sheets - 2" PE/STL | N | 168777007.M.020 | N/A | N/A | N/A
DOT | N18617 | 1214502 | MT MORRIS | Matt Hopkins | BL | 2 | 2024-10-14 | 2024-10-14 | 2024-10-22 | 2024-10-22 | 2024-11-05 | Shactee | 2 Sheets - 2" & 4" STL | N | 168777007.M.012 | N/A | N/A | N/A
DOT | N18617 | 1214502 | MT MORRIS | Matt Hopkins | D | 2 | 2024-10-24 | 2024-10-24 | 2024-11-01 | 2024-11-01 | 2024-11-05 | Shactee | 2 Sheets - 2" STL & 4" PE | N | 168777007.M.012 | N/A | N/A | N/A
DOT | M16016 | 1214783 | Chicago Heights | Matt Hopkins | BL/D | 2 | 2024-12-17 | 2024-12-17 | 2025-01-10 | 2025-01-10 | 2025-01-28 | Shactee | 1 Sheets - 4" PE | N | 168777007.M.033 | 6929.52 | 2025-03-25 | Y
DOT | SC25712 | 1415154 | Pontiac | Matt Hopkins | BL | 3 | 2025-03-17 | 2025-03-17 | 2025-03-25 | 2025-03-25 | 2025-04-01 | Shactee | 4 Sheets - 4" PE | N | 168777007.M.055 | 4305.26 | 2025-07-01 | Y
DOT | SC25712 | 1415154 | Pontiac | Matt Hopkins | D | 2 | 2025-03-28 | 2025-03-28 | 2025-04-07 | 2025-04-03 | 2025-04-15 | Shactee | 2 Sheets - 4" PE Install & IDOT Typical Section | Y | 168777007.M.055 | 2947.76 | 2025-07-01 | Y
DOT | SC25578 |  | WILMINGTON | Matt Hopkins | BL/D | 2 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-22 | 2025-04-29 | Shactee | 600' of 2" STL | N | 168777007.M.056 | 2982.58 | 2025-06-25 | Y
DOT | N19953 | 1215725 | ELK GROVE VILLAGE | Matt Hopkins | BL | 7 | 2025-08-07 | 2025-08-07 | 2025-08-19 | 2025-08-19 | 2025-08-26 | Shactee | 7 sheets - 4" STL & 6" STL | N | 168777007.M.075 | 3957.6 | 2025-12-01 | N
DOT | N19953 | 1215725 | ELK GROVE VILLAGE | Matt Hopkins | D | 7 | 2025-08-20 | 2025-08-20 | 2025-08-27 | 2025-08-27 | N/A | Shactee | 1 sheets - ~350' of 6" PE Jumper | N | 168777007.M.075 | 3000 | 2025-12-01 | N
DOT | M15914 |  | OAK PARK | Matt Hopkins | BL | 7 | 2025-04-15 | 2025-04-15 | 2025-04-29 | N/A | N/A | Shactee | 7 sheets ~ 2" & 8" STL | N | 168777007.M.060 | 1541.69 | 2025-06-01 | Y
DOT | M15984 |  | Berwyn | Matt Hopkins | D | 3 | Pending Scope |  | Pending Scope |  |  | Shactee | TBD | N | 168777007.M.072 | 8000 | 2025-12-01 | N
DOT | M16521 |  | Bensenville | Matt Hopkins | BL | 4 | TBD |  | TBD |  | TBD | Shactee | 4 Sheets, BL 4" PE | N | 168777007.M.063 | 2500 | 2026-02-01 | N
DOT | TRAINING | TRAINING | TRAINING | Matt Welz | BL | 3 | 2025-06-03 | 2025-06-05 | 2025-07-31 |  | Bi-Weekly | Helix | Practice project - SC18359, bore profile | N | 168777007.D.903 | 10000 | 2025-09-23 | N
DOT | TRAINING | TRAINING | TRAINING | Matt Welz | D | [5 empty] | Bi-Weekly | Helix | Practice project - SC18359, bore profile | N | 168777007.D.903 | 8000 | 2025-09-01 | N
DOT | N18185 | 1215592 | ELGIN | Michael Molloy | BL | 6 | 2025-07-03 | 2025-07-09 | 2025-07-23 | 2025-07-23 | N/A | Shactee | 6 sheets baseline (Including LG Sheet) | Y | 168777007.M.074 | 8981.15 | 2026-03-26 | N
DOT | N18185 | 1215592 | ELGIN | Michael Molloy | D | TBD | TBD |  |  |  |  | Shactee | Pending Nicor coordination/vibrational analysis. | Y | 168777007.M.074 | 10000 | 2026-03-26 | N
TIMP | TP618 | 1214547 | NORTHLAKE | Mitchell Pohlman | BL/D | 9 | 2024-11-13 | 2024-11-13 | 2024-12-20 | 2024-12-19 | N/A | Shactee | 9 sheets - MAOP Validation Digs | N | 168777008.1.026 | 23218.5 | 2025-02-01 | Y
TIMP | TP618A | 1214532 | ELMHURST | Mitchell Pohlman | BL/D | 3 | 2024-11-13 | 2024-11-13 | 2024-12-02 | 2024-12-04 | N/A | Shactee | 3 sheets - MAOP Validation Digs | N | 168777008.1.027 | 6957.5 | 2025-02-01 | Y
TIMP | TP659 | 1015283 | ROCKFORD | Mitchell Pohlman | BL | 30 | 2025-08-06 | 2025-08-06 | 2025-08-12 | 2025-08-14 |  | Shactee | Hydrotest reconfirmation BL/D QC | N | 168777008.1.702 | 9000 | 2025-10-01 | N
TIMP | TP659A | 1015585 | ROCKFORD | Mitchell Pohlman | BL/D Review | 1 | 2025-07-24 | 2025-07-24 | 2025-07-28 | 2025-07-28 |  | Shactee | First Stage Reg retirement BL/D QC | N | 168777008.3.703 | 3000 | 2025-10-01 | N
NBA | NBA10013088 | 1513479 | NAPERVILLE | Nick Michaels | BL | 5 | 2024-01-19 | 2024-01-24 | 2024-02-01 | 2024-02-05 | 2024-02-26 | Shactee |  |  | 168777007.J.500 | N/A | N/A | N/A
NBA | NBA10013088 | 1513479 | NAPERVILLE | Nick Michaels | D | 5 | 2024-02-08 | 2024-02-26 | 2024-02-29 | 2024-02-29 | 2024-03-12 | Shactee |  |  |  | N/A | N/A | N/A
DOT | N17942 | - | HOFFMAN ESTATES | Nick Michaels | BL | 2 | 2024-01-19 | 2024-01-19 | 2024-01-25 | 2024-01-25 | 2024-01-31 | Shactee | 2 sheets - 2" PE | N | 168777007.D.134 | N/A | N/A | N/A
NON-DOT | NBA10013465 | 1914022 | Gilman | Nick Michaels | LG Sheets | 4 | 2024-12-12 | 2024-12-12 | 2024-12-19 | 2024-12-19 | N/A | Shactee | 4 Sheets - 2 Railroad crossings | Y | 168777007.J.505 |  | 2025-03-25 | Y
NBA | NBA10013465 | 1914022 | GILMAN | Nick Michaels | BL | 40 | 2024-10-30 | 2024-10-30 | 2024-11-13 | 2024-11-20 | TBD | Shactee | 40 sheets | Y | 168777007.J.505 |  | 2025-03-25 | Y
DOT | N17942 | - | HOFFMAN ESTATES | Nick Michaels | D | 2 | 2024-02-01 | 2023-01-30 | 2024-02-05 | 2024-02-05 | 2024-02-13 | Shactee | 2 Sheets - 2" PE | N | 168777007.D.134 | N/A | N/A | N/A
DIMP MR | MR2107 | 1313515 | NAPERVILLE | Nick Michaels | BL | 3 | 2024-01-22 | 2024-01-23 | 2024-01-29 | 2024-01-29 | 2024-01-31 | Shactee |  |  | 168777007.J.001 | N/A | N/A | N/A
DIMP MR | MR2107 | 1313515 | NAPERVILLE | Nick Michaels | D | 3 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 2024-02-06 | 2024-02-13 | Shactee |  |  |  | N/A | N/A | N/A
MR | MR1796 | 1210690 | SUMMIT | Nick Michaels | BL | 5 | TBD | TBD | TBD |  |  | Shactee | 5 Sheets - 16" & 8" STL - Pending Survey | Y | 168777007.1.306
Non-DOT | MR2192 | 1414512 | KANKAKEE | Nick Michaels/Tom McTigue | BL/D | 1 | 2024-11-25 | 2024-11-25 | 2024-12-12 | 2024-12-13 | 2024-12-19 | Shactee | 1 Sheet - 4" STL Railroad crossing | Y | 168777007.J.009 | 10069.75 |  | N
TIMP | TP636 | 1014825 | ROCKFORD | Nick Watt | BL/D | 5 | 2025-01-20 | 2025-01-20 | 2025-02-07 | 2025-02-07 | N/A | Shactee | Five (5) ECDA/ICDA DA digs on 16" Rockford Power Plant Line - Sta 295 to Sta 366 - R2-INDECK-DA | N | 168777008.1.031 | 9747.77 | 2025-04-01 | Y
TIMP | TP637 | 1014826 | ROCKFORD | Nick Watt | BL/D | 5 | 2025-01-20 | 2025-01-20 | 2025-02-04 | 2025-02-04 | N/A | Shactee | Five (5) ECDA/ICDA DA digs on 24" Rockford Line - Sta 395 to Sta 295 | N | 168777008.1.030 | 9485.49 | 2025-04-01 | Y
TR | TWS119 | 1014188 | KINGS | Nick Watt | QA/QC | 27 | 2025-01-08 | 2025-01-10 | 2025-01-15 | 2025-01-30 | N/A | Shactee | Est. 27 Sheets of Station Mechanical | N | 168777008.1.600 | 644.3 | 2025-06-01 | N
DOT | M15365 | - | BRIDGEVIEW | Randy Castellon | Nicor Locates | NA | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-09 | N/A | Shactee | Locates | N | 168777007.D.141 | N/A | N/A | N/A
DOT | SC21396 | 1413772 | NEW LENOX | Randy Castellon | BL | 8 | 2024-03-27 | 2024-03-27 | 2024-04-30 | 2024-04-30 | N/A | Shactee | 8 sheets - 6" PE | N | 168777007.D.105 | 11915 | 2025-07-01 | Y
DOT | SC21396 | 1413772 | NEW LENOX | Randy Castellon | D | 7 | 2024-05-20 | 2024-05-20 | 2024-05-31 | 2024-05-30 | 2024-06-18 | Shactee | 7 Sheets - 6" Partially Reimbursable | N | 168777007.D.105 | 7550 | 2025-07-01 | Y
DOT | N17081 | 1214649 | Freeport | Randy Castellon | BL | 2 | 2024-11-14 | 2024-11-15 | 2025-11-27 | 2024-12-23 | 2025-01-21 | Shactee | 2 Sheet Jumper under a railroad crossing | Potentially | 168777007.M.042 | 13464 | 2025-02-25 | Y
DOT | N10173 | 128466 | Hawthorn Woods | Randy Castellon | BL/D Review | 45 | 2024-12-18 | 2024-12-18 | 2025-01-03 | 2025-01-06 | N/A | Shactee | 45 Sheets - 2", 4" 6" 8" 10" 12" STL & PE | N | 168777007.D.088 | 5731 | 2025-08-01 | N
DOT | SC25031 | 1415051 | Rockdale | Randy Castellon | BL/D Review | 5 | 2025-03-20 | 2025-03-20 | 2025-03-24 | 2025-03-24 | N/A | Shactee | BL/D Review | N | 168777007.M.048 | 750.58 | 2025-05-25 | Y
DOT | SC23762 | 1413498 | Lockport | Randy Castellon | BL/D Review | 2 | 2024-03-21 | 2024-03-21 | 2024-02-25 | 2025-03-25 | N/A | Shactee | 2 Sheets - 12" STL | N | 168777007.D.122 | 845 | 2025-08-01 | N
DOT | N10173 | 128466 | Hawthorn Woods | Randy Castellon | Lake County Permit | 1 | 2025-05-14 | 2025-05-14 | 2025-05-28 | 2025-05-28 | N/A | Shactee |  |  | 168777007.D.088 | 4487.48 | 2025-08-01 | N
DOT | N16744 | 1214571 | CRYSTAL LAKE | Randy Castellon | D | 59 | 2025-05-15 | 2025-05-15 | 2025-07-16 | TBD |  | Shactee | 59 Sheets of pure design | N | 168777007.M.052 | 7801.7 | 2025-01-01 | N
DOT | N17141 | N/A | Huntley | Randy Castellon | BL/D | 2 | 2025-09-22 |  | 2025-09-30 |  |  | Shactee | Pending reimbursable confirmation with Developer, sent 3/13 | N | 168777007.D.100 | 8000 | 2025-12-01 | N
DOT | M12980 | 1212834 | LaGrange Park | Randy Castellon | BL | 4 | 2025-09-10 | 2025-09-10 | 2025-09-23 |  |  | Shactee | 4-5 Sheets, BL | N | 168777007.D.081 | 13000 | 2025-12-01
DOT | N14920 | 1215831 | Huntley | Randy Castellon | BL/D Review | 5 | 2025-09-29 |  | 2025-10-01 |  |  | Shactee | 5-6 Sheets, BL | N | 168777007.M.079 | 11000 | 2025-11-01 | N
DOT | SC23351 | 1413351 | CREST HILL | Taylor Lierow | BL/D Review | 2 | 2023-12-12 | 2023-12-12 | 2023-12-14 | 2023-12-14 | N/A | Shactee | 2 Sheets - 2" PE | N | 168777007.D.123 | N/A | N/A | N/A
DOT | SC23626 | 1413473 | TROY TWP | Taylor Lierow | BL | 1 | 2024-01-05 | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-23 | Shactee | 1 Sheet - 2" PE | N | 168777007.D.130 | N/A | N/A | N/A
DOT | SC23626 | 1413473 | TROY TWP | Taylor Lierow | D | 1 | 2024-01-10 | 2023-01-10 | 2024-01-15 | 2024-01-15 | 2024-01-23 | Shactee | 1 Sheet - 2" PE | N | 168777007.D.130 | N/A | N/A | N/A
DOT | SC21051 | 1213617 | OLYMPIA FIELDS | Taylor Lierow | BL | 13 | 2024-02-21 | 2024-02-21 | 2024-03-06 | 2024-03-07 | 2024-03-26 | Shactee | 13 sheets - 2" PE | N | 168777007.M.007 | N/A | N/A | N/A
DOT | N16542 | 1213673 | HOFFMAN ESTATES | Taylor Lierow | BL | 2 | 2024-02-27 | 2024-02-27 | 2024-03-12 | 2024-03-18 | 2024-03-26 | Shactee | 2 sheets - 6" PE | N | 168777007.D.136 | N/A | N/A | N/A
DOT | SC21051 | 1213617 | OLYMPIA FIELDS | Taylor Lierow | D | 13 | 2024-03-01 | 2024-03-04 | 2024-03-15 | 2024-03-20 | 2024-04-02 | Shactee | 13 sheets - 2" PE | N | 168777007.M.007 | N/A | N/A | N/A
DOT | N16542 | 1213673 | HOFFMAN ESTATES | Taylor Lierow | D | 2 | 2024-02-28 | 2024-02-28 | 2024-03-22 | 2024-03-21 | 2024-03-26 | Shactee | 2 sheets - 6" PE | N | 168777007.D.136 | N/A | N/A | N/A
DOT | N18054-1 | 1213715 | HOFFMAN ESTATES | Taylor Lierow | BL/D Review | 2 | 2024-04-03 | 2024-04-09 | 2024-04-12 | 2024-04-11 | 2024-04-16 | Shactee | 2 Sheets - 2" PE | N | 168777007.D.143 | N/A | N/A | N/A
DOT | N17815 | 1214002 | ROUND LAKE BEACH | Taylor Lierow | BL | 20-25 | 2024-03-08 | 2024-03-08 | 2024-04-17 | 2024-04-17 | 2024-06-18 | Shactee | 20 sheets - 2" PE, 4" PE and 6" PE | N | 168777007.D.106 | N/A | N/A | N/A
DOT | SC23070 | 1341001 | AURORA | Taylor Lierow | BL | 7 | 2024-06-06 | 2024-06-06 | 2024-06-24 | 2024-06-21 | 2024-08-13 | Shactee | 7 Sheets - 12" MOP main | N | 168777007.D126 | N/A | N/A | N/A
DOT | N18693 | 1214064 | GENESEO | Taylor Lierow | BL | 3 | 2024-06-25 | 2024-06-25 | 2024-07-01 | 2024-07-01 | 2024-07-09 | Shactee | 3 Sheets - 2 and 4" PE | N | 168777007.M.014 | N/A | N/A | N/A
DOT | N18693 | 1214064 | GENESEO | Taylor Lierow | D | 3 | 2024-06-26 | 2024-06-26 | 2024-07-11 | 2024-07-11 | 2024-07-16 | Shactee | 3 Sheets - 2 and 4" PE | N | 168777007.M.014 | N/A | N/A | N/A
DOT | SC23070 | 1341001 | AURORA | Taylor Lierow | BL | 16 | 2024-07-26 | 2024-07-26 | 2024-08-06 | 2024-08-06 | 2024-08-13 | Shactee | 20 sheets - 12" MOP, 2" PE, 4" PE 6" PE | N | 168777007.D.126 | N/A | N/A | N/A
DOT | N12987 | 1214085 | SCHAUMBURG | Taylor Lierow | BL | 3 | 2024-07-30 | 2024-07-30 | 2024-08-13 | 2024-08-12 | 2024-08-13 | Shactee | 3 Sheets - 6" PE | N | 168777007.D.002 | 4085.5 | 2025-03-25 | Y
DOT | N17815 | 1214002 | ROUND LAKE BEACH | Taylor Lierow | D | 25 | 2024-07-17 | 2024-07-17 | 2024-08-13 | 2024-08-14 | 2024-08-27 | Shactee | 16 sheets - 2, 4, 6 PE | N | 168777007.D.106 | N/A | N/A | N/A
DOT | N12987 | 1214085 | SCHAUMBURG | Taylor Lierow | D | 3 | 2024-08-13 | 2024-08-13 | 2024-08-20 | 2024-08-20 | 2024-08-27 | Shactee | 3 Sheets - 6" PE | N | 168777007.D.002 | 4236.25 | 2025-03-25 | Y
DOT | N17815 | 1214002 | ROUND LAKE BEACH | Taylor Lierow | Permit Package | 25 | 2024-07-31 | 2024-07-31 | TBD | 2024-09-16 | 2024-11-26 | Shactee | LCDOT Permit Package | N | 168777007.D.106 | N/A | N/A | N/A
DOT | N18492 | 1214923 | Long Grove | Taylor Lierow | BL | 5 | 2025-01-30 | 2025-01-30 | 2025-02-14 | 2025-02-14 | 2025-03-11 | Shactee | 5 sheets - 2", 4" and 8" install | N | 168777007.M.045 | 8935.97 | 2025-07-25 | Y
DOT | N18492 | 1214923 | Long Grove | Taylor Lierow | D | 4 | 2025-03-10 | 2025-03-10 | 2025-03-19 | 2025-03-19 | 2025-03-25 | Shactee | 4 sheets - 2" install and cross sections | N | 168777007.M.045 | 5602.72 | 2025-07-25 | Y
DOT | SC25832 | 1415311 | BRADLEY | Taylor Lierow | BL/D | 3 | 2025-05-08 | 2025-05-08 | 2025-05-15 | 2025-05-14 | 2025-05-22 | Shactee | 3 sheets - 8" STL | N | 168777007.M.061 | 8361.6 | 2025-07-25 | Y
DOT | N19731 | 1215667 | MACHESNEY PARK | Taylor Lierow | BL | 1 | 2025-07-29 | 2025-07-29 | 2025-08-06 | 2025-08-04 | N/A | Shactee | 1 sheet - 8" STL | N | 168777007.M.058 | 1999.08 | 2025-10-01 | N
DOT | N19731 | 1215667 | MACHESNEY PARK | Taylor Lierow | D | 1 | 2025-08-11 | 2025-08-11 | 2025-08-15 | 2025-08-18 | N/A | Shactee | 1 sheet - 8" STL | N | 168777007.M.058 | 5000 | 2025-10-01 | N
DOT | N19731 | 1215667 | MACHESNEY PARK | Taylor Lierow | PCTS Estimate | 1 | 2025-08-11 | 2025-08-11 | 2025-08-18 | 2025-08-19 | TBD | Shactee | 1 sheet - 8" STL | N | 168777007.M.058 | 1000 | 2025-10-01 | N
DOT | SC25777 | 1315433 | Westmont | Taylor Lierow | BL | 10 | 2025-08-11 | 2025-08-11 | 2025-08-29 | 2025-08-29 | TBD | Shactee | Pending Preliminary plans, anticipated end of July. | N | 168777007.M.066 | 8500 | 2025-11-01 | N
DOT | SC25777 | 1315433 | Westmont | Taylor Lierow | D | 11 | 2025-09-09 | 2025-09-08 | 2025-09-16 |  |  | Shactee | Pending Pre-Final plans, anticipated end of Sep | N | 168777007.M.066 | 5000 | 2025-11-25 | N
DOT | N14298 | 1214663 | STERLING | Taylor Lierow/Caroline Kulach | BL | 4 | 2024-11-22 | 2024-11-22 | 2024-12-03 | 2024-12-03 | 2024-12-17 | Shactee | 4 Sheets - 2" & 4" PE, 12" STL | N | 168777007.M.038 | 8203.25 | 2025-02-25 | Y
DOT | N14298 | 1214663 | STERLING | Taylor Lierow/Caroline Kulach | D | 4 | 2024-12-03 | 2024-12-05 | 2024-12-20 | 2024-12-23 | 2024-01-07 | Shactee | 4 Sheets - 2" & 4" PE, 12" STL | N | 168777007.M.038 | 4592.5 | 2025-02-25 | Y
DOT | N13601 | - | ROCKFORD | Tim Purtell | BL | TBD | 2024-01-22 | 2024-01-22 | 2024-01-31 | 2024-02-08 | 2024-02-26 | Shactee | 4 Sheets - 12" and 2" | N | 168777007.D.133 | N/A | N/A | N/A
DOT | SC23548 | 1313599 | NAPERVILLE | Tim Purtell | BL/D | 1 | 2024-02-02 | 2024-02-02 | 2024-02-24 | 2024-02-09 | 2024-02-27 | Shactee | 1 sheet, 2" PE | N | 168777007.D.135 | N/A | N/A | N/A
DOT | N18296 | 1213596 | PROSPECT HEIGHTS | Tim Purtell | BL/D | 5 | 2024-02-06 | 2024-02-06 | 2024-02-16 | 2024-02-22 | 2024-03-05 | Shactee | 4 sheets - 2" PE, 6'' PE, 6" STL | N | 168777007.M.008 | N/A | N/A | N/A
DOT | N13601-1 | 1213788 | Rockford | Tim Purtell | BL | 5 | 2024-03-27 | 2024-03-27 | 2024-04-10 | 2024-04-09 | 2024-04-16 | Shactee | 5 sheets - 2" PE | N | 168777007.D.144 | N/A | N/A | N/A
DOT | SC23749 | 1413789 | Manteno | Tim Purtell | BL | 10 | 2024-03-29 | 2024-03-29 | 2024-04-12 | 2024-04-09 | 2024-04-16 | Shactee | 10 sheets - 4" PE | N | 168777007.D.147 | N/A | N/A | N/A
DOT | SC23448 | 1413787 | Peotone | Tim Purtell | BL | 5 | 2024-04-01 | 2024-04-02 | 2024-04-12 | 2024-04-10 | 2024-05-28 | Shactee | 4 sheets - 2" PE | N | 168777007.G.800 | N/A | N/A | N/A
DIMP MR | MR2BID9834-2 | 1214993 | Oak Lawn | Tom McTigue | BL | 28 | 2025-02-05 | 2025-02-05 | 2025-03-05 | 2025-03-07 | 2025-03-18 | Shactee | ~28 sheets - 2", 4" STL | N | 168777007.J.305 | 28550 | 2025-05-25 | N
DIMP MR | MR2BID9843-1 | 1214925 | Hometown | Tom McTigue | LG Sheets | 1 | 2025-03-26 | 2025-03-26 | 2025-04-04 | 2025-04-04 | 2025-04-08 | Shactee | 1 Metra crossing LG sheets | Y | 168777007.J.302 | 3691.55 | 2025-06-01 | N
DIMP MR | MR2BID9834-1 | 1214925 | HOMETOWN | Tom McTigue | D QC | 26 | 2025-04-07 | 2025-04-07 | 2025-04-10 | 2025-04-10 | N/A | Shactee | ~26 sheets - 2", 4", 8" STL | Y | 168777007.J.302 | 1291.2 | 2025-06-01 | N
DIMP MR | MR2BID9834-1 | 1214925 | Hometown | Tom McTigue | BL | 26 | 2025-02-05 | 2025-02-05 | 2025-03-05 | 2025-03-07 | 2025-03-18 | Shactee | ~26 sheets - 2", 4", 8" STL | Y | 168777007.J.302 | 24100 | 2025-06-09 | N
DIMP MR | MR2255 | 1215239 | ROCHELLE | Tom McTigue | BL | 1 | 2025-04-15 | 2025-04-15 | 4/21/20225 | 2025-04-21 | N/A | Shactee | 50' of 8" STL | N | 168777007.J.013 | 2733.85 | 2025-06-25
Non-DOT | MR2255 | 1215239 | ROCHELLE | Tom McTigue | D Review | 1 | 2025-04-24 | 2025-04-24 | 2025-04-30 | 2025-04-29 | N/A | Shactee | 1 Sheet 8" Valve replacement | N | 168777007.J.013 | 737.25 | 2025-06-25
CRA | MR2259 | 1215296 | Kinsman | Tom McTigue | BL/D | 2 | 2025-05-21 | 2025-05-21 | 2025-06-06 | 2025-06-09 | 2025-06-10 | Shactee | 8" MOP creek crossing with a profile | N | 168777007.G.000 | 6603.02 | 2025-07-25
Non-DOT | MR2277 | 1215381 | Lansing | Tom McTigue | BL/D | 1 | 2025-06-11 | 2025-06-11 | 2025-06-17 | 2025-06-18 | N/A | Shactee | 300' of 4" STL replacement | N | 168777007.J.015 | 3356.16 | 2025-07-25 | N
CRA | RS1312 | 1014880 | OTTAWA | Tom McTigue | BL | 2 | 2025-06-06 | 2025-06-06 | 2025-06-25 | 2025-06-25 | N/A | Shactee | 2 Sheets - TW and 2" STL installation | N | 168777007.G.808 | 3569.26 | 2025-09-25 | N
CRA | RS1312 | 1014880 | OTTAWA | Tom McTigue | D Review | 3 | 2025-07-23 | 2025-07-24 | 2025-07-28 | 2025-07-28 | N/A | Shactee | 2 Sheets - TW and 2" STL installation | N | 168777007.G.808 | 1267.05 | 2025-09-25 | N
CRA | RS1300 | 1014890 | WINNEBAGO | Tom McTigue | BL/D | 5 | 2025-09-30 |  | 2025-10-07 |  |  | Shactee | Pending Survey | N | 168777007.G.823 | 7000 | 2025-09-25 | N
CRA | RS1308 | 1015189 | KINGSTON | Tom McTigue | BL/D | 2 | 2025-09-05 | 2025-09-05 | 2025-09-16 |  |  | Shactee | 2 Sheets - TW replacement | N | 168777007.G.620 | 5000 | 2025-11-01 | N
Non-DOT | PRIM719 | 1215554 | ROCHELLE | Tom McTigue | BL | 5 | 2025-07-02 | 2025-07-02 | 2025-07-14 | 2025-07-14 | N/A | Shactee | 2,500' of baseline tracing | N | 168777007.J.601 | 6049.36 | 2025-09-25 | N
DIMP MR | M2321 | 1215731 | Country Club Hills | Tom McTigue | BL/D | 2 | 2025-09-30 |  | 2025-10-07 |  |  | Shactee | Pending survey, 800' 2" PE & 50' of 8" STL | N | 168777007.J.016 | 4000 | 2025-11-25 | N
DIMP MR | MR2328 | 1215809 | BEDFORD PARK | Tom McTigue | BL | 13 | 2025-10-20 |  | 2025-10-24 |  |  | Shactee | Pending Survey, 6000' of 8" STL | Y | 168777007.J.200 | 5000 | 2025-12-25 | N
DIMP MR | MR2328 | 1215809 | BEDFORD PARK | Tom McTigue | D | 13 | 2025-10-29 |  | 2025-11-07 |  |  | Shactee | Pending Survey, 6000' of 8" STL | Y | 168777007.J.200 | 10000 | 2025-12-25 | N
TIMP | TP684 | 1115800 | GLENDALE HEIGHTS | Mark Stanley | BL/D | 1 | 2025-09-16 | 2025-09-16 | 2025-10-15 |  |  | Shactee | One ILI confirmation dig on the Des Plaines 36-in line | N | 168777008.1.042 | 9000
TIMP | TP694 | 1115799 | LISLE | Mark Stanley | BL/D | 1 | 2025-09-16 | 2025-09-16 | 2025-10-08 |  |  | Shactee | One ILI confirmation dig ont he 36-in Aux Sable line | N | 168777008.1.044 | 9000
[21 empty] | Drafting Schedules Reviewed | Review Schedule Reviewed
[20 empty] | Project Lead | Initials | Initials
Randy Castellon
Conner Chamernik
Camille Corbi
Ethan Ekstrom
Matt Hopkins
Caroline Kulach
Marissa LaPorte
Taylor Lierow
Madie Roman
Mark Stanley
Tom McTigue
Julia Holstead
Michael Molloy
Mitch Pohlman
Nick Watt
Formulas:
NTP = Table5[[#This Row],[Anticipated NTP]]
Note on F1: Betland, Joseph: -BL -BL/D -Conflict Analysis -Permitting -LG Drawing
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan could you please adjust these Anticipated Fee numbers to match our 2025 - 3rd Party Review numbers so that we can make sure everything is syncing up? Would be great to make sure that the reported month is matching as well. Reply: do you want all these numbers updated? or just the red ones? are we updating based on what has been billed or is this based off of what hasn't been invoiced and someone has entered? Reply: for projects that have been completed and invoiced i'd ideally like to have these numbers match up with the actual invoices instead of being the "anticipated fee" so that our DBE summary matches up with what we report in Steering Committee. Does that help? Looping in @Dina, Eric as well Reply: not totally. Since there are multiple invoices for certain sites and duplicate sites on this list I am not really sure what goes in each spot. @Dina, Eric, let me know if you have some time to discuss. Reply: Maybe we all discuss next week quickly just to get on the same page
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille - Please fill out this row.
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille updated from 9/2 to 9/10. Shactee said they coordinated this with you already but wanted to give you a heads up if not.
Note on N62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roman, Madeline any update on this? Reply: Last f/u 5/23. SysPlan generally takes a few weeks to create
Note on Q69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Chamernik, Conner why N/A? Reply: Combined BL/D cost. Cell Q73 shows the cost and has a note that says it accounts for the BL as well
Note on Q70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BL/D combined
Note on P83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Ekstrom, Ethan plz fill this out
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ekstrom, Ethan Reply: most likely going to shactee, could you fill out the anticipated fee and as much as possible? no need to include anticipated dates. if we dont send to shactee, we can delete later on
Note on Q98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Holstead, Julia please clean up the red cells here (even if projects were in the past) - this is really important to get our forecasting correct for monthly reporting.
Note on Q104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Roman, Madeline please clean up the red cells here (even if projects were in the past) - this is really important to get our forecasting correct for monthly reporting. Reply: they should be all filled out now and highlighted yellow
Note on J114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was on hold for several months
Note on L115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sent comments to shactee 6/16
Note on J116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated from 7/1/2025
Note on L118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has not been reviewed due to project being on hold for rescoping
Note on L121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Madie send comments to Shactee on 5/13/25
Note on J122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated from 6/4/2025 due to workload
Note on M125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roman, Madeline plz fil out
Note on Q131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Purtell, Tim seeing a lot of red over here so it’s hard to see if your projections are correct - are you able to work with Madie/Julia to fill these out?
Note on Q133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @LaPorte, Marissa please clean up the red cells here (even if projects were in the past) - this is really important to get our forecasting correct for monthly reporting.
Note on J135: LaPorte, Marissa: Originally asked for 8/25/25
Note on Q140: LaPorte, Marissa: avg ~$1,500 per project and only 20 continuing as TWVs
Note on J179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Hopkins, Matt can you fill this out?
Note on G181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Welz, Matt can you work with @Dina, Eric to enter in the information here for the training we are having Helix do, how much fee it is, and when we think we’re going to be invoiced it and report to Nicor?
Note on Q181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CPM $20,000 Reply: @Welz, Matt shouldn’t this be more like 20k? Reply: No idea Reply: Can you help me find out since you're taking point on this coordination? I believe that Eric noted it was approximately $20k Reply: I'd stick w/ $10k for now. I can ask Jason where their spend is when I talk to him next.
Note on R181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Welz, Matt are these dates accurate? essentially, put in the date you anticipate this being done
Note on N197: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Stanley, Mark any update on this for shactee? Reply: Nothing yet, will likely send to Shactee for drafting but will need to review scope with Nicor and send for Survey. All pending a site visit. Reply: @Stanley, Mark Any update on this? Reply: Still planning on sending to Shactee for B&D. Survey schedule will give us our timeline.
Note on C211: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Castellon, Randy fill out red cells
Note on C212: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Castellon, Randy PLZ FILL OUT RED CELLS
Note on H237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lierow, Taylor can you make sure the dates are updated when youre able to? Reply: This is correct
Note on G250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas - Can you fill out/update the line for the -1 and -2?
Note on Q256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas please clean up the red cells here (even if projects were in the past) - this is really important to get our forecasting correct for monthly reporting. Reply: Yep my bad, updated now
Note on F258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: are these baselines or just QCs Reply: @McTigue, Thomas Reply: drafting

## Data
SCOPE DESCRIPTION | PROJECT TYPE
Geotechnical | COR
Geotechnical, SUE A | CRA
Survey | DIMP MR
SUE Level A | DOT
Survey, SUE Level B | DOT-TR
Survey, SUE Level B, Geotechnical | MR
Survey, SUE Level A/B | NBA
Survey, SUE Level A/B, Geotechnical | Non-DOT
Boundary Survey | RS
TIMP
TR
TW
TWV

## CP-ACM
[21 empty] | Mears |  |  |  | Vecor |  |  |  | Campos |  |  |  | ARK
# | Project Type | Engineering Number | WO | Town | Project Lead | Scope | RFP Issuance | RFP Due | Planned NTP | Expected Completion | Issued for KH Approval | KH approval Received | to Nicor for Approval | Nicor Approval | Actual NTP | Co-Signed IPO Returned | Sub Task Number | Current Expected Compl | Deliverables Received | Billed Nicor? | Issued to | Proposal Received | Cost | Schedule | Issued to2 | Proposal Received3 | Cost4 | Schedule5 | Issued to6 | Proposal Received7 | Cost8 | Schedule9 | Issued to62 | Proposal Received73 | Cost84 | Schedule95 | Contractor Selected | Amount
1 | Non-Dot | NBA1822993 | 168679 | DeKalb | L. Crofton | CP/AC Design | 2021-05-12 | 2021-05-17 | 2021-06-07 | 2021-06-21 | 2021-05-21 | 2021-06-04 |  |  | 2021-06-07 |  |  | 2021-06-21 |  |  | X | 2021-05-17 | 20990 |  | X | 2021-05-17 | 46551 |  | X | 2021-05-17 | 85926 |  | X | 2021-05-16 | 12200 |  |  | NO SELECTION
2 | TR | - | - | Bensenville | Mitchell Pohlman | CP/AC Design | 2023-03-19 | 2023-03-23 | 2023-04-15 | 2023-09-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-09-22 | 2023-09-26 | X | 168777008.Z.002 | N/A | Canelled | N | [12 empty] | x | 2023-04-28 | 21700
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Subcoord and subconsultant tasks should be opened once we provide NTP and have both executed IPO and WO Forms
Note on U2: Whitson, Bryan: TBD = Ready to bill to Nicor N = Hold off on billing to Nicor DATE = Month it was billed to Nicor

## Sheet1
SUB | Invoice Date | Sub Invoice # | KH Program | ENG # | TOWN | KH Project # | Month Reported | Invoiced | Survey, Geotech, Misc | Field Noting & Locating | Staffing | Total
Shäctee Engineering |  | Forecast | CRA | RS1249 | Roselle | 168777007.G.606 | 2025-03-01 | 0 | 5000 |  |  | 5000
Shäctee Engineering |  |  | CRA | COR1062 | Glenwood | 168777007.H.804 | 2025-03-01 | 0 |  |  | 5979.5 | 5979.5
Shäctee Engineering |  |  | CRA | COR1063 | Joliet | 168777007.H.805 | 2025-03-01 | 6861.4375 |  |  | 6749.5 | 6749.5
Shäctee Engineering |  |  | Non-DOT | MR2203 | Wilmington | 168777007.J.007 | 2025-03-01 | 15029.5916 |  |  | 6000 | 6000
Shäctee Engineering |  |  | Non-DOT | MR2203 | Wilmington | 168777007.J.007 | 2025-03-01 | 15029.5916 |  |  | 5906 | 5906
Shäctee Engineering (Forecast) |  |  | CRA | COR1065-76 Projects | All | All | 2025-03-01 | 0 | 10000 | 18000 | 18000 | 46000
Shäctee Engineering |  |  | DOT | M16089 | Oak Forest | 168777007.M.037 | 2025-03-01 | 0 |  | 14396.49 |  | 14396.49
Shäctee Engineering |  |  | Non-DOT | NBA10013465 | Gilman | 168777007.J.505 | 2025-03-01 | 0 |  |  | 129.75 | 129.75
Shäctee Engineering |  |  | Non-DOT | NBA10013465 | Gilman | 168777007.J.505 | 2025-03-01 | 0 |  |  | 13698 | 13698
Shäctee Engineering |  |  | DOT | SC18359 | Oswego | 168777007.M.032 | 2025-03-01 | 0 |  |  | 4306.25 | 4306.25
Shäctee Engineering |  |  | TR | TWS119 | Kings |  | 2025-03-01 | 0 |  |  | 6000 | 6000
Shäctee Engineering (Forecast) |  |  | CRA | COR Projects | All | All | 2025-04-01 | 0 |  | 4500 | 18000 | 22500
Shäctee Engineering |  |  | DOT | N10173 | Hawthorn Woods | 168777007.D.088 | 2025-04-01 | 9111.6667 |  |  | 3316.5 | 3316.5
Shäctee Engineering |  |  | DOT | N10173 | Hawthorn Woods | 168777007.D.088 | 2025-04-01 | 9111.6667 |  |  | 1856 | 1856
Shäctee Engineering |  |  | DOT | SC25418 | Normal | 168777007.M.051 | 2025-04-01 | 0 |  |  | 4234.48 | 4234.48
Shäctee Engineering |  |  | DOT | M15904 | Maywood | 168777007.M.030 | 2025-01-01 | 21989.468 |  |  | 2053 | 2053
Shäctee Engineering (Forecast) |  |  | CRA | COR Projects | All | All | 2025-05-01 | 0 |  |  | 18000 | 18000
Shäctee Engineering (Forecast) |  |  | DOT | N18492 | Long Grove | 168777007.M.045 | 2025-05-01 | 0 |  |  | 8486.34 | 8486.34
Shäctee Engineering |  |  | DOT | N16744 | Crystal Lake | 168777007.D.165 | 2025-06-01 | 0 |  |  | 47796.5 | 47796.5
Helix Engineering |  |  | DOT TR | M15898 | Glenview | 168777007.D.154 | 2025-04-01 | #VALUE! |  | 6250 |  | #REF!
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulls the invoice amount from Completed Projects
Note on J1: Dina, Eric: Report Nicor spend as soon as we're invoiced. Report internal spend the month that the project fee is invoiced.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan /@Rojas, Taylor - Please check this row. The amount looks to be an estimated fee minus an amount actually invoiced but it takes away an amount from COR1061 not COR1062?
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan /@Rojas, Taylor - Can you check this row. I think this one might be completely messed up?
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan / @Rojas, Taylor - can you confirm if this is just an estimate/can be deleted? Looks like it is. Reply: this can probably be deleted. looks too round of a number. has to be an estimate someone entered
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan / @Rojas, Taylor - can you confirm if this is just an estimate/can be deleted? Looks like it is. Reply: this was from their 6,540.50 estimate minus the 634.50 they billed in December
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADA Surveys
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated 1500/project. Likely low
Note on L7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forecasting subbing out 2
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan /@Rojas, Taylor - can you please look into the red cells in this row? Im concerned that we reported staffing spend in Jan that wasn’t real. If this isnt real spend, please just respond to this comment. Reply: this was an estimate amount from Shactee. we have not received an invoice for this exact amount. this should not have been reported as their is not an invoice actually attached to it and it is not IPO related.
Note on L17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Betland, Joseph / @Dina, Eric - FYI pending Logan/Taylors findings to the left, this may have been mis-reported in Jan. Reply: will check it out once it's all done
Note on H21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DOT TR Reply: Updated to next year since we haven't released this yet

## Field Noting
[12 empty] | DLZ |  |  |  | Helix |  |  |  | Millennia |  |  |  | Dawood |  |  |  | Shactee |  |  |  | LWS
Project Type | Engineering Number | Town | Project Lead | Scope | RFP Issuance | Actual NTP | Sub Task Number | Current Expected Compl | Deliverables Received | Anticipated Nicor Report Month | Billed/ Reported to Nicor? | Issued to DLZ | Proposal Received DLZ | Cost DLZ | Schedule DLZ | Issued to Helix | Proposal Received Helix | Cost Helix | Schedule Helix | Issued to Millennia | Proposal Received Millennia | Cost Millennia | Schedule Millennia | Issued to Dawood | Proposal Received Dawood | Cost Dawood | Schedule Dawood | Issued to Shactee | Proposal Recieved Shactee | Cost Shactee | Schedule Shactee | Issued to LWS | Proposal Received LWS | Cost LWS | Schedule LWS | Contractor Selected | Amount | Helix Total | Millennia Total | DLZ Total | Dawood Total | Shactee Total
DOT | SC18611 | Normal | Camille Corbi | SUE Level B | 2023-09-19 | 2023-09-25 | 168777007.D.903 | 2023-10-11 | 2023-10-11 | 2023-10-01 | Y | X | Declined |  |  | X | 2023-09-22 | 7300 | 2023-10-11 | [16 empty] | Helix | 7300 | 7300 | 0 | 0 | 0 | 0
DOT | M15844 | Justice | Camille Corbi | SUE Level B | 2024-04-23 | 2024-04-24 | 168777007.D.903 | 2024-05-02 | 2024-04-30 | 2024-06-01 | Y |  |  |  |  | X | 2024-04-23 | 2950 | 2024-05-02 | [16 empty] | Helix | 2950 | 2950 | 0 | 0 | 0 | 0
DOT | SC24292 | Plainfield | Camille Corbi | SUE Level B | 2024-04-02 | 2024-04-02 | 168777007.D.150 | 2024-04-18 | 2024-04-18 | 2024-08-01 | Y |  |  |  |  | X | 2024-04-03 | 16760 | 2024-04-18 | [16 empty] | Helix | 16760 | 16760 | 0 | 0 | 0 | 0
DOT | SC24018 | Addison | Camille Corbi | Redline Locates | 2024-08-29 | 2024-08-29 | 168777007.D.999 | 2024-09-05 | 2024-09-04 | 2024-09-01 | Y | [16 empty] | X | N/A | [6 empty] | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | M13314 | Wood Dale | Camille Corbi | Redline Locates | 2024-08-21 | 2024-08-21 | 168777007.D.999 | 2024-08-28 | 2024-08-22 | 2024-09-01 | Y | [16 empty] | X | N/A | [6 empty] | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | SC24878 | Normal | Camille Corbi | SUE Level B | 2024-08-15 | 2024-08-15 | 168777007.M.900 | 2024-08-23 | 2024-08-21 | 2024-10-24 | Y | [16 empty] | X | N/A | 1520.43 | 2024-08-21 |  |  |  |  | Shactee | 1520.43 | 0 | 0 | 0 | 0 | 1520.43
DOT | N14793 | Woodstock | Camille Corbi | SUE Level A | 2024-04-02 | 2024-04-12 | 168777007.D.906 | 2024-05-23 | 2024-05-23 | 2024-12-01 | Y |  |  |  |  | X | [15 empty] | X | 2024-04-11 | 15925 | 2024-04-26 | LWS | 15925 | 0 | 0 | 0 | 0 | 0
DOT | N14793 | Woodstock | Camille Corbi | SUE Level B | 2024-01-16 | 2024-01-18 | 168777007.D.903 | 2024-02-09 | 2024-02-09 | 2024-12-01 | Y |  |  |  |  | X | 2024-01-18 | 17185 | 2024-02-02 | [16 empty] | Helix | 17185 | 17185 | 0 | 0 | 0 | 0
DOT | SC22322 | Bloomingdale | Camille Corbi | Redline Locates | 2024-12-11 | 2024-12-11 | 168777007.D.999 | 2024-12-18 | 2024-12-16 | 2025-01-01 | Y | [16 empty] | X | N/A | [6 empty] | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | SC18359 | Oswego | Camille Corbi | SUE Level B | 2024-10-08 | 2024-10-08 | 168777007.M.903 | 2024-10-16 | 2024-10-11 | 2025-03-25 | Y |  |  |  |  | X | 2024-10-08 | 2430 | 2024-10-16 | [16 empty] | Helix | 2430 | 2430 | 0 | 0 | 0 | 0
Non-DOT | MR2BID5541 | Oak Park | Camille Corbi | Locates | N/A | N/A | 168777007.J.011 | 2025-03-05 | 2025-03-05 | 2025-05-01 | Y | [24 empty] | Shactee | 1272.6 | 0 | 0 | 0 | 0 | 1272.6
Non-DOT | MR2BID5541 | Oak Park | Camille Corbi | Locates | N/A | N/A | 168777007.J.011 | 2025-02-21 | 2025-02-21 | 2025-05-01 | Y | [24 empty] | Shactee | 816.63 | 0 | 0 | 0 | 0 | 816.63
Non-DOT | MR2BID5541 | Oak Park | Camille Corbi | Locates | N/A | N/A | 168777007.J.011 | 2025-02-21 | 2025-02-21 | 2025-05-01 | Y | [24 empty] | Shactee | 1757.81 | 0 | 0 | 0 | 0 | 1757.81
DOT | N19470 | Sterling Twp | Camille Corbi | Redline Locates | 2025-06-26 | 2025-06-26 | 168777007.D.999 | 2025-07-03 | 2025-06-30 | 2025-09-01 | N | [16 empty] | X | N/A | 2435.58 | 2025-06-30 |  |  |  |  | Shactee | 2435.58 | 0 | 0 | 0 | 0 | 2435.58
DOT | N14644 | WHEELING | Camille Corbi | SUE Level B | 2025-01-14 | 2025-01-16 | 168777007.M.903 | 2025-02-10 | 2025-02-10 | 2025-09-01 | N |  |  |  |  | X | 2025-01-15 | 19785 | 2025-02-06 | [16 empty] | Helix | 19785 | 19785 | 0 | 0 | 0 | 0
DOT | N17936 | Arlington Heights | Camille Corbi | SUE Level B | 2025-08-05 | 2025-08-07 | 168777007.M.903 | 2025-08-14 |  | 2025-11-01 | N |  |  |  |  | X | 2025-08-07 | 6900 | 2025-08-14 | [16 empty] | Helix | 6900 | 6900 | 0 | 0 | 0 | 0
DOT | SC24323 | NEW LENOX | Camille Corbi | SUE Level B | 2025-01-06 | 2025-01-13 | 168777007.M.903 | 2025-01-27 | 2025-01-27 | 2025-12-01 | N |  |  |  |  | X | 2025-01-09 | 7800 | 2025-01-30 | [16 empty] | helix | 7800 | 7800 | 0 | 0 | 0 | 0
DOT | SC25268 | New Lenox | Camille Corbi | SUE Level B | 2024-11-21 | 2024-11-26 | 168777007.M.903 | 2024-12-18 | 2024-12-18 | 2025-12-01 | N |  |  |  |  | X | 2024-11-22 | 11350 | 2024-12-18 | [16 empty] | Helix | 11350 | 11350 | 0 | 0 | 0 | 0
DOT | SC25957 | GILMAN | Camille Corbi | SUE Level B | 2025-09-03 | 2025-09-05 | 168777007.M.903 | 2025-09-12 | 2025-09-10 | 2025-11-01 | N |  |  |  |  | X | 2025-09-04 | 2000 | 2025-09-12 | [16 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0
DOT | SC25997 | Yorkville | Caroline Kulach | Redline Locates | 2025-05-06 | 2025-05-06 | 168777009.2.499 | 2025-05-13 | 2025-05-08 | 2025-05-25 | Y | [16 empty] | X | TBD | T&M | 2025-05-13 |  |  |  |  | Shactee | T&M | 0 | 0 | 0 | 0 | T&M
DOT | SC25330 | Grant Park | Caroline Kulach | SUE Level B | 2024-12-30 | 2025-10-03 | 168777007.M.903 | 2025-01-09 | 2025-01-08 | 2025-07-01 | Y |  |  |  |  | X | 2025-01-02 | 3100 | 2025-01-09 | [16 empty] | Helix | 3100 | 3100 | 0 | 0 | 0 | 0
DOT | SC25757 | St. Charles | Caroline Kulach | Sue Level B | 2025-05-16 | 2025-05-19 | 168777007.M.071 | 2024-06-04 | 2025-06-10 | 2025-07-25 | Y |  |  |  |  | X | 2025-05-19 | 10660 | 2025-05-26 | [16 empty] | Helix | 10660 | 10660 | 0 | 0 | 0 | 0
DOT | N15864 | McHenry | Caroline Kulach | SUE Level B | 2025-05-11 | 2025-05-12 | 168777007.M.073 | 2025-05-21 | 2025-05-20 | 2025-08-01 | N |  |  |  |  | X | 2025-05-11 | 3195 | 2025-05-21 | [16 empty] | Helix | 3195 | 3195 | 0 | 0 | 0 | 0
DOT | N19472 | Hanover Park | Caroline Kulach | SUE Level B | 2025-03-26 | 2025-03-26 | 168777007.M.057 | 2025-04-02 | 2025-04-03 | 2025-10-01 | N |  |  |  |  | X | 2025-03-27 | 7670 | 2025-04-03 | [16 empty] | Helix | 7670 | 7670 | 0 | 0 | 0 | 0
DOT | N19472 | Hanover Park | Caroline Kulach | Topo Survey | 2025-08-19 | 2025-08-26 | 168777007.E.105 | 2025-09-05 | 2025-09-05 | 2025-10-01 | N |  |  |  |  | X | 2025-08-20 | 2000 | 2025-09-05 | [16 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0
DOT | SC25745 | Ford Heights | Caroline Kulach | Survey | 2025-07-28 | 2025-08-08 | 168777007.M.064 | TBD | TBD | 2025-10-01 | N | X | 2025-07-29 | 33850 | [5 empty] | X | Declined | [14 empty] | DLZ | 33850 | 0 | 0 | 33850 | 0 | 0
DOT | SC25745 | Ford Heights | Caroline Kulach | SUE Level B | 2025-06-16 | 2025-06-18 | 168777007.M.064 | 2025-06-25 | 2025-06-25 | 2025-10-01 | N |  |  |  |  | X | 2025-06-17 | 3895 | 2025-06-25 | [16 empty] | Helix | 3895 | 3895 | 0 | 0 | 0 | 0
DOT | M12594 | Niles | Caroline Kulach | SUE Level B | 2025-03-05 | 2024-03-10 | 168777007.M.054 | 2025-03-14 | 2025-03-18 | 2025-10-01 | N |  |  |  |  | X | 2025-03-06 | 3615 | 2025-03-18 | [16 empty] | Helix | 3615 | 3615 | 0 | 0 | 0 | 0
DOT | N19002 | Oregon | Caroline Kulach/Taylor Lierow | Sue Level B | 2024-11-14 | 2024-11-20 | 168777007.M.041 | 2024-11-26 | 2024-11-26 | 2025-03-25 | Y |  |  |  |  | X | 2024-11-18 | 3785 | 2024-11-26 | [16 empty] | Helix | 3785 | 3785 | 0 | 0 | 0 | 0
DOT | N16609 | Rockford | Conner Chamernik | SUE Level B | 2023-09-14 | 2023-09-19 | 168777007.X.003 | 2023-10-04 | 2023-09-29 | 2023-10-01 | Y | X | 2023-09-19 | 22450 | 2023-10-04 | - | - | - | - | [16 empty] | DLZ | 22450 | 0 | 0 | 22450 | 0 | 0
DOT | N15012 | E Dubuque | Conner Chamernik | Survey, SUE Level B | 2023-10-23 | 2023-10-25 | 168777007.D.903 | 2023-11-09 | 2023-11-03 | 2023-11-01 | Y | X | Declined | - | - | X | 2023-10-23 | 3000 | 2023-11-13 | [16 empty] | Helix | 3000 | 3000 | 0 | 0 | 0 | 0
DOT | N17925 | Hoffman Estates | Conner Chamernik | SUE Level B | 2023-10-09 | 2023-10-12 | 168777007.D.903 | 2023-10-30 | 2023-10-30 | 2023-11-01 | Y | X | 2023-10-11 | 32950 | 2023-10-30 | X | 2023-10-11 | 8990 | 2023-10-30 | [16 empty] | Helix | 8990 | 8990 | 0 | 0 | 0 | 0
DOT | N18056 | Buffalo Grove | Conner Chamernik | Survey, SUE Level B | 2023-11-29 | 2023-11-30 | 168777007.D.904 | 2023-12-08 | 2023-12-07 | 2023-12-01 | Y |  |  |  |  | X | 2023-11-29 | 3800 | 2023-12-08 | [16 empty] | Helix | 3800 | 3800 | 0 | 0 | 0 | 0
DOT | SC23728 | Ottawa | Conner Chamernik | Survey, SUE Level B | 2023-11-10 | 2023-11-15 | 168777007.X.004 | 2023-11-30 | 2023-11-30 | 2024-01-01 | Y | X | Declined | - | - | X | 2023-11-10 | 5200 | 2023-12-01 | X | 2023-11-14 | 10040 | 2023-12-01 | [12 empty] | Millennia | 10040 | 0 | 10040 | 0 | 0 | 0
DOT | N16291 | Prospect Heights | Conner Chamernik | SUE Level B | 2024-02-28 | 2024-02-29 | 168777007.D.903 | 2024-03-14 | 2024-03-11 | 2024-05-01 | Y |  |  |  |  | X | 2024-02-28 | 4100 | 2024-03-11 | [16 empty] | Helix | 4100 | 4100 | 0 | 0 | 0 | 0
DOT | SC24208 | Lockport | Conner Chamernik | SUE Level B | 2024-03-05 | 2024-03-06 | 168777007.D.903 | 2024-03-20 | 2024-03-15 | 2024-06-01 | Y |  |  |  |  | X | 2024-03-05 | 4200 | 3/20/24 | [16 empty] | Helix | 4200 | 4200 | 0 | 0 | 0 | 0
DOT | N16431 | Rock Falls | Conner Chamernik | SUE Level B | 2024-02-06 | 2024-02-08 | 168777007.D.903 | 2024-02-22 | 2024-02-22 | 2024-06-01 | Y |  |  |  |  | X | 2024-01-06 | 6850 | 2024-02-22 | [16 empty] | Helix | 6850 | 6850 | 0 | 0 | 0 | 0
DOT | N18056 | Buffalo Grove | Conner Chamernik | Survey, SUE Level B | 2024-08-29 | 2024-08-30 | 168777007.E.053 | 2024-09-09 | 2024-09-09 | 2024-09-24 | Y |  |  |  |  | X | 2024-08-30 | 3500 | 2024-09-09 | [16 empty] | Helix | 3500 | 3500 | 0 | 0 | 0 | 0
DOT | M13879 | Park Ridge | Conner Chamernik | SUE Level B | 2024-06-21 | 2024-06-24 | 168777007.M.903 | 2024-07-01 | 2024-07-01 | 2024-09-24 | Y |  |  |  |  | X | 2024-06-24 | 5000 | 2024-07-01 | [16 empty] | Helix | 5000 | 5000 | 0 | 0 | 0 | 0
DOT | M13879 | Park Ridge | Conner Chamernik | SUE Level B | 2024-08-05 | 2024-08-05 | 168777007.M.900 | 2024-08-09 | 2024-08-08 | 2024-09-24 | Y | [16 empty] | X | 2024-08-05 | 679.5 | 2024-08-08 |  |  |  |  | Shactee | 679.5 | 0 | 0 | 0 | 0 | 679.5
DOT | SC24952 | Bloomingdale | Conner Chamernik | Service Locates | 2024-09-05 | 2024-09-05 | 168777007.M.025 | 2024-09-06 | 2024-09-06 | 2024-10-01 | Y | [16 empty] | X | N/A | 445.59 | 2024-09-06 |  |  |  |  | Shactee | 445.59 | 0 | 0 | 0 | 0 | 445.59
DOT | M11560 | Northlake | Conner Chamernik | SUE Level B | 2024-04-03 | 2024-04-04 | 168777007.M.903 | 2024-04-12 | 2024-04-12 | 2024-10-01 | Y |  |  |  |  | X | 2024-04-04 | 8750 | 2024-04-12 | [16 empty] | Helix | 8750 | 8750 | 0 | 0 | 0 | 0
DOT | SC19500 | Shorewood | Conner Chamernik | SUE Level B | 2024-08-21 | 2024-08-21 | 168777007.E.036 | 2024-08-28 | 2024-08-28 | 2024-11-01 | Y | [16 empty] | X | 2024-08-21 | 699.36 | 2024-08-28 |  |  |  |  | Shactee | 699.36 | 0 | 0 | 0 | 0 | 699.36
DOT | SC21136 | Plano | Conner Chamernik | Redline Locates | 2024-10-11 | 2024-10-11 | 168777007.D.999 | 2024-10-18 | 2024-10-18 | 2024-11-24 | Y | [16 empty] | X | N/A | 1693.13 | 2024-10-18 |  |  |  |  | Shactee | 1693.13 | 0 | 0 | 0 | 0 | 1693.13
DOT | SC24047 | Joliet | Conner Chamernik | SUE Level B | 2024-10-30 | 2024-10-31 | 168777007.M.040 | 2024-11-06 | 2024-11-04 | 2024-12-01 | Y | [16 empty] | X | N/A |  | 2024-11-06 |  |  |  |  | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | N17722 | Wheeling | Conner Chamernik | SUE Level B | 2024-10-21 | 2024-10-22 | 168777007.M.903 | 2024-11-05 | 2024-11-04 | 2024-12-24 | Y |  |  |  |  | X | 2024-10-21 | 13975 | 2024-11-05 | [16 empty] | Helix | 13975 | 13975 | 0 | 0 | 0 | 0
DOT | SC20245 | Carol Stream | Conner Chamernik | SUE Level B | 2024-09-12 |  | 168777007.M.903 | 2024-10-01 | 2024-09-27 | 2025-03-25 | Y |  |  |  |  | X | 2024-09-16 | 3900 | 2024-09-30 | [16 empty] | Helix | 3900 | 3900 | 0 | 0 | 0 | 0
DOT | SC24631 | St Charles | Conner Chamernik | SUE Level B | 2024-06-13 | 2024-06-14 | 168777007.M.903 | 2024-06-24 | 2024-06-21 | 2025-04-25 | Y |  |  |  |  | X | 2024-06-14 | 7330 | 2024-06-24 | [16 empty] | Helix | 7330 | 7330 | 0 | 0 | 0 | 0
DOT | N17865/N17865-1 | Elk Grove Village | Conner Chamernik | SUE Level B | 2024-08-01 | 2024-08-05 | 168777007.D.903 | 2024-08-30 | 2024-08-30 | 2025-06-25 | Y |  |  |  |  | X | 2024-08-05 | 34500 | 2024-08-30 | [16 empty] | Helix | 34500 | 34500 | 0 | 0 | 0 | 0
DOT | N18824 | Algonquin | Conner Chamernik | Redline Locates | 2025-04-02 | 2025-04-02 | 168777007.D.999 | 2025-04-09 | 2025-04-09 | 2025-06-25 | Y | [16 empty] | X | N/A | 1109.73 | [5 empty] | Shactee | 1109.73 | 0 | 0 | 0 | 0 | 1109.73
DOT | N17865 | Elk Grove Village | Conner Chamernik | Flagging | 2025-01-13 | 2025-01-14 | 168777007.D.903 | 2025-01-21 | 2025-01-21 | 2025-06-25 | Y |  |  |  |  | X | 2025-01-14 | 2500 | 2025-01-21 | [16 empty] | Helix | 2500 | 2500 | 0 | 0 | 0 | 0
DOT | SC24978 | New Lenox | Conner Chamernik | Redline Locates | 2025-04-15 | 2025-04-15 | 168777007.D.999 | 2025-04-22 | 2025-04-21 | 2025-06-25 | Y | [16 empty] | X | N/A | 510.16 | [5 empty] | Shactee | 510.16 | 0 | 0 | 0 | 0 | 510.16
DOT | SC17821 | Villa Park | Conner Chamernik | Redline Locates | 2025-04-15 | 2025-04-15 | 168777007.D.999 | 2025-04-22 | 2025-04-21 | 2025-06-25 | Y | [16 empty] | X | N/A | 1806.8 | [5 empty] | Shactee | 1806.8 | 0 | 0 | 0 | 0 | 1806.8
DOT | N18592 | McHenry | Conner Chamernik | SUE Level B | 2024-04-16 | 2024-04-17 | 168777007.D.903 | 2024-04-18 | 2024-04-25 | 2025-06-25 | Y |  |  |  |  | X | 2024-04-17 | 2200 | 2024-04-25 | [16 empty] | Helix | 2200 | 2200 | 0 | 0 | 0 | 0
DOT | SC24663 | Olympia Fields | Conner Chamernik | SUE LEVEL B | 2025-05-01 | 2025-05-02 | 168777007.M.903 | 2025-05-19 | 2025-05-12 | 2025-07-25 | Y |  |  |  |  | X | 2025-05-02 | 10925 | 2025-05-12 | [16 empty] | Helix | 10925 | 10925 | 0 | 0 | 0 | 0
DOT | N19030 | Round Lake Beach | Conner Chamernik | SUE Level B | 2024-09-25 | 2024-09-25 | 168777007.M.903 | 2024-10-07 | 2024-10-10 | 2025-07-25 | Y |  |  |  |  | X | 2024-09-27 | 4900 | [17 empty] | Helix | 4900 | 4900 | 0 | 0 | 0 | 0
Non-DOT | PRIM718 | GLENDALE HEIGHTS | Conner Chamernik | SUE Level B | 2025-06-12 | 2025-06-13 | 168777007.J.600 | 2025-06-23 | 2025-06-20 | 2025-08-01 | N |  |  |  |  | X | [19 empty] | Helix | 1320 | 1320 | 0 | 0 | 0 | 0
Non-DOT | PRIM718 | GLENDALE HEIGHTS | Conner Chamernik | Locates | 2025-05-21 | 2025-05-21 | 168777007.J.600 | 2025-06-04 | 2025-06-04 | 2025-09-25 | N | [16 empty] | X | TBD | 724 | 2025-06-04 |  |  |  |  | Shactee | 724 | 0 | 0 | 0 | 0 | 724
DOT | N20224 | KANE CO | Conner Chamernik | Redline Locates | 2025-08-05 | 2025-08-05 | 168777007.D.999 | 2025-08-12 | 2025-08-11 | 2025-10-01 | N | [16 empty] | X | N/A | 1208.45 | 2025-08-12 |  |  |  |  | Shactee | 1208.45 | 0 | 0 | 0 | 0 | 1208.45
DOT | N20239 | Spring Grove | Conner Chamernik | Redline Locates | 2025-08-19 | 2025-08-19 | 168777007.D.999 | 2025-08-26 |  | 2025-10-01 | N | [16 empty] | X | TBD | T&M | 2025-08-26 |  |  |  |  | Shactee | T&M | 0 | 0 | 0 | 0 | T&M
DOT | SC24448 | Joliet | Conner Chamernik | Redline Locates | 2025-08-08 | 2025-08-08 | 168777007.D.999 | 2025-08-15 |  | 2025-09-25 | N | [16 empty] | X | N/A | 1200 | [5 empty] | Shactee | 1200 | 0 | 0 | 0 | 0 | 1200
DOT | SC24452 | Joliet | Conner Chamernik | SUE Level B | 2024-07-29 | 2024-08-13 | 168777007.D.903 | 2024-09-09 | 2024-09-09 | 2025-11-01 | N |  |  |  |  | X | 2024-08-12 | 16500 | 2024-09-09 | [16 empty] | Helix | 16500 | 16500 | 0 | 0 | 0 | 0
DOT | SC21753 | Wheaton | Eric Dina | Survey, SUE Level B | 2023-07-10 | 2023-07-27 | 168777007.X.500 | 2023-08-10 | 2023-08-10 | 2023-08-01 | Y | X | 2023-07-19 | 29250 | 2-3 wks NTP | X | 2023-07-18 | 11200 | 2023-08-07 | [16 empty] | Helix | 11200 | 11200 | 0 | 0 | 0 | 0
DOT | SC21753 | Wheaton | Eric Dina | Survey, SUE Level B | 2023-09-14 | 2023-09-19 | 168777007.D.903 | 2023-10-13 | 2023-10-10 | 2023-10-01 | Y |  |  |  |  | X | 2023-09-18 | 29500 | 2023-10-13 | [16 empty] | Helix | 29500 | 29500 | 0 | 0 | 0 | 0
DOT | N18268 | Palatine | Eric Dina | SUE Level B | 2024-01-22 | 2024-01-22 | 168777007.D.903 | 2024-02-02 | 2024-01-31 | 2024-05-01 | Y |  |  |  |  | X | 2024-01-22 | 2550 | 2024-02-02 | [16 empty] | Helix | 2550 | 2550 | 0 | 0 | 0 | 0
DOT | N15193 | Streamwood | Eric Dina | Survey, SUE Level B | 2024-01-29 | 2024-01-31 | 168777007.D.903 | 2024-02-16 | 2024-02-16 | 2024-06-01 | Y |  |  |  |  | X | 2024-01-30 | 7300 | 2024-02-16 | [16 empty] | Helix | 7300 | 7300 | 0 | 0 | 0 | 0
DOT | M10905 | Justice | Eric Dina | SUE Level B | 2024-11-26 | 2024-12-02 | 168777007.E.072 | 2024-12-06 | 2024-12-06 | 2025-02-25 | Y |  |  |  |  | X | 2024-11-27 | 2500 | 2025-12-06 | [16 empty] | Helix | 2500 | 2500 | 0 | 0 | 0 | 0
DOT | SC20556 | Bloomington | Eric Dina/ Ethan Ekstrom | SUE Level B | 2024-03-21 | 2024-03-23 | 168777007.D.148 | 2024-04-05 | 2024-04-03 | 2024-09-01 | Y |  |  |  |  | X | 2024-03-22 | 3640 | 2024-04-05 | [16 empty] | Helix | 3640 | 3640 | 0 | 0 | 0 | 0
DOT | SC20556 | Bloomington | Eric Dina/ Ethan Ekstrom | SUE Level A | 2024-04-05 | 2024-04-09 | 168777007.D.904 | 2024-05-10 | 2024-05-07 | 2024-09-01 | Y |  |  |  |  | X |  |  |  | X | 2024-04-09 | 1903-10-26 | 2024-04-15 | [12 empty] | Millennia | 1395 | 0 | 1395 | 0 | 0 | 0
DOT | N18640 | Buffalo Grove | Ethan Ekstrom | SUE Level B | 2024-05-22 | 2024-05-23 | 168777007.M.013 | 2024-06-03 | 2024-06-03 | 2024-11-01 | Y |  |  |  |  | X | 2024-05-23 | 9750 | 2024-06-03 | [16 empty] | Helix | 9750 | 9750 | 0 | 0 | 0 | 0
DOT | N18674 | Prospect Heights | Ethan Ekstrom | SUE Level B | 2024-10-24 | 2024-10-28 | 168777007.M.039 | 2024-11-04 | 2024-11-04 | 2025-03-25 | Y |  |  |  |  | X | 2024-10-24 | 5350 | 2024-11-04 | [16 empty] | Helix | 5350 | 5350 | 0 | 0 | 0 | 0
DOT | N13645 | Buffalo Grove | Ethan Ekstrom | SUE Level B | 2024-12-30 | 2025-01-03 | 168777007.M.049 | 2025-01-17 | 2025-01-17 | 2025-04-25 | Y |  |  |  |  | X | 2025-01-03 | 18335 | 2025-01-17 | [16 empty] | Helix | 18335 | 18335 | 0 | 0 | 0 | 0
DOT | M16089 | Oak Forest | Ethan Ekstrom | Redline Locates | 2024-10-31 | 2024-10-31 | 168777007.M.037 | 2024-11-13 | 2024-11-13 | 2025-04-25 | Y | [16 empty] | X | 2024-10-31 | 7198.72 | 2024-11-13 |  |  |  |  | Shactee | 7198.72 | 0 | 0 | 0 | 0 | 7198.72
DOT | N19947 | Elk Grove Village | Ethan Ekstrom | Redline Locates | 2025-06-25 | 2025-06-25 | 168777007.D.999 | 2025-07-07 | 2025-07-07 | 2025-07-01 | Y | [16 empty] | X | N/A | 4064.81 | 2025-07-25 |  |  |  |  | Shactee | 4064.81 | 0 | 0 | 0 | 0 | 4064.81
DOT | SC25188 | Bloomington | Ethan Ekstrom | SUE Level B | 2025-04-21 | 2025-04-22 | 168777007.M.068 | 2025-05-01 | 2025-05-01 | 2025-11-01 | N |  |  |  |  | X | 2025-04-22 | 6945 | 2025-05-01 | [16 empty] | Helix | 6945 | 6945 | 0 | 0 | 0 | 0
DOT | SC25188 | Bloomington | Ethan Ekstrom | Survey, SUE Level B | 2025-06-11 | 2025-06-12 | 168777007.M.068 | 2025-07-07 | 2025-07-07 | 2025-11-01 | N |  |  |  |  | X | 2025-06-12 | 14120 | 2025-07-07 | [16 empty] | Helix | 14120 | 14120 | 0 | 0 | 0 | 0
DOT | N17019 | Mt Prospect | Ethan Ekstrom | Survey, SUE Level B | 2025-06-11 | 2025-06-12 | 168777007.M.034 | 2025-06-30 | 2025-06-30 | 2025-12-01 | N |  |  |  |  | X | 2025-06-12 | 4420 | 2025-06-30 | [16 empty] | Helix | 4420 | 4420 | 0 | 0 | 0 | 0
CRA | RS1238 | Mt Morris | Madie Roman | SUE Level B | N/A | 2024-09-10 | 168777007.G.605 | 2024-09-24 | 2024-09-17 | 2024-11-01 | Y | [16 empty] | X | N/A |  | 2024-09-24 |  |  |  |  | Shactee
CRA | RS1254 | Gilberts | Madie Roman | SUE Level B | N/A | 2024-09-10 | 168777007.G.609 | 2024-10-03 | 2024-09-24 | 2024-12-01 | Y | [16 empty] | X | N/A |  | 2024-10-03 |  |  |  |  | Shactee
COR | COR1058 | CRESTWOOD | Madie Roman | Locates | 2024-12-02 | 2024-12-02 | 168777007.H.800 | 2024-12-10 | 2024-12-09 | 2025-02-25 | Y | [16 empty] | X | N/A | 863.25 | 2024-12-10 |  |  |  |  | Shactee |  |  |  |  | 0
COR | COR1059 | Glenwood | Madie Roman | Locates | N/A | 2024-12-16 | 168777007.H.801 | 2024-12-23 | 2024-12-23 | 2025-03-01 | Y | [16 empty] | X | N/A | 2355.79 | 2024-12-23 |  |  |  |  | Shactee | 2355.79 | 0 | 0 | 0 | 0 | 2355.79
COR | COR1062 | GLENWOOD | Madie Roman | Locates | 2024-12-02 | 2024-12-02 | 168777007.H.804 | 2024-12-11 | 2024-12-09 | 2025-03-01 | Y | [16 empty] | X | N/A | 1362 | 2024-12-11 |  |  |  |  | Shactee |  |  |  |  | 0
COR | COR1064 | CRESTWOOD | Madie Roman | Locates | N/A | 2024-12-16 | 168777007.H.806 | 2024-12-24 | 2024-12-23 | 2025-03-01 | Y | [16 empty] | X | N/A | 1315.34 | 2024-12-24 |  |  |  |  | Shactee | 1315.34 | 0 | 0 | 0 | 0 | 1315.34
CRA | RS959 | Geneseo | Madie Roman | SUE Level B | N/A | 2024-10-03 | 168777007.G.500 | 2024-10-12 | 2024-10-09 | Bill ahead Accrued Hours | 2024-12-01 | [25 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0
DOT | M15904 | Maywood | Marissa LaPorte | SUE Level B | 2024-09-25 | 2024-10-01 | 168777007.M.030 | 2024-10-11 | 2024-10-11 | 2025-01-25 | Y |  |  |  |  | X | 2024-09-25 | 5390 | 2024-10-11 | [16 empty] | Helix | 5390 | 5390 | 0 | 0 | 0 | 0
COR | COR1060 | KANKAKEE | Marissa LaPorte | Locates | N/A | 2024-12-13 | 168777007.H.802 | 2024-12-23 | 2024-12-23 | 2025-03-01 | Y | [17 empty] | N/A | [6 empty] | Shactee | 0 | 0 | 0 | 0 | 0 | 0
COR | COR1061 | KANKAKEE | Marissa LaPorte | Locates | 2024-12-02 | 2024-12-02 | 168777007.H.803 | 2024-12-10 | 2024-12-09 | 2025-03-10 | Y | [16 empty] | X | N/A | 879.5 | 2024-12-10 |  |  |  |  | Shactee |  |  |  |  | 0
COR | COR1063 | JOLIET | Marissa LaPorte | Locates | 2024-12-02 | 2024-12-02 | 168777007.H.805 | 2024-12-11 | 2024-12-11 | 2025-03-25 | Y | [16 empty] | X | N/A |  | 2024-12-11 |  |  |  |  | Shactee |  |  |  |  | 0
DOT | SC25775 | Plainfield | Marissa LaPorte | SUE LEVEL B | 2025-04-22 | 2025-04-23 | 168777007.M.065 | 2025-05-02 | 2025-05-02 | 2025-08-01 | N |  |  |  |  | X | 2025-04-24 | 7430 | 2025-05-02 | [16 empty] | HELIX | 7430 | 7430 | 0 | 0 | 0 | 0
DOT | SC23981 | Wheatland Twp | Marissa LaPorte | SUE Level B | 2024-06-27 | 2024-07-02 | 168777007.M.017 | 2024-06-10 | 2024-07-08 | 2025-10-01 | N |  |  |  |  | X | 2024-06-28 | 2000 | 2024-07-08 | [16 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0
TIMP | TP645 | BOURBONNAIS | Mark Stanley | SUE Level B | 2025-02-27 | 2025-03-04 | 168777008.1.033 | 2025-03-19 | 2025-03-19 | 2025-05-01 | Y |  |  |  |  | X | 2025-03-03 | 5465 | 2025-03-19 | [16 empty] | Helix | 5465 | 5465 | 0 | 0 | 0 | 0
TIMP | TP662 | Ancona | Mark Stanley | SUE Level B | 2025-07-18 | 2025-07-22 | 168777008.1.039 | 2025-08-06 | 2025-08-07 | 2025-09-01 | N |  |  |  |  | X | 2025-07-21 | 3500 | 2025-08-06 | [16 empty] | Helix | 3500 | 3500 | 0 | 0 | 0 | 0
DOT-TR | SC25259-T | Elwood | Mark Stanley | SUE Level B | 2024-11-15 | 2024-11-20 | 168777007.E.075 | 2024-11-27 | 2024-11-27 | 2025-09-01 | N |  |  |  |  | X | 2024-11-18 | 4700 | 2024-11-27 | [16 empty] | Helix | 4700 | 4700 | 0 | 0 | 0 | 0
DOT | N16744 | Crystal Lake | Mark Stanley | SUE Level B | 2024-07-25 | 2024-07-26 | 168777007.D.165 | 2024-08-09 | 2024-08-12 | 2025-11-01 | N |  |  |  |  | X | 2024-07-25 | 30500 | 2024-08-09 | [16 empty] | Helix | 30500 | 30500 | 0 | 0 | 0 | 0
DOT-TR | N19216-T | Rockford | Mark Stanley | SUE Level B | 2024-11-19 | 2024-11-22 | 168777007.E.076 | 2024-12-06 | 2024-12-04 | 2025-11-01 | N |  |  |  |  | X | 2024-11-22 | 2500 | 2024-12-06 | [16 empty] | Helix | 2500 | 2500 | 0 | 0 | 0 | 0
DOT | SC23750 | Downers Grove | Matt Hopkins | SUE Level B | 2024-02-19 | 2024-02-22 | 168777007.D.142 | 2024-03-08 | 2024-03-04 | 2024-06-01 | Y |  |  |  |  | X | 2024-02-21 | 2400 | 2024-03-08 | [16 empty] | Helix | 2400 | 2400 | 0 | 0 | 0 | 0
DOT | M15665 | Northlake | Matt Hopkins | SUE Level B | 2024-03-12 | 2024-03-15 | 168777007.D.145 | 2024-03-29 | 2024-03-29 | 2024-06-01 | Y |  |  |  |  | X | 2024-03-14 | 27500 | 2024-03-29 | [16 empty] | Helix | 27500 | 27500 | 0 | 0 | 0 | 0
DOT | SC25032 | Plainfield | Matt Hopkins | SUE Level B | 2024-09-19 | 2024-09-24 | 168777007.M.028 | 2024-09-30 | 2024-09-26 | 2024-10-24 | Y |  |  |  |  | X | 2024-09-23 | 1950 | 2024-09-30 | [16 empty] | Helix | 1950 | 1950 | 0 | 0 | 0 | 0
DOT | M15389 | Berwyn | Matt Hopkins | Redline Locates | 2024-09-23 | 2024-09-23 | 168777007.D.999 | 2024-10-01 | 2024-09-26 | 2024-11-01 | Y | [16 empty] | X | N/A | 1029.48 | 2024-09-26 |  |  |  |  | Shactee | 1029.48 | 0 | 0 | 0 | 0 | 1029.48
DOT | N12480 | Carpentersville | Matt Hopkins | SUE Level B | 2024-07-24 | 2024-07-25 | 168777007.M.020 | 2024-08-02 | 2024-08-02 | 2024-11-01 | Y |  |  |  |  | X | 2024-07-24 | 6150 | 2024-08-02 | [16 empty] | Helix | 6150 | 6150 | 0 | 0 | 0 | 0
DOT | N17110 | Dixon | Matt Hopkins | Redline Locates | 2024-10-21 | 2024-10-21 | 168777007.D.999 | 2024-10-29 | 2024-10-24 | 2024-11-24 | Y | [16 empty] | X | N/A | 1557 | 2024-10-24 |  |  |  |  | Shactee | 1557 | 0 | 0 | 0 | 0 | 1557
DOT | N18617 | Mt. Morris | Matt Hopkins | SUE Level B | 2024-04-30 | 2024-05-01 | 168777007.M.012 | 2024-05-09 | 2024-05-08 | 2024-12-01 | Y |  |  |  |  | X | 2024-05-22 | 1500 | 2024-05-09 | [16 empty] | Helix | 1500 | 1500 | 0 | 0 | 0 | 0
DOT | N18617 | Mt Morris | Matt Hopkins | SUE Level B | 2024-09-19 | 2024-09-19 | 168777007.M.012 | 2024-09-26 | 2024-09-24 | 2024-12-24 | Y | [16 empty] | X | N/A | 700 | 2024-09-26 |  |  |  |  | Shactee | 700 | 0 | 0 | 0 | 0 | 700
DOT | SC24490 | Pontiac | Matt Hopkins | SUE Level B | 2024-05-29 | 2024-05-30 | 168777007.M.903 | 2024-06-07 | 2024-06-07 | 2024-12-24 | Y |  |  |  |  | X | 2024-05-30 | 4500 | 2024-06-07 | [16 empty] | Helix | 4500 | 4500 | 0 | 0 | 0 | 0
DOT | SC25613 | Winfield | Matt Hopkins | SUE Level B | 2025-02-13 | 2025-02-15 | 168777007.M.053 | 2025-02-25 | 2025-02-21 | 2025-03-25 | Y |  |  |  |  | X | 2025-02-17 | 6340 | 2025-02-25 | [16 empty] | Helix | 6340 | 6340 | 0 | 0 | 0 | 0
DOT | SC19290 | Chicago Heights | Matt Hopkins | SUE Level B | 2024-10-16 | 2024-10-21 | 168777007.M.033 | 2024-11-01 | 2024-11-01 | 2025-03-25 | Y |  |  |  |  | X | 2024-10-21 | 14600 | 2024-11-01 | [16 empty] | Helix | 14600 | 14600 | 0 | 0 | 0 | 0
DOT | SC25118 | Westmont | Matt Hopkins | SUE level B | 2024-10-16 | 2024-10-17 | 168777007.M.036 | 2024-10-28 | 2024-10-28 | 2025-03-25 | Y |  |  |  |  | X | 2024-10-17 | 5000 | 2024-10-28 | [16 empty] | Helix | 5000 | 5000 | 0 | 0 | 0 | 0
DOT | N19534 | Sterling | Matt Hopkins | Redline Locates | 2025-04-14 | 2025-04-14 | 168777007.D.999 | 2025-04-17 | 2025-04-17 | 2025-05-01 | Y | [16 empty] | X | N/A | 1728.75 | [5 empty] | SHACTEE | 1728.75 | 0 | 0 | 0 | 0 | 1728.75
DOT | SC25911 | Aurora | Matt Hopkins | Redline Locates | 2025-05-08 | 2025-05-08 | 168777007.D.999 | 2025-05-15 | 2025-05-15 | 2025-05-25 | Y | [16 empty] | X | N/A | 3764.23 | [5 empty] | Shactee | 3764.23 | 0 | 0 | 0 | 0 | 3764.23
DOT | N19411 | Fox River Grove | Matt Hopkins | Redline Locates | 2025-03-24 | 2025-03-24 | 168777007.D.999 | 2025-03-31 | 2025-03-26 | 2025-06-25 | Y | [16 empty] | X | N/A | 1212.55 | [5 empty] | Shactee | 1212.55 | 0 | 0 | 0 | 0 | 1212.55
DOT | M15914 | Oak Park | Matt Hopkins | SUE Level B | 2025-03-25 | 2025-03-26 | 168777007.M.060 | 2025-04-03 | 2025-04-04 | 2025-06-25 | Y | [6 empty] | 6210 | [17 empty] | Helix | 6210 | 6210 | 0 | 0 | 0 | 0
DOT | SC24836 | Park Forest | Matt Hopkins | Redline Locates | 2025-02-14 | 2025-02-14 | 168777007.D.999 | 2025-02-21 | 2025-02-18 | 2025-06-25 | Y | [16 empty] | X | N/A | 1395.75 | [5 empty] | Shactee | 1395.75 | 0 | 0 | 0 | 0 | 1395.75
DOT | SC25578 | Wilmington | Matt Hopkins | Redline Locates | 2025-02-04 | 2025-02-04 | 168777007.D.999 | 2025-02-11 | 2025-02-10 | 2025-06-25 | Y | [16 empty] | X | N/A | 1091.8 | [5 empty] | Shactee | 1091.8 | 0 | 0 | 0 | 0 | 1091.8
DOT | SC25712 | Pontiac | Matt Hopkins | SUE Level B | 2025-03-05 | 2025-03-07 | 168777007.M.055 | 2025-03-14 | 2025-03-14 | 2025-07-25 | Y | [24 empty] | Helix | 3365 | 3365 | 0 | 0 | 0 | 0
DOT | SC25712 | Pontiac | Matt Hopkins | Locates | 2025-03-17 | 2025-03-17 | 168777007.M.055 | 2025-03-24 | 2025-03-24 | 2025-07-25 | Y | [16 empty] | X | N/A | 1789.7 | 2025-04-13 |  |  |  |  | Shactee | 1789.7 | 0 | 0 | 0 | 0 | 1789.7
DOT | M16805 | Glenview | Matt Hopkins | Redline Locates | 2025-07-14 | 2025-07-14 | 168777007.D.999 | 2025-07-22 | 2025-07-21 | 2025-09-01 | N | [16 empty] | x | N/A | 6553.13 | 2025-07-22 |  |  |  |  | Shactee | 6553.13 | 0 | 0 | 0 | 0 | 6553.13
DOT | SC25745 | Ford Heights | Matt Hopkins | Redline Locates | 2025-03-07 | 2025-03-07 | 168777007.D.999 | 2025-03-14 | 2025-03-14 | 2025-10-01 | N | [16 empty] | X | N/A | 2715.4 | [5 empty] | Shactee | 2715.4 | 0 | 0 | 0 | 0 | 2715.4
DOT | M15984 | Berwyn | Matt Hopkins | SUE Level B | 2025-05-12 | 2025-05-14 | 168777007.M.072 | 2025-05-21 | 2025-05-21 | 2025-11-01 | N |  |  |  |  | X | 2025-05-13 | 9760 | 2025-05-21 | [16 empty] | Helix | 9760 | 9760 | 0 | 0 | 0 | 0
DOT | N19953 | Elk Grove Village | Matt Hopkins | SUE LEVEL B | 2025-05-22 | 2025-06-03 | 168777007.M.075 | 2025-06-11 | 2025-06-11 | 2025-10-01 | N |  |  |  |  | x | 2025-06-02 | 11700 | 2025-06-11 | [16 empty] | Helix | 11700 | 11700 | 0 | 0 | 0 | 0
DOT-TR | M16521-T | Bensenville | Matt Hopkins | SUE Level B | 2025-04-15 | 2025-04-17 | 168777007.M.063 | 2025-04-24 | 2025-04-24 | 2026-02-01 | N |  |  |  |  | X | 2025-04-16 | 5200 | 2025-04-24 | [16 empty] | Helix | 5200 | 5200 | 0 | 0 | 0 | 0
DOT | N19585 | Hoffman Estates | Matt Hopkins | Redline Locates | 2025-09-12 | 2025-09-12 | 168777007.D.999 | 2025-09-19 |  | 2025-10-25 | N | [16 empty] | X | N/A | [6 empty] | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | SC21051 | Olympia Fields | Mitchell Pohlman | SUE Level B | 2023-12-22 | 2023-12-27 | 168777007.M.903 | 2023-01-13 | 2024-01-09 | 2024-05-01 | Y |  |  |  |  | X | 2023-12-26 | 10430 | 2023-01-13 | [16 empty] | Helix | 10430 | 10430 | 0 | 0 | 0 | 0
TIMP | TP609 | Franklin Park | Mitchell Pohlman | SUE Level B | 2024-08-07 | 2024-08-15 | 168777008.1.902 | 2024-08-23 | 2024-09-03 | 2024-11-01 | Y |  |  |  |  | X | 2024-08-13 | 2000 | 2024-08-23 | [16 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0
TIMP | TP618 | Northlake | Mitchell Pohlman | SUE Level B | 2024-10-30 | 2024-11-04 | 168777008.1.902 | 2024-11-14 | 2024-11-17 | 2025-02-01 | Y |  |  |  |  | X | 2024-11-01 | 5725 | 2024-11-14 | [16 empty] | Helix | 5725 | 5725 | 0 | 0 | 0 | 0
TIMP | TP640 | Markham | Mitchell Pohlman | SUE Level B | 2025-01-27 | 2025-01-30 | 168777008.1.902 | 2025-02-19 | 2025-02-18 | 2025-04-01 | Y |  |  |  |  | X | 2025-01-29 | 7660 | 2025-02-19 | [16 empty] | Helix | 7660 | 7660 | 0 | 0 | 0 | 0
DOT-TR | N16379-1 | Chicago | Mitchell Pohlman | SUE Level A | 2024-04-01 | 2024-04-02 | 168777007.D.905 | 2024-08-05 | 2024-08-02 | 2025-04-01 | Y | [12 empty] | X | 2024-04-01 | 11000 | 2024-04-26 | [8 empty] | Dawood | 11000 | 0 | 0 | 0 | 11000 | 0
TIMP | TP634 | Hoffman Estates | Mitchell Pohlman | Sue Level B | 2024-12-19 | 2025-12-30 | 168777008.1.902 | 2025-01-07 | 2025-01-07 | 2025-05-01 | Y |  |  |  |  | X | 2025-12-21 | 3250 | 2025-01-07 | [16 empty] | Helix | 3250 | 3250 | 0 | 0 | 0 | 0
DOT-TR | M15898-T | Glenview | Mitchell Pohlman | SUE Level B | 2024-06-07 | 2024-06-11 | 168777007.D.903 | 2024-06-18 | 2024-06-18 | 2025-08-01 | N |  |  |  |  | X | 2024-06-10 | 6250 | 2024-06-15 | [16 empty] | Helix | 6250 | 6250 | 0 | 0 | 0 | 0
DOT | N15708 | Hanover | Randy Castellon | SUE Level B | 2023-07-05 | 2023-07-19 | 168777007.M.902 | 2023-08-01 | 2023-07-25 | 2023-09-01 | Y | X | 2023-07-17 | 4550 | 2023-08-01 | [20 empty] | DLZ | 4550 | 0 | 0 | 4550 | 0 | 0
DOT | SC21396 | New Lenox | Randy Castellon | SUE Level B | 2023-09-01 | 2023-09-07 | 168777007.D.903 | 2023-09-22 | 2023-09-18 | 2023-10-23 | Y |  |  |  |  | X | 2023-09-05 | 6800 | 2023-09-22 | [16 empty] | Helix | 6800 | 6800 | 0 | 0 | 0 | 0
DOT | N15193 | Streamwood | Randy Castellon | Survey, SUE Level B | 2023-11-01 | 2023-11-06 | 168777007.D.902 | 2023-11-15 | 2023-11-15 | 2023-11-01 | Y | X | 2023-11-02 | 12500 | 2023-11-17 | X | 2023-11-02 | 5300 | 2023-11-17 | [16 empty] | DLZ | 12500 | 0 | 0 | 12500 | 0 | 0
DOT | M15635 | Bridgeview | Randy Castellon | SUE Level B | 2024-02-08 | 2023-02-13 | 168777007.D.903 | 2024-02-27 | 2024-02-28 | 2024-07-01 | Y |  |  |  |  | X | 2024-02-12 | 8730 | 2/27/2024 or sooner | [16 empty] | Helix | 8730 | 8730 | 0 | 0 | 0 | 0
DOT | SC24717 | Bloomington | Randy Castellon | SUE Level B | 2024-07-17 | 2024-07-18 | 168777007.M.903 | 2024-07-29 | 2024-07-25 | 2024-09-24 | Y |  |  |  |  | X | 2024-07-18 | 1945 | 2024-07-29 | [16 empty] | Helix | 1945 | 1945 | 0 | 0 | 0 | 0
DOT | SC24572 | W Chicago | Randy Castellon | SUE Level B | 2024-08-15 | 2024-08-16 | 168777007.M.903 | 2024-08-26 | 2024-08-23 | 2024-10-24 | Y |  |  |  |  | X | 2024-08-16 | 2650 | 2024-08-26 | [16 empty] | Helix | 2650 | 2650 | 0 | 0 | 0 | 0
DOT | N18962 | Monroe Center | Randy Castellon | SUE Level B | 2024-09-23 | 2024-09-26 | 168777007.M.903 | 2024-10-03 | 2024-10-03 | 2024-11-01 | Y |  |  |  |  | X | 2024-09-25 | 2450 | 2024-10-03 | [16 empty] | Helix | 2450 | 2450 | 0 | 0 | 0 | 0
DOT | SC24983 | Joliet | Randy Castellon | SUE Level B | 2024-09-23 | 2024-09-26 | 168777007.M.903 | 2024-10-03 | 2024-10-03 | 2024-11-24 | Y |  |  |  |  | X | 2024-09-25 | 3250 | 2024-10-03 | [16 empty] | Helix | 3250 | 3250 | 0 | 0 | 0 | 0
DOT | N17081 | Freeport | Randy Castellon | SUE Level B | 2024-11-13 | 2024-11-18 | 168777007.M.903 | 2024-11-27 | 2024-11-26 | 2025-02-25 | Y |  |  |  |  | X | 2024-11-15 | 6940 | 2024-11-27 | [16 empty] | Helix | 6940 | 6940 | 0 | 0 | 0 | 0
DOT | N17091 | Huntley | Randy Castellon | SUE Level B | 2025-01-16 | 2025-01-20 | 168777007.M.903 | 2025-01-30 | 2025-01-28 | 2025-03-25 | Y |  |  |  |  | X | 2025-01-19 | 6800 | 2025-01-30 | [16 empty] | Helix | 6800 | 6800 | 0 | 0 | 0 | 0
DOT | SC25031 | Rockdale | Randy Castellon | SUE Level B | 2025-01-03 | 2025-01-07 | 168777007.M.903 | 2025-01-15 | 2025-01-15 | 2025-05-25 | Y |  |  |  |  | X | 2025-01-03 | 8300 | 2025-01-01 | [16 empty] | Helix | 8300 | 8300 | 0 | 0 | 0 | 0
DOT | N13882 | Mundelein | Randy Castellon | SUE Level B | 2024-04-29 | 2024-04-30 | 168777007.D.903 | 2024-05-16 | 2024-05-14 | 2025-07-01 | Y |  |  |  |  | X | 2024-04-29 | 20550 | 2024-05-16 | [16 empty] | Helix | 20550 | 20550 | 0 | 0 | 0 | 0
DOT | SC21396 | New Lenox | Randy Castellon | SUE Level B | 2023-09-01 | 2023-09-06 | 168777007.D.105 | 2023-09-07 | 2023-09-18 | 2025-07-01 | Y |  |  |  |  | X | 2023-09-07 | 6800 | 2023-09-21 | [16 empty] | Helix | 6800 | 6800 | 0 | 0 | 0 | 0
DOT | SC21396 | New Lenox | Randy Castellon | Locates | 2024-02-21 | 2024-02-21 | 168777007.D.105 | 2024-02-23 | 2024-02-23 | 2025-07-01 | Y | [16 empty] | X |  | 478.12 | [5 empty] | Shactee | 478.12 | 0 | 0 | 0 | 0 | 478.12
DOT | N16723 | Hawthorn Woods | Randy Castellon | SUE Level B | 2024-06-10 | 2024-06-12 | 168777007.D.069 | 2024-06-19 | 2024-06-20 | 2025-08-01 | N |  |  |  |  | X | 2024-06-20 | 26500 | 6/19/2024 | [16 empty] | Helix | 26500 | 26,500 | 0 | 0 | 0 | 0
DOT | SC23762 | Lockport | Randy Castellon | SUE Level B | 2024-04-12 | 2024-04-15 | 168777007.D.903 | 2024-04-23 | 2024-04-18 | 2025-08-01 | N |  |  |  |  | X | 2024-04-15 | 2300 | 2024-04-23 | [16 empty] | Helix | 2300 | 2300 | 0 | 0 | 0 | 0
DOT | N10173 | Hawthorn Woods | Randy Castellon | SUE Level B | 2024-03-19 | 2024-03-27 | 168777007.D.903 | 2024-04-10 | 2024-04-12 | 2025-08-25 | N |  |  |  |  | X | 2024-03-21 | 25500 | 2024-04-10 | [16 empty] | Helix | 25500 | 25500 | 0 | 0 | 0 | 0
DOT | SC20310 | Sheridan | Randy Castellon | SUE LEVEL B | 2025-05-07 | 2025-05-09 | 168777007.M.903 | 2025-05-16 | 2025-05-20 | 2025-09-01 | N |  |  |  |  | X | 2025-05-08 | 2500 | 2025-05-16 | [16 empty] | HELIX | 2500 | 2500 | 0 | 0 | 0 | 0
DOT | N16723 | Hawthorn Woods | Randy Castellon | UAV | 2025-08-11 | 2025-08-22 | 168777007.E.097 | 2025-09-22 |  | 2025-10-01 | N |  |  |  |  | X | 2025-08-13 | 8800 | [17 empty] | Helix | 8800 | 8800 | 0 | 0 | 0 | 0
DOT | N17925 | Hoffman Estates | Randy Castellon | SUE Level B | 2025-06-09 | TBD | 168777007.D.903 | 2025-06-18 | 2025-06-18 | 2025-10-01 | N |  |  |  |  | X | 2025-06-09 | 1300 | 2025-06-18 | [16 empty] | Helix | 1300 | 1300 | 0 | 0 | 0 | 0
DOT | N14920 | Huntley | Randy Castellon | SUE LEVEL B | 2025-07-01 | 2025-07-03 | 168777007.D.903 | 2025-07-14 | 2025-07-14 | 2025-11-01 | N |  |  |  |  | X | 2025-07-02 | 7300 | 2025-07-14 | [16 empty] | Helix | 7300 | 7300 | 0 | 0 | 0 | 0
DOT | M12980 | LaGrange Park | Randy Castellon | SUE Level B | 2024-04-29 | 2024-05-02 | 168777007.D.903 | 2024-05-16 | 2024-05-16 | 2025-12-01 | N |  |  |  |  | X | 2024-05-01 | 27900 | 2024-05-16 | [16 empty] | Helix | 27900 | 27900 | 0 | 0 | 0 | 0
DOT | N20224 | Elgin | Randy Castellon | SUE Level B | 2025-08-19 | TBD | 168777007.M.903 | 2025-09-08 |  | 2025-11-01 | N |  |  |  |  | X |  | 7000 | [17 empty] | Helix | 7000 | 7000 | 0 | 0 | 0 | 0
DOT | N17815 | Round Lake Beach | Taylor Lierow | SUE Level B | 2023-09-07 | 2023-09-13 | 168777007.D.903 | 2023-09-27 | 2023-09-27 | 2023-10-01 | Y |  |  |  |  | X | 2023-09-11 | 17900 | 2023-09-27 | [16 empty] | Helix | 17900 | 17900 | 0 | 0 | 0 | 0
DOT | SC23070 | Aurora | Taylor Lierow | SUE Level B | 2023-11-14 | 2023-11-20 | 168777007.D.903 | 2023-12-08 | 2023-12-05 | 2023-12-01 | Y | X | Declined | - | - | X | 2023-11-16 | 5400 | 2023-12-08 | X | No Response | - | - | [12 empty] | Helix | 5400 | 5400 | 0 | 0 | 0 | 0
DOT | SC23323 | Naperville | Taylor Lierow | Service Locates | 2023-12-20 | 2023-12-20 | 168777007.E.030 | 2023-12-27 | 2023-12-22 | 2024-01-01 | Y | [18 empty] | 696.98 | [5 empty] | Shactee | 696.98 | 0 | 0 | 0 | 0 | 696.98
DOT | N18054 | Hoffman Estates | Taylor Lierow | SUE Level B | 2024-02-06 | 2024-02-09 | 168777007.D.903 | 2024-03-05 | 2024-03-05 | 2024-03-01 | Y |  |  |  |  | X | 2024-02-08 | 36250 | 2024-03-05 | [16 empty] | Helix | 36250 | 36250 | 0 | 0 | 0 | 0
DOT | N16542 | Hoffman Estates | Taylor Lierow | SUE Level B | 2024-01-05 | 2024-01-08 | 168777007.D.903 | 2024-01-19 | 2024-01-19 | 2024-04-01 | Y |  |  |  |  | X | 2024-01-18 | 5900 | 2024-01-19 | [16 empty] | Helix | 5900 | 5900 | 0 | 0 | 0 | 0
DOT | SC21051 | Olympia Fields | Taylor Lierow | Electronic Locates | 2024-01-24 | 2024-01-24 | 168777007.M.007 | 2024-01-31 | 2024-01-29 | 2024-05-01 | Y |  |  |  |  | - | - | - | - | [8 empty] | 2024-01-24 | 2024-01-24 | 1753 | 2024-01-21 |  |  |  |  | Shactee | 1753 | 0 | 0 | 0 | 0 | 1753
DOT | N18693 | Geneseo | Taylor Lierow | SUE Level B | 2024-05-23 | 2024-05-23 | 168777007.M.903 | 2024-06-04 | 2024-06-04 | 2024-08-01 | Y |  |  |  |  | X | 2024-05-23 | 7600 | 2024-06-04 | [16 empty] | Helix | 7600 | 7600 | 0 | 0 | 0 | 0
DOT | SC19888 | St. Charles | Taylor Lierow | Sue Level B | 2024-04-11 | 2024-04-12 | 168777007.D.903 | 2024-04-22 | 2024-04-22 | 2024-08-24 | Y |  |  |  |  | X | 2024-04-11 | 9400 | 2024-04-22 | [16 empty] | Helix | 9400 | 9400 | 0 | 0 | 0 | 0
DOT | SC24032 | Joliet | Taylor Lierow | Sue Level B | 2024-09-03 | 2024-09-04 | 168777007.M.903 | 2024-09-20 | 2024-09-20 | 2024-11-24 | Y |  |  |  |  | X | 2024-09-04 | 10920 | 2024-09-20 | [16 empty] | Helix | 10920 | 10920 | 0 | 0 | 0 | 0
DOT | N12987 | Schaumburg | Taylor Lierow | SUE Level B | 2024-02-12 | 2024-02-15 | 168777007.D.903 | 2024-02-26 | 2024-02-26 | 2025-03-25 | Y |  |  |  |  | X | 2024-02-14 | 5400 | 2024-02-26 | [16 empty] | Helix | 5400 | 5400 | 0 | 0 | 0 | 0
DOT | SC25832 | Bradley | Taylor Lierow | SUE Level B | 2025-04-04 | 2025-04-08 | 168777007.M.903 | 2025-04-15 | 2025-04-15 | 2025-07-25 | Y |  |  |  |  | X | 2025-04-07 | 11405 | 2025-04-15 | [16 empty] | Helix | 11405 | 11405 | 0 | 0 | 0 | 0
DOT | N18492 | Long Grove | Taylor Lierow | SUE Level B | 2024-12-18 | 2034-12-30 | 168777007.M.903 | 2025-01-14 | 2025-01-14 | 2025-07-25 | Y |  |  |  |  | X | 2024-12-20 | 16300 | 2025-01-14 | [16 empty] | Helix | 16300 | 16300 | 0 | 0 | 0 | 0
DOT | SC18317 | Troy Twp | Taylor Lierow | Sue Level B | 2024-04-10 | 2024-04-11 | 168777007.D.903 | 2024-04-19 | 2024-04-18 | 2025-09-01 | N |  |  |  |  | X | 2024-04-10 | 6900 | 2024-04-19 | [16 empty] | Helix | 6900 | 6900 | 0 | 0 | 0 | 0
DOT | N19731 | Machesney Park | Taylor Lierow | Sue Level B | 2025-07-29 | 2025-08-04 | 168777007.M.903 | 2025-08-06 |  | 2025-09-25 | N |  |  |  |  | X | 2025-07-30 | 2695 | 2025-08-06 | [16 empty] | Helix | 2695 | 2695 | 0 | 0 | 0 | 0
DOT-TR | M15242-T | Berwyn | Taylor Lierow | SUE Level B | 2025-02-13 | 2024-02-17 | 168777007.M.903 | 2025-02-24 | 2025-02-24 | 2025-10-25 | N |  |  |  |  | X | 2025-02-17 | 4750 | 2025-02-24 | [16 empty] | Helix | 4750 | 4750 | 0 | 0 | 0 | 0
DOT | N18185 | Elgin | Taylor Lierow | Sue Level B | 2025-05-20 | 5/22/025 | 168777007.M.903 | 2025-05-30 | 2025-05-30 | 2025-11-01 | N |  |  |  |  | X | 2025-05-21 | 11300 | 2025-05-30 | [16 empty] | Helix | 11300 | 11300 | 0 | 0 | 0 | 0
DOT | SC25777 | Westmont | Taylor Lierow | SUE LEVEL B | 2025-04-25 | 2025-04-28 | 168777007.M.903 | 2025-05-13 | 2025-05-12 | 2025-11-25 | N |  |  |  |  | X | 2025-04-28 | 9850 | 2025-05-13 | [16 empty] | Helix | 9850 | 9850 | 0 | 0 | 0 | 0
DOT | SC25777 | Westmont | Taylor Lierow | Survey, SUE Level B | 2025-06-09 | 2025-06-17 | 168777007.M.903 | 2025-07-07 | 2025-07-09 | 2025-11-25 | N | X | 2025-06-11 | 29650 | 2025-07-07 | X | 2025-06-11 | 21740 | 2025-07-07 | [16 empty] | DLZ | 29650 | 0 | 0 | 29650 | 0 | 0
DOT | N14298 | Sterling | Taylor Lierow/Caroline Kulach | SUE Level B | 2024-10-18 | 2024-10-23 | 168777007.M.038 | 2024-11-13 | 2024-11-11 | 2025-02-25 | Y |  |  |  |  | X | 2024-10-21 | 6685 | 2024-11-13 | [16 empty] | Helix | 6685 | 6685 | 0 | 0 | 0 | 0
DOT | N17019 | Mt Prospect | Taylor Lierow/Ethan Ekstrom | SUE Level B | 2024-10-09 | 2024-10-10 | 168777007.M.034 | 2024-10-23 | 2024-10-17 | 2025-12-25 | N |  |  |  |  | X | 2024-10-10 | 11700 | 2024-10-23 | [16 empty] | Helix | 11700 | 11700 | 0 | 0 | 0 | 0
DOT | N18185 | Elgin | Taylor Lierow/Michael Molloy | Service Locates | 2025-09-05 | 2025-09-05 | 168777007.M.074 | 2025-09-12 | 2025-09-12 | 2026-03-01 | N | [16 empty] | X | 2025-09-05 |  | 2025-09-12 |  |  |  |  | Shactee | 0 | 0 | 0 | 0 | 0 | 0
DOT | SC23548 | Naperville | Tim Purtell | Locates | 2024-01-04 | 2024-01-04 | 168777007.D.135 | 2024-01-11 | 2024-01-09 | 2024-01-01 | Y |  |  |  |  | - | - | - | - | [8 empty] | X | 2024-01-04 | 1561.5 | 2024-01-11 |  |  |  |  | Shactee | 1561.5 | 0 | 0 | 0 | 0 | 1561.5
DOT | N18296 | Prospect Heights | Tim Purtell | SUE Level B | 2024-01-17 | 2024-01-22 | 168777007.M.008 | 2024-01-31 | 2024-01-31 | 2024-03-01 | Y |  |  |  |  | x | 2024-01-18 | 11870 | 2024-01-31 | [16 empty] | Helix | 11870 | 11870 | 0 | 0 | 0 | 0
DOT | N13601 | Rockford | Tim Purtell | SUE Level B | 2024-01-05 | 2024-01-08 | 168777007.D.903 | 2024-01-19 | 2024-01-18 | 2024-03-01 | Y |  |  |  |  | X | 2024-01-08 | 9990 | 2024-01-19 | [16 empty] | Helix | 9990 | 9990 | 0 | 0 | 0 | 0
DOT | SC23448 | Peotone | Tim Purtell | SUE Level B | 2024-03-05 | 2024-03-06 | 168777007.D.903 | 2024-03-22 | 2024-03-18 | 2024-06-01 | Y |  |  |  |  | X | 2024-03-05 | 4100 | 2024-03-22 | [16 empty] | Helix | 4100 | 4100 | 0 | 0 | 0 | 0
DOT | N18337 | Schaumburg | Tim Purtell | SUE Level B | 2024-02-05 | 2024-02-07 | 168777007.D.903 | 2024-02-21 | 2024-02-21 | 2024-10-01 | Y |  |  |  |  | X | 2024-02-06 | 4615 | 2024-02-21 | [16 empty] | Helix | 4615 | 4615 | 0 | 0 | 0 | 0
DOT | SC23749 | Manteno | Tim Purtell/Matt Hopkins | SUE Level B | 2024-03-19 | 2024-03-19 | 168777007.D.147 | 2024-04-04 | 2024-04-03 | 2024-06-01 | Y |  |  |  |  | X | 2024-03-19 | 5525 | 2024-04-04 | [16 empty] | Helix | 5525 | 5525 | 0 | 0 | 0 | 0
Non-DOT | MR2277 | Lansing | Tom McTigue | Service Locates | 1141519 | 2025-05-15 | 168777007.J.015 | 2025-05-22 | 2025-05-20 | 2025-07-25 | Y | [16 empty] | X | N/A | [6 empty] | Shactee | 1068.63 | 0 | 0 | 0 | 0 | 1068.63
Non-DOT | PRIM719 | Rochelle | Tom McTigue | Locates | 2025-06-30 | 2025-07-02 | 168777007.J.601 | 2025-07-11 | 2025-07-10 | 2025-08-25 | N |  |  |  |  | X | 2025-07-01 | 6500 | 2025-07-11 | [16 empty] | Helix | 6500 | 6500 | 0 | 0 | 0 | 0
CRA | RS1312 | Ottawa | Tom McTigue | Locates | 2025-06-18 | 2025-06-18 | 168777007.G.808 | 2025-06-25 | 2025-06-23 | 2025-09-25 | N | [16 empty] | X | N/A |  | 2025-06-25 |  |  |  |  | Shactee | 3527.15 | 0 | 0 | 0 | 0 | 3527.15
CRA | RS1308 | Kingston | Tom McTigue | Locates | 2025-08-21 | 2025-08-28 | 168777007.G.620 | 2025-09-05 |  | 2025-11-25 | N |  |  |  |  | X | 2025-08-21 | 2000 | 2025-09-05 | [16 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0
TIMP | TP684 | Glendale Heights | Mark Stanley | SUE Level B | 2025-09-12 |  | 168777008.1.042 | 2025-10-01 | [7 empty] | X | 2025-09-15 | 1500 | 2025-10-01 | [16 empty] | Helix | 1500 | 1500 | 0 | 0 | 0 | 0
TIMP | TP685 | Glendale Heights | Mark Stanley | SUE Level B | 2025-09-12 |  | 168777008.1.043 | 2025-10-01 | [7 empty] | X | 2025-09-15 | 1750 | 2025-10-01 | [16 empty] | Helix | 1750 | 1750 | 0 | 0 | 0 | 0
DOT | SC26438 | Bloomington | Caroline Kulach | SUE Level B | TBD | TBD | 168777007.M.083 | TBD | TBD | [27 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0
TIMP | TP694 | Lisle | Mark Stanley | SUE Level B | 2025-09-12 |  | 168777008.1.044 | 2025-10-01 | [7 empty] | X | 2025-09-15 | 1500 | 2025-10-01 | [16 empty] | Helix | 1500 | 1500 | 0 | 0 | 0 | 0
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lierow, Taylor @Corbi, Camille @Hopkins, Matt @Chamernik, Conner @Ekstrom, Ethan @Kulach, Caroline can we note these as “Redline Locates” when they are just for redlines?
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to "TBD" when ready to bill. Not billing until project is released.
Note on AL6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Betland, Joseph This appears to have been reported in Sept 2024. These values can be added but will no longer be needed for forecasting.
Note on AL7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille do we have an approximate value for these two redline locates projects? Reply: Joey - This appears to have been reported in Sept 2024. These values can be added but will no longer be needed for forecasting.
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille please update these rows
Note on K19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulling ahead
Note on K20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulling ahead
Note on AL26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kulach, Caroline we got invoiced for $7670, is that accurate? Reply: Yes, that is what the IPO stated. Reply: ok please fill it in so that we can reference it here
Note on K61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy FYI this will be reported with your project release
Note on AL62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Chamernik, Conner do we have a value for this yet? Reply: These just got delivered this morning with no cost attached with them. Should only be a few hundred dollars.
Note on AL74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ekstrom, Ethan please update Reply: Done
Note on E76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ekstrom, Ethan how much were these locates? @Lierow, Taylor @Bruce, Logan we’ll likely want to get these on the upcoming invoice Reply: @Betland, Joseph @Lierow, Taylor we may want to hop on a quick call to discuss how to invoice for these. Reply: updated - $4,064.81
Note on H80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rojas, Taylor can I get a hand updating these red cells? Reply: Done!
Note on AK80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Roman, Madeline please update red cells
Note on L86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: not sure which invoice this is releated to. We had Nicor Initiated in October 2024 from Helix then Shactee in January of 2025
Note on AL108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt please update
Note on AL109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt please update
Note on L111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Betland, Joseph Colored this cell yellow in case we didnt report the 2nd half of the shactee invoice
Note on AL111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt please update based on invoiced amount Reply: updated.
Note on AL119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hopkins, Matt do we have a value for these locates? Reply: added
Note on T134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy please update
Note on K142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulled this ahead from 2026 to report
Note on K145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulling ahead to report. Reply: Assuming to leave as billing to be in august with this note
Note on K148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pulling ahead to report. Reply: Joey - I think this project wont realistically be released till next year, maybe january. Want me to leave this as this date? Unsure what you mean with pulling ahead to report Reply: leave date as is - i'm puling those values ahead to report this year. I sent a note about it last week
Note on K166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reporting ahead
Note on L166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan can you verify that this wasn’t reported next year? Reply: likely not. 2024 tracking has May 2025 tagged.
Note on AE174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending invoice
Note on R182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas Update this to the date you received the bid
Note on R184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas Update this to the date you received their bid

## Nicor Initiated
[23 empty] | Atlas (AEGroup) |  |  |  | DLZ |  |  |  | Helix |  |  |  | Millennia |  |  |  | Dawood |  |  |  | Accurate |  |  |  | LWS
# | Project Type | Engineering Number | WO | Town | Project Lead | Scope | RFP Issuance | RFP Due | Planned NTP | Expected Completion | Issued for KH Approval | KH Approval Received | to Nicor for Approval | Nicor Approval | Actual NTP | Co-Signed IPO Returned | Sub Task Number | Current Expected Compl | Deliverables Received | Billed/ Reported to Nicor? | KH Cost? | Anticipated Billing Month | Issued to AEG | Proposal Received AEG | Cost AEG | Schedule AEG | Issued to DLZ | Proposal Received DLZ | Cost DLZ | Schedule DLZ | Issued to Helix | Proposal Received Helix | Cost Helix | Schedule Helix | Issued to Millennia | Proposal Received Millennia | Cost Millennia | Schedule Millennia | Issued to Dawood | Proposal Received Dawood | Cost Dawood | Schedule Dawood | Issued To Accurate | Proposal Received Accurate | Cost Accurate | Schedule Accurate | Issued To LWS | Proposal Received LWS | Cost LWS | Schedule LWS | Contractor Selected | Amount | Helix Total | Millennia Total | DLZ Total | Atlas Total | Dawood Total | Accurate Total | LWS TOTAL
1 | Non-DOT | VW142 | 120595 | Calumet Park | Nick Michaels | Survey, SUE Level B | 2021-04-06 | 2021-04-08 | 2021-04-12 | 2021-05-10 | - | - | - | - | 2021-04-20 | X | 168777000.1.836 | 2021-05-11 | 2021-05-11 | 2021-05-11 | N | 2023-01-01 | X | 2021-04-09 | Unknown | [25 empty] | Atlas | Unknown | 0 | 0 | 0 | Unknown | 0 | 0 | 0
2 | Non-DOT | VW222 | 120571 | N Riverside | Josh Meyer | Survey, SUE Level B | 2021-05-05 | 2021-05-07 | 2021-05-11 | 2021-05-25 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-13 | 2021-05-13 | X | 168777000.1.845 | 2021-05-28 | 2021-05-28 | 2021-05-28 |  | 2023-01-01 | [12 empty] | X | 2021-05-07 | 22044 | 2021-05-28 | [12 empty] | Millennia | 22044 | 0 | 22044 | 0 | 0 | 0 | 0 | 0
3 | CRA | RS846 | 102154 | Lee Center | Billy Pacheco |  | 2021-05-06 | 2021-05-10 | 2021-05-17 | 2021-06-07 | 2021-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-17 | 2021-05-18 |  |  | 2021-06-08 | 2021-06-07 | 2021-06-07 |  | 2023-01-01 | [8 empty] | X | 2021-05-11 | 6750 | 2021-06-08 | X | 2021-05-12 | 8920 | 2021-06-08 | [12 empty] | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRA | RS852 | 101205 | Compton | Billy Pacheco |  | 2021-05-06 | 2021-05-10 | 2021-05-17 | 2021-06-07 | 2021-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-17 | 2021-05-18 |  |  | 2021-06-08 | 2021-06-07 | 2021-06-07 |  | 2023-01-01 | [8 empty] | X | 2021-05-11 | 6750 | 2021-06-08 | X | 2021-05-12 | 8610 | 2021-06-08 | [12 empty] | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
5 | CRA | RS857 | 101206 | W. Brooklyn | Billy Pacheco |  | 2021-05-06 | 2021-05-10 | 2021-05-17 | 2021-06-07 | 2021-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-17 | 2021-05-18 |  |  | 2021-06-08 | 2021-06-07 | 2021-06-07 |  | 2023-01-01 | [8 empty] | X | 2021-05-11 | 6750 | 2021-06-08 | X | 2021-05-12 | 8830 | 2021-06-08 | [12 empty] | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
6 | CRA | RS886 | 102155 | Wheeling | Matt Crescenti |  | 2021-05-07 | 2021-05-11 | 2021-05-18 | 2021-06-08 | - | - | - | 2021-05-17 | 2021-05-18 | X |  | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | 2023-01-01 | X | 2021-05-11 | 9680 | 2021-06-08 | [8 empty] | X | 2021-05-12 | 29430 | 2021-06-11 | [12 empty] | Atlas | 9680 | 0 | 0 | 0 | 9680 | 0 | 0 | 0
8 | DOT | SC9720 | 140780 | Joliet | Josh Meyer | Survey, SUE Level B | 2021-05-13 | 2021-05-17 | 2021-05-19 | - | 2021-05-19 | 2021-05-19 |  |  | 2021-05-21 | X | 168777000.1.949 | 2021-06-16 | 2021-06-11 | 2021-06-11 | N | 2023-01-01 | X | 2021-05-17 | 18850 | 2021-06-11 | X |  | 43500 | 2021-06-16 | X | 2021-05-17 | 17850 | 2021-06-01 | X | 2021-05-18 | 38120 | 2021-06-25 | [12 empty] | DLZ | 43500 | 0 | 0 | 43500 | 0 | 0 | 0 | 0
7 | DOT | SC17932 | 135740 | Winfield | Mike Diorio | Survey, SUE Level B | 2021-05-10 | 2021-05-13 | 2021-05-19 | 2021-06-18 | 2021-05-17 | - | 2021-05-17 | - | 2021-05-24 | X | 168777000.1.961 | 2021-06-18 | 2021-06-18 | 2021-06-18 | N | 2023-01-01 | [12 empty] | X | 2021-05-14 | 21550 | 2021-06-18 | [12 empty] | Millennia | 21550 | 0 | 21550 | 0 | 0 | 0 | 0 | 0
9 | CRA | RS869 | 1010219 | Grant Park | Billy Pacheco |  | 2021-06-07 | 2021-06-09 | 2021-06-16 | 2021-07-07 | 2021-06-14 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-16 | X |  | 2021-07-07 | 2021-07-12 | 2021-07-12 |  | 2023-01-01 | [8 empty] | X | 2021-06-08 | 7000 | 2021-07-07 | X | 2021-06-09 | 10500 | 2021-07-07 | [12 empty] | Helix | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0
10 | CRA | RS871 | 1010232 | Kempton | Billy Pacheco |  | 2021-06-07 | 2021-06-09 | 2021-06-16 | 2021-07-07 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-06-16 | X |  | 2021-07-07 | 2021-07-12 | 2021-07-12 |  | 2023-01-01 | [8 empty] | X | 2021-06-07 | 6750 | 2021-07-07 | X | 2021-06-09 | 8750 | 2021-07-07 | [12 empty] | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
11 | CRA | RS880 | 1010234 | Cabery | Billy Pacheco |  | 2021-06-07 | 2021-06-09 | 2021-06-16 | 2021-07-07 | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-06-16 | X |  | 2021-07-07 | 2021-07-12 | 2021-07-12 |  | 2023-01-01 | [8 empty] | X | 2021-06-08 | 6750 | 2021-07-07 | X | 2021-06-09 | 8991 | 2021-07-07 | [12 empty] | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
12 | DOT | SC17896 | 1410323 | Bloomington | Mike Diorio | SUE Level A | 2021-06-14 | 2021-06-16 | 2021-06-23 | 2021-07-15 | 2021-06-16 | 2021-06-17 | 2021-06-17 | 2021-06-22 | 2021-06-22 |  | 168777000.1.953 | 2021-07-15 | 2021-07-20 | 2021-07-20 | N | 2023-01-01 |  |  |  |  | X |  | 6250 | 2021-07-15 | [20 empty] | DLZ | 6250 | 0 | 0 | 6250 | 0 | 0 | 0 | 0
13 | Non-DOT | VW71 | 1210371 | Glenview | Lucy Crofton | Survey, SUE Level B | 2021-06-29 | 2021-06-29 | 2021-07-02 | 2021-07-16 | 2021-06-24 | 2021-06-25 | 2021-07-01 | 2021-07-02 | 2021-07-02 | X | 168777000.1.855 | 2021-07-19 | 2021-08-04 | 2021-08-04 |  | 2023-01-01 | [8 empty] | X | 2021-06-29 | 28750 | 2021-07-16 | X | 2021-06-25 | 48600 | 2021-07-21 | [12 empty] | Helix | 28750 | 28750 | 0 | 0 | 0 | 0 | 0 | 0
15 | Non-DOT | MR1756 | 1310429 | Wayne | Joey Betland | Survey, SUE Level B, Geotechnical | 2021-07-19 | 2021-07-20 | 2021-07-23 | 2021-08-13 | 2021-07-22 | 2021-07-22 | 2021-07-23 | 2021-07-26 | 2021-07-26 | X | 168777000.1.859 | 2021-08-06 | 2021-08-06 | 2021-08-06 |  | 2023-01-01 |  |  |  |  | X | 2021-07-22 | 29350 | [5 empty] | X |  |  | 2021-08-06 | [12 empty] | DLZ | 29350 | 0 | 0 | 29350 | 0 | 0 | 0 | 0
14 | Non-DOT | BS550-1 | 1210760 | Elgin | Billy Pacheco | Survey, SUE Level B, Geotechnical | 2021-07-06 | - | - | - | - | - | - | - | 2021-07-13 | - | 168777000.1.860 | 2021-08-09 | 2021-08-09 | 2021-08-09 |  | 2023-01-01 | [12 empty] | X | 2021-07-02 | 45170 | 2021-08-09 | [12 empty] | Millennia | 45170 | 0 | 45170 | 0 | 0 | 0 | 0 | 0
21 | DOT | N14676 | 1210511 | Wauconda | Mike Diorio | SUE Level A | 2021-08-11 | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-08-13 | 2021-08-13 | 2021-08-16 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 168777000.1.966 | 2021-08-27 | 2021-08-26 | 2021-08-26 | N | 2023-01-01 |  |  |  |  | X | 2021-08-12 | 11560 | TBD | [20 empty] | DLZ | 11560 | 0 | 0 | 11560 | 0 | 0 | 0 | 0
18 | CRA | RS856 | 1010410 | Verona | Billy Pacheco |  | 2021-07-22 | 2021-07-26 | 2021-08-02 | 2021-08-23 | 2021-07-27 | 2021-07-27 | 2021-07-29 | 2021-08-11 | 2021-08-12 | X |  | 2021-09-01 | 2021-08-31 | 2021-08-31 |  | 2023-01-01 | [8 empty] | X | 2021-07-27 | 8000 | 2021-08-23 | X | 2021-07-27 | 8950 | 2021-08-23 | [12 empty] | Millennia | 8950 | 0 | 8950 | 0 | 0 | 0 | 0 | 0
17 | CRA | RS854 | 1010408 | Kinsman | Billy Pacheco |  | 2021-07-22 | 2021-07-26 | 2021-08-02 | 2021-08-23 | 2021-07-27 | 2021-07-27 | 2021-07-29 | 2021-08-11 | 2021-08-12 | X |  | 2021-09-01 | 2021-09-01 | 2021-09-01 |  | 2023-01-01 | [8 empty] | X | 2021-07-27 | 12500 | 2021-08-23 | X | 2021-07-27 | 8765 | 2021-08-23 | [12 empty] | Millennia | 8765 | 0 | 8765 | 0 | 0 | 0 | 0 | 0
16 | CRA | RS850 | 1010405 | Plano | Billy Pacheco |  | 2021-07-22 | 2021-07-26 | 2021-08-02 | 2021-08-23 | 2021-07-27 | 2021-07-27 | 2021-07-29 | 2021-08-11 | 2021-08-12 | X |  | 2021-09-01 | 2021-09-03 | 2021-09-03 |  | 2023-01-01 | [8 empty] | X | 2021-07-27 | 8000 | 2021-08-23 | X | 2021-07-27 | 9525 | 2021-08-23 | [12 empty] | Millennia | 9525 | 0 | 9525 | 0 | 0 | 0 | 0 | 0
20 | Non-DOT | NBA1999345 | 168700 | Cherry Valley | Mike Diorio | Survey, SUE Level B, Geotechnical | 2021-08-06 | 2021-08-10 | 2021-08-16 | 2021-09-13 | 2021-08-11 | 2021-08-11 | 2021-08-12 | 2021-08-16 | 2021-08-17 | X | 168777000.1.867 | 2021-09-13 | 2021-09-13 | 2021-09-13 |  | 2023-01-01 |  |  |  |  | X | 2021-08-10 | 17999 | 2021-09-13 | X | 2021-08-09 | 9000 | 2021-09-13 | X | [15 empty] | Helix | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
22 | CRA | RS864 | 1010502 | Garfield | Billy Pacheco |  | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-09-13 | 2021-08-19 | 2021-08-19 | 2021-08-23 | 2021-09-02 | 2021-09-03 | X |  | 2021-09-13 | 2021-09-15 | 2021-09-15 |  | 2023-01-01 | [8 empty] | X | 2021-08-16 | 6300 | 2021-09-13 | X | 2021-08-17 | 7885 | 2021-09-16 | [12 empty] | Helix | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0
23 | CRA | RS887 | 1010503 | New Bedford | Billy Pacheco |  | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-09-13 | 2021-08-19 | 2021-08-19 | 2021-08-24 | 2021-08-30 | 2021-08-30 | X |  | 2021-09-13 | 2021-09-15 | 2021-09-15 |  | 2023-01-01 | [8 empty] | X | 2021-08-16 | 6300 | 2021-09-13 | X | 2021-08-17 | 8435 | 2021-09-16 | [12 empty] | Helix | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0
24 | CRA | RS888 | 1010504 | Normandy | Billy Pacheco |  | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-09-13 | 2021-08-19 | 2021-08-19 | 2021-08-24 | 2021-08-30 | 2021-08-30 | X |  | 2021-09-13 | 2021-09-15 | 2021-09-15 |  | 2023-01-01 | [8 empty] | X | 2021-08-16 | 6300 | 2021-09-13 | X | 2021-08-17 | 8845 | 2021-09-16 | [12 empty] | Helix | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0
19 | Non-DOT | BS363 | 1210489 | Harvard | Josh Meyer | Survey, SUE Level B | 2021-08-05 | 2021-08-09 | 2021-08-13 | 2021-09-03 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-12 | 2021-08-12 | X | 168777000.1.862 | 2021-09-10 | 2021-09-17 | 2021-09-17 |  | 2023-01-01 |  |  |  |  | X | Declined | - | - |  |  |  |  | X | 2021-08-09 | 93478 | 2021-09-10 | [12 empty] | Millennia | 93478 | 0 | 93478 | 0 | 0 | 0 | 0 | 0
25 | CRA | RS890 | 1010505 | Dewey | Billy Pacheco |  | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-09-13 | 2021-08-19 | 2021-08-19 | 2021-08-24 | 2021-08-30 | 2021-08-30 | X |  | 2021-09-13 | 2021-09-17 | 2021-09-17 |  | 2023-01-01 | [8 empty] | X | 2021-08-16 | 6300 | 2021-09-13 | X | 2021-08-17 | 9125 | 2021-09-16 | [12 empty] | Helix | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0
26 | CRA | RS898 | 1010506 | Paxton | Billy Pacheco |  | 2021-08-12 | 2021-08-16 | 2021-08-23 | 2021-09-13 | 2021-08-19 | 2021-08-19 | 2021-08-24 | 2021-08-30 | 2021-08-30 | X |  | 2021-09-13 | 2021-09-17 | 2021-09-17 |  | 2023-01-01 | [8 empty] | X | 2021-08-16 | 6300 | 2021-09-13 | X | 2021-08-17 | 8925 | 2021-09-16 | [12 empty] | Helix | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0
27 | Non-DOT | NBA1970737 | 1910574 | Minonk | Billy Pacheco | Survey, SUE Level B | 2021-08-23 | 2021-08-25 | 2021-08-30 | 2021-09-10 | 2021-08-25 | 2021-08-26 | 2021-08-30 | 2021-09-07 | 2021-09-07 | X | 168777000.1.874 | 2021-09-17 | 2021-09-22 | 2021-09-22 |  | 2023-01-01 | [8 empty] | X | 2021-08-24 | 8250 | 2021-09-10 | [16 empty] | Helix | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0
28 | CRA | RS500 | 102083 | Deer Park | Josh Meyer | Survey, SUE Level B | 2021-08-25 | 2021-08-27 | 2021-09-02 | 2021-10-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-03 | 2021-09-07 | X | 168777000.1.968 | 2021-10-06 | 2021-10-12 | 2021-10-12 |  | 2023-01-01 |  |  |  |  | X |  |  |  | X | 2021-08-30 | 31750 | 2021-10-06 | X | [15 empty] | Helix | 31750 | 31750 | 0 | 0 | 0 | 0 | 0 | 0
29 | CRA | MR1790 | 3210573 | Arlington Heights | Mitch Pohlman | Survey | 2021-09-03 | 2021-09-08 | 2021-09-15 | 2021-10-06 | 2021-10-04 | 10/4/2021 | 2021-10-04 | 2021-10-07 | 2021-10-07 | X | 168777000.1.976 | 2021-10-15 | 2021-10-16 | 2021-10-16 |  | 2023-01-01 |  |  |  |  | - | 2021-09-09 | 41750 | 2021-09-29 |  |  |  |  | X | 2021-10-01 | 2725 | 2021-10-15 | [12 empty] | Millennia | 2725 | 0 | 2725 | 0 | 0 | 0 | 0 | 0
30 | Non-DOT | BS194D-1 | 1210460 | Chicago Heights | Josh Meyer | Survey, SUE Level B, Geotechnical | 2021-09-09 | 2021-09-13 | - | 2021-10-29 | 2021-10-01 | 2021-10-04 | 2021-10-04 | 2021-10-08 | 2021-10-08 | X | 168777000.1.877 | 2021-10-29 | 2021-10-19 | 2021-10-19 |  | 2023-01-01 |  |  |  |  | X | 2021-10-19 | 51200 | 2021-10-29 | [20 empty] | DLZ | 51200 | 0 | 0 | 51200 | 0 | 0 | 0 | 0
34 | Non-DOT | BS255 | 1410708 | Morris | Nick Michaels | Survey, SUE Level B, Geotechnical | 2021-10-13 | 2021-10-15 | 2021-10-22 | 2021-11-17 | 2021-10-21 | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-25 | X | 168777000.1.880 | 2021-11-17 | 2021-11-17 | 2021-11-01 | N/A | 2023-01-01 | X | 2021-10-18 | 27875 | 2021-11-17 | X | 2021-10-20 | 52500 | 2021-12-07 | X | 2021-10-18 | 32125 | 2021-11-17 | X | 2021-10-18 | 59889 | 2021-11-17 | [12 empty] | Millennia | 59889 | 0 | 59889 | 0 | 0 | 0 | 0 | 0
32 | Non-DOT | VW213 | 1210692 | Lansing | Nick Michaels | Survey, SUE Level B | 2021-10-12 | 2021-10-14 | 2021-10-19 | 2021-11-02 | 2021-10-14 | 2021-10-18 | 2021-10-19 | 2021-10-22 | 2021-10-22 | X | 168777000.1.879 | 2021-11-19 | 2021-11-12 | 2021-11-01 | N/A | 2023-01-01 |  |  |  |  | X | 2021-10-14 | 36500 | 2021-11-15 | [20 empty] | DLZ | 36500 | 0 | 0 | 36500 | 0 | 0 | 0 | 0
38 | CRA | RS927 | 1010728 | Morton Grove | Billy Pacheco |  | 2021-10-21 | 2021-10-25 | 2021-10-29 | 2021-11-19 | 2021-10-26 | 2021-10-27 | 2021-10-27 | 2021-11-01 | 2021-11-01 | X |  | 2021-11-19 | 2021-11-19 | 2021-11-19 |  | 2023-01-01 | [8 empty] | X | 2021-10-25 | 17150 | 2021-11-19 | X | Declined | [14 empty] | Helix | 17150 | 17150 | 0 | 0 | 0 | 0 | 0 | 0
37 | CRA | RS923 | 1010732 | Naperville | Marissa LaPorte | Survey, SUE Level B | 2021-10-21 | 2021-10-25 | 2021-10-29 | 2021-11-19 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-29 | 2021-10-29 | X | 168777000.1.883 | 2021-11-19 | 2021-11-22 | 2021-11-22 |  | 2023-01-01 | X | 2021-10-26 | 32400 | 2021-11-19 | X | Declined | - | - | X | 2021-10-25 | 29355 | 2021-11-19 | X | Declined | [14 empty] | Helix | 29355 | 29355 | 0 | 0 | 0 | 0 | 0 | 0
36 | DOT | SC18768 | 1310739 | CAROL STREAM | Joey Betland | SUE Level A | 2021-10-14 | 2021-10-21 | 2021-10-26 |  | 2021-10-20 | 2021-10-21 | 2021-10-21 | 2021-10-27 | 2021-10-27 | X | 168777000.1.986 | 2021-11-24 | 2021-11-24 | 2021-11-24 | N | 2023-01-01 |  |  |  |  | X | 2021-10-20 | 28900 | [5 empty] | X | No response | [14 empty] | DLZ | 28900 | 0 | 0 | 28900 | 0 | 0 | 0 | 0
40 | Non-DOT | BS456 | 1410797 | Sun River Terrace | Mitch Pohlman | Survey, SUE Level B | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2022-01-11 | 2021-12-06 | 2021-12-06 | 2021-12-07 | 2021-12-14 | 2021-12-14 | X | 168777000.1.989 | 2022-01-18 | 2022-01-18 | 2022-01-18 |  | 2023-01-01 |  | 2021-11-23 | 18200 | 2022-01-11 | X | 2021-12-03 | 53890 | 2022-01-18 |  | 2021-11-30 | 22250 | 2022-01-11 |  | 2021-12-02 | 33920 | 2022-02-01 | [12 empty] | DLZ | 53890 | 0 | 0 | 53890 | 0 | 0 | 0 | 0
41 | Non-DOT | BS457 | 1410798 | St Anne | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2022-01-11 | 2021-12-06 | 2021-12-06 | 2021-12-07 | 2021-12-14 | 2021-12-14 | X | 168777000.1.990 | 2022-01-18 | 2022-01-18 | 2022-01-18 |  | 2023-01-01 |  | 2021-11-23 | 29900 | 2022-01-11 | X | 2021-12-03 | 32510 | 2022-01-18 |  | 2021-11-30 | 21500 | 2022-01-11 |  | 2021-12-02 | 29850 | 2022-02-01 | [12 empty] | DLZ | 32510 | 0 | 0 | 32510 | 0 | 0 | 0 | 0
45 | CRA | MR1826 | 1210876 | Palatine | Marissa LaPorte | Survey | 2021-12-28 | 2022-01-05 | 2022-01-12 | 2022-02-02 | 2022-01-06 | 2022-01-06 | 2022-01-10 | 2022-01-13 | 2022-01-13 | X | 168777000.1.893 | 2022-02-02 | 2022-01-24 | 2022-01-24 |  | 2023-01-01 | X | 2022-01-05 | 3600 | 2022-02-02 | X | 2022-01-05 | 1875 | 2022-02-02 | X | 2022-01-05 | 3000 | 2022-02-02 | X | Declined | [14 empty] | DLZ | 1875 | 0 | 0 | 1875 | 0 | 0 | 0 | 0
42 | Non-DOT | BS458 | 1410799 | St Anne | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2022-01-11 | 2021-12-06 | 2021-12-06 | 2021-12-07 | 2021-12-14 | 2021-12-14 | X | 168777000.1.991 | 2022-01-25 | 2022-01-25 | 2022-01-25 |  | 2023-01-01 |  | 2021-11-23 | 44750 | 2022-01-11 | X | 2021-12-03 | 55300 | 2022-01-25 |  | 2021-11-30 | 40500 | 2022-01-11 |  | 2021-12-02 | 34150 | 2022-02-01 | [12 empty] | DLZ | 55300 | 0 | 0 | 55300 | 0 | 0 | 0 | 0
43 | Non-DOT | BS459 | 1410800 | St Anne | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2022-01-11 | 2021-12-06 | 2021-12-06 | 2021-12-07 | 2021-12-14 | 2021-12-14 | X | 168777000.1.308 | 2022-01-25 | 2022-01-25 | 2022-01-25 |  | 2023-01-01 |  | 2021-11-23 | 34100 | 2022-01-11 | X | 2021-12-03 | 51050 | 2022-01-25 |  | 2021-11-30 | 28500 | 2022-01-11 |  | 2021-12-02 | 37570 | 2022-02-01 | [12 empty] | DLZ | 51050 | 0 | 0 | 51050 | 0 | 0 | 0 | 0
48 | Non-DOT | VW197 | 1210792 | Burbank | Anna Yordan | Survey, SUE Level B | 2022-01-06 | 2022-01-07 | 2022-01-14 | 2022-01-28 | 2022-01-07 | 2022-01-07 | 2022-01-10 | 2022-01-11 | 2022-01-11 | X | 168777000.A.009 | 2022-01-28 | 2022-01-25 | 2022-01-25 |  | 2023-01-01 |  |  |  |  | X | 2022-01-07 | 4300 | 2022-01-28 |  |  |  |  | X | No Response | [14 empty] | DLZ | 4300 | 0 | 0 | 4300 | 0 | 0 | 0 | 0
44 | Non-DOT | NBA10001378 | 1611126 | Malta | Marissa LaPorte | Survey, SUE Level A/B | 2021-12-17 | 2021-12-21 | 2021-12-29 | 2022-01-19 | 2021-12-22 | 2021-12-22 | 2021-12-27 | 2022-01-18 | 2022-01-18 | X | 168777000.1.898 | 2021-01-19 | 2022-02-09 | 2022-02-01 | N/A | 2023-01-01 | X | 2021-12-22 | 36297 | 2022-01-19 | X | Declined | - | - | X | 2021-12-21 | 31250 | 2021-01-19 | X | Declined | - | - | [12 empty] | Atlas | 36297 | - | - | - | 36297 | 0 | 0 | 0
49 | CRA | MR1836 | 3210900 | Westchester | Anna Yordan | Survey | 2022-01-12 | 2022-01-14 | 2022-01-24 | 2022-02-14 | 2022-01-17 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-19 | X |  | 2022-02-14 | 2022-02-03 | 2022-02-03 |  | 2023-01-01 |  |  |  |  | X | 2022-01-15 | 1625 | 2022-02-14 | [20 empty] | DLZ | 1625 | 0 | 0 | 1625 | 0 | 0 | 0 | 0
50 | CRA | MR1839 | 3210894 | LaGrange | Marissa LaPorte | Survey | 2022-01-13 | 2022-01-17 | 2022-01-25 | 2022-02-15 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-24 | 2022-01-24 | X | 168777000.1.897 | 2022-02-15 | 2022-02-03 | 2022-02-03 |  | 2023-01-01 | X | 2022-01-17 | 3200 | 2022-02-15 | X | 2022-01-17 | 1350 | 2022-02-15 | X | 2022-01-17 | 2000 | 2022-02-15 | X | 2022-01-17 | 3840 | 2022-02-15 | [12 empty] | DLZ | 1350 | 0 | 0 | 1350 | 0 | 0 | 0 | 0
46 | Non-DOT | MR1813 | 1410850 | Ludlow | Billy Pacheco | Survey, SUE Level B, Geotechnical | 2022-01-03 | 2022-01-05 | 2022-01-10 | 2022-01-26 | 2022-01-06 | 2022-01-06 | 2022-01-10 | 2022-01-13 | 2022-01-13 | X | 168777000.A.000 | 2022-01-26 | 2022-02-07 | 2022-02-07 |  | 2023-01-01 | X | 2022-01-05 | 23279 | 2022-01-26 |  | 2022-01-07 | 19800 | 2022-02-21 |  | 2022-01-05 | 29600 | 2022-01-26 |  | 2022-01-05 | 34300 | 2022-02-09 | [12 empty] | Atlas | 23279 | 0 | 0 | 0 | 23279 | 0 | 0 | 0
55 | CRA | RS989 | 1010985 | Willow Springs | Billy Pacheco |  | 2022-01-31 | 2022-02-02 | 2022-02-07 | 2022-02-28 | 2022-02-03 | 2022-02-03 | 2022-02-07 | 2022-02-08 | 2022-02-08 | X | 168777000.A.504 | 2022-02-28 | 2022-02-24 | 2022-02-24 |  | 2023-01-01 | X | 2022-02-02 | 10690 | 2022-02-28 | X | 2022-02-02 | 16750 | 2022-02-28 | X | 2022-02-02 | 11500 | 2022-02-28 | X | 2022-02-03 | 32220 | 2022-03-16 | [12 empty] | DLZ | 16750 | 0 | 0 | 16750 | 0 | 0 | 0 | 0
56 | CRA | RS991 | 1010976 | Rolling Meadows | Anna Yordan | Survey, SUE Level B | 2022-01-31 | 2022-02-02 | 2022-02-07 | 2022-02-28 | 2022-02-03 | 2022-02-03 | 2022-02-04 | 2022-02-08 | 2022-02-08 | X | 168777000.A.501 | 2022-02-28 | 2022-02-28 | 2022-02-28 |  | 2023-01-01 | X | 2022-02-02 | 8400 | 2022-02-28 | X | 2022-02-02 | 17400 | 2022-02-28 | X | 2022-02-02 | 14250 |  | X | [15 empty] | Atlas | 8400 | 0 | 0 | 0 | 8400 | 0 | 0 | 0
52 | CRA | RS927 | 1010728 | Morton Grove | Billy Pacheco |  | 2022-01-25 | 2022-01-27 | 2022-01-31 | 2022-02-25 | 2022-01-28 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 2022-02-03 | X | 168777000.A.512 | 2022-02-25 | 2022-03-01 | 2022-03-01 |  | 2023-01-01 | [8 empty] | X | 2022-01-27 | 29000 | 2022-02-25 | [16 empty] | Helix | 29000 | 29000 | 0 | 0 | 0 | 0 | 0 | 0
54 | CRA | RS988 | 1010960 | Hawthorn Woods | Matt Crescenti |  | 2022-01-31 | 2022-02-02 | 2022-02-07 | 2022-02-25 | 2022-02-03 | 2022-02-03 | 2022-02-06 | 2022-02-08 | 2022-02-08 | X | 168777000.A.502 | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 2023-01-01 | X | 2022-02-02 | 21400 | 2022-02-25 | X | 2022-02-02 | 58650 | 2022-02-25 | X | 2022-02-02 | 21750 | 2022-03-03 | X | - | 0 | - | [12 empty] | Helix | 21750 | 21750 | 0 | 0 | 0 | 0 | 0 | 0
53 | CRA | RS939 | 1010971 | Sterling | Marissa LaPorte | Survey, SUE Level B | 2022-01-31 | 2022-02-02 | 2022-02-08 | 2022-03-01 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-08 | 2022-02-08 | X | 168777000.A.503 | 2022-03-03 | 2022-03-07 | 2022-03-07 |  | 2023-01-01 | X | 2022-02-02 | 10300 | 2022-03-01 | X | 2022-02-02 | 12750 | 2022-03-01 | X | 2022-02-02 | 10750 | 2022-03-03 | X | 2022-02-02 | 24190 | 2022-03-11 | [12 empty] | Helix | 10750 | 10750 | 0 | 0 | 0 | 0 | 0 | 0
47 | DOT | SC19989 | 1010941 | Chenoa | Joey Betland | Survey, SUE Level A/B | 2022-01-05 | 2022-01-10 | 2022-01-17 | 2022-02-01 | 2022-01-13 | 2022-01-13 | 2022-01-18 | 2022-01-18 | 2022-01-20 | X | 168777000.1.995 | 2022-03-07 | 2022-03-07 | 2022-03-07 | N | 2023-01-01 |  |  |  |  | X | 2022-01-10 | 18250 | [5 empty] | X | 2022-01-10 | 15845 | 2022-02-01 | [12 empty] | Millennia | 15845 | 0 | 15845 | 0 | 0 | 0 | 0 | 0
58 | Non-DOT | MR1851 | 1211026 | Rockford | Anna Yordan | Survey, SUE Level B | 2022-02-02 | 2022-02-04 | 2022-02-14 | 2022-03-07 | 2022-02-07 | 2022-02-09 | 2022-02-09 | 2022-02-10 | 2022-02-10 | X | 168777000.A.006 | 2022-03-07 | 2022-03-07 | 2022-03-07 |  | 2023-01-01 | X | 2022-02-04 | 17850 | 2022-03-07 | X | 2022-02-04 | 16400 | 2022-03-07 | X | 2022-02-03 | 16750 | 2022-03-18 | X | Declined | [14 empty] | DLZ | 16400 | 0 | 0 | 16400 | 0 | 0 | 0 | 0
57 | CRA | RS993 | 1010970 | Ottawa | Josh Meyer | Survey, SUE Level B, Geotechnical | 2022-02-01 | 2022-02-03 | 2022-02-10 | 2022-03-10 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-08 | 2022-02-08 | X | 168777000.A.505 | 2022-03-10 | 2022-03-08 | 2022-03-08 |  | 2023-01-01 | N/A | N/A | N/A | N/A | X | 2022-02-03 | 37250 | 2022-03-10 | X | 2022-02-01 | 21000 | 2022-03-10 | X | 2022-02-02 | 54110 | 2022-03-21 | [12 empty] | DLZ | 37250 | 0 | 0 | 37250 | 0 | 0 | 0 | 0
61 | CRA | RS938 | 1011052 | Geneseo | Matt Crescenti |  | 2022-02-15 | 2022-02-17 | 2022-02-24 | 2022-03-17 | 2022-02-21 | 2022-02-22 | 2022-02-22 | 2022-02-24 | 2022-02-24 | X | 168777000.A.516 | 2022-03-17 | 2022-03-15 | 2022-03-15 |  | 2023-01-01 | X | declined | 0 | - | X | 2022-02-17 | 11650 | 2022-03-18 | X | 2022-02-17 | 8900 | 2022-03-17 | X | 2022-02-17 | 24925 | 2022-03-17 | [12 empty] | Helix | 8900 | 8900 | 0 | 0 | 0 | 0 | 0 | 0
62 | DOT | SC19761 | 1411083 | Mokena | Joey Betland | SUE Level A | 2022-02-15 | 2022-02-17 | 2022-03-02 | 2022-04-01 | 2022-03-01 | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-03-02 | X | 168777000.1.076 | 2022-04-01 | 2022-03-15 | 2022-03-15 | N | 2023-01-01 |  |  |  |  | X | 2022-02-17 | 24900 | [5 empty] | X | No Response | [14 empty] | DLZ | 24900 | 0 | 0 | 24900 | 0 | 0 | 0 | 0
59 | DOT | M9725 | 1210923 | Glenview | Joey Betland | Geotechnical | 2022-02-04 | 2022-02-08 | 2022-02-11 | 2022-03-18 | 2022-02-08 | 2022-02-08 | 2022-02-09 | 2022-02-15 | 2022-02-15 | X | 168777000.1.068 | 2022-03-16 | 2022-03-16 | 2022-03-16 | N | 2023-01-01 |  |  |  |  | X | 2022-02-08 | 16750 | 2022-03-29 |  |  |  |  | X | 2022-02-08 | 17950 | 2022-03-18 | [12 empty] | Millennia | 17950 | 0 | 17950 | 0 | 0 | 0 | 0 | 0
63 | CRA | RS1000 | 1011072 | Shabbona | Matt Crescenti |  | 2022-03-06 | 2022-03-08 | 2022-03-14 | 2022-04-04 | 2022-03-09 | 2022-03-09 | 2022-03-10 | 2022-03-15 | 2022-03-15 | X | 168777000.A.518 | 2022-04-04 | 2022-04-04 | 2022-04-04 |  | 2023-01-01 | X | 2022-03-08 | 7700 | 2022-04-04 | X | 2022-03-08 | 9375 | 2022-04-14 | X | 2022-03-08 | 8000 | 2022-04-11 | X | 2022-03-08 | 13750 | 2022-04-06 | [12 empty] | Atlas | 7700 | 0 | 0 | 0 | 7700 | 0 | 0 | 0
64 | CRA | RS972 | 1011071 | Lee | Marissa LaPorte | Survey, SUE Level B | 2022-03-06 | 2022-03-08 | 2022-03-14 | 2022-04-04 | 2022-03-09 | 2022-03-09 | 2022-03-10 | 2022-03-15 | 2022-03-15 | X | 168777000.A.517 | 2022-04-04 | 2022-04-04 | 2022-04-04 |  | 2023-01-01 | X | 2022-03-08 | 7700 | 2022-04-04 | X | 2022-03-08 | 7275 | 2022-04-14 | X | 2022-03-08 | 8000 | 2022-04-11 | X | 2022-03-08 | 12440 | 2022-04-06 | [12 empty] | Atlas | 7700 | 0 | 0 | 0 | 7700 | 0 | 0 | 0
60 | Non-DOT | BS611 | 1410951 | Joliet | Mitch Pohlman | Survey, SUE Level B | 2022-02-09 | 2022-02-11 | 2022-02-18 | 2022-03-11 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-03-02 | 2022-03-02 | X | 168777000.A.011 | 2022-04-01 | 2022-04-08 | 2022-04-08 |  | 2023-01-01 | [8 empty] | X | 2022-02-21 | 41750 | 2022-03-21 | [16 empty] | Helix | 41750 | 41750 | 0 | 0 | 0 | 0 | 0 | 0
67 | CRA | RS995 | 1011105 | Hudson | Anna Yordan | Survey, SUE Level B | 2022-03-17 | 2022-03-21 | 2022-03-28 | 2022-04-15 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | X | 168777000.A.014 | 2022-04-15 | 2022-04-13 | 2022-04-13 |  | 2023-01-01 | X | no response | - | - | X | 2022-03-21 | 6800 | 2022-04-15 | X | 2022-03-21 | 7800 | 2022-04-15 | X | 2022-03-21 | 8195 | 2022-04-15 | [12 empty] | DLZ | 6800 | 0 | 0 | 6800 | 0 | 0 | 0 | 0
68 | CRA | RS999 | 1011070 | Hooppole | Anna Yordan | Survey, SUE Level B | 2022-03-21 | 2022-03-22 | 2022-03-30 | 2022-04-21 | 2022-04-23 | 2022-03-28 | 2022-03-28 | 2022-03-29 | 2022-03-29 | X | 168777000.A.527 | 2022-04-18 | 2022-04-15 | 2022-04-15 |  | 2023-01-01 | X | declined | - | - | X | 2022-03-22 | 8250 | 2022-04-15 | x | 2022-03-22 | 7250 | 2022-04-18 | X | No Response | [14 empty] | Helix | 7250 | 7250 | 0 | 0 | 0 | 0 | 0 | 0
70 | DOT | SC14346 (1) | 1111271 | Woodridge | Joey Betland | Survey, SUE Level B | 2022-03-30 | 2022-04-01 | 2021-04-05 | 2022-04-25 | 2022-04-04 | 2022-04-04 | 2022-04-11 | 2022-04-11 | 2022-04-11 | X | 168777000.A.019 (12") 168777000.A.020 (36") | 2022-04-29 | 2022-04-26 | 2022-04-26 | N | 2023-01-01 |  |  |  |  | X | 2022-03-31 | 34480 | 2022-04-25 |  |  |  |  | X | [15 empty] | DLZ | 34480 | 0 | 0 | 34480 | 0 | 0 | 0 | 0
69 | CRA | RS989 | 1010985 | Willow Springs | Alban Shehu | Survey, SUE Level B | 2022-03-23 | 2022-03-25 | 2022-04-08 | 2022-04-20 | 2022-04-05 | 2022-04-06 | 2022-04-11 | 2022-04-13 | 2022-04-15 | X | 168777000.A.525 | 2022-05-04 | 2022-04-28 | 2022-04-28 |  | 2023-01-01 |  |  |  |  | X | 2022-04-01 | 10950 | 2022-04-20 | [20 empty] | DLZ | 10950 | 0 | 0 | 10950 | 0 | 0 | 0 | 0
71 | CRA | RS996 | 1011090 | Wilmington | Alban Shehu | Survey, SUE Level B | 2022-04-05 | 2022-04-07 | 2022-04-11 | 2022-05-04 | 2022-04-11 | 2022-04-11 | 2022-04-11 | 2022-04-13 | 2022-04-15 | X | 168777000.A.526 | 2022-05-06 | 2022-05-02 | 2022-05-02 |  | 2023-01-01 | X |  |  |  | X | 2022-04-07 | 6150 | 2022-05-04 | X | 2022-04-07 | 9000 | 2022-05-03 | X | [15 empty] | DLZ | 6150 | 0 | 0 | 6150 | 0 | 0 | 0 | 0
72 | DOT | N14027 | 1211368 | Lake Villa | Tim Purtell | SUE Level A | 2022-04-26 | 2022-04-29 | 2022-05-04 | 2022-05-18 | 2022-04-25 | 2022-04-25 | 2022-04-26 | 2022-05-06 | 2022-05-09 | X | 168777000.A.521 | 2022-05-24 | 2022-05-24 | 2022-05-24 | N | 2023-01-01 |  | 2022-05-02 | 17000 | 2022-05-13 | X | 2022-04-29 | 21900 | 2022-05-18 |  | No Response |  |  |  | No Reponse | [14 empty] | DLZ | 21900 | 0 | 0 | 21900 | 0 | 0 | 0 | 0
73 | DOT | SC20874 | 1311367 | West Chicago | Randy Castellon | Survey, SUE Level B | 2022-05-02 | 2022-05-05 | 2022-05-11 | 2022-05-27 | 2022-05-09 | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-05-11 | X | 168777000.A.024 | 2022-07-15 | 2022-05-27 | 2022-05-27 | N | 2023-01-01 | X | 2022-05-05 | 14200 | 2022-05-13 | X | 2022-05-05 | 12250 | 2022-05-27 | X | No Response |  |  | X | No Reponse | [14 empty] | DLZ | 12250 | 0 | 0 | 12250 | 0 | 0 | 0 | 0
76 | Non-DOT | BS110 | 1211333 | Calumet City | Mitch Pohlman | Survey, SUE Level B | 2022-05-11 | 2022-05-13 | 2022-05-24 | 2022-06-14 | 2022-05-17 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-19 | X | 168777000.A.031 | 2022-06-14 | 2022-06-16 | 2022-06-01 |  | 2023-01-01 | [9 empty] | 2022-05-13 | 46460 | 2022-06-17 |  | No Response |  |  |  | 2022-05-16 | 44285 | 2022-06-14 | [8 empty] | Dawood | 44285 | 0 | 0 | 0 | 0 | 44285 | 0 | 0
78 | Non-DOT | VW284 | 1211335 | Worth | Mark Stanley | Survey, SUE Level B | 2022-05-11 | 2022-05-13 | 2022-05-24 | 2022-06-17 | 2022-05-17 | 2022-05-19 | 2022-05-20 | 2022-05-24 | 2022-05-25 | X | 168777000.A.032 | 2022-06-17 | 2022-06-17 | 2022-06-01 |  | 2023-01-01 | [8 empty] | X | 2022-05-13 | 27850 | 2022-06-17 | X | No Response |  |  | X | 2022-05-16 | 32175 | 2022-06-14 | [8 empty] | Helix | 27850 | 27850 | 0 | 0 | 0 | 0 | 0 | 0
75 | Non-DOT | BS419 | 1211332 | Park Ridge | Nick Michaels | Survey, SUE Level A/B | 2022-05-04 | 2022-05-06 | 2022-05-13 | 2022-06-24 | 2022-05-18 | 2022-05-18 | 2022-05-19 | 2022-05-24 | 2022-05-25 | X | 168777000.A.528 | 2022-06-24 | 2022-06-24 | 2022-06-01 |  | 2023-01-01 |  |  |  |  | X | Declined |  |  | X | 2022-05-09 | 72500 | 2022-06-14 | X | 2022-05-10 | 55950 | 2022-06-24 | X | 2022-05-10 | 30100 | 4 wks from NTP | [8 empty] | Helix | 72500 | 72500 | 0 | 0 | 0 | 0 | 0 | 0
66 | Non-DOT | BS450-453 | 1411323 | Momence | Mitch Pohlman | Survey, SUE Level A/B, Geotechnical | 2022-03-15 | 2022-03-18 | 2022-03-28 | 2022-06-17 | 2022-03-24 | 2022-04-13 | 2022-04-13 | 2022-04-26 | 2022-05-02 | X | 168777000.A.023 | 2022-06-17 | 2022-06-17 | 2022-06-17 |  | 2023-01-01 |  |  |  |  | X | 2022-03-21 | 148950 | 2022-05-09 |  | 2022-03-22 | 196650 | 2022-06-30 |  | 2022-03-21 | 209535 | 2022-06-06 | [12 empty] | DLZ | 148950 | 0 | 0 | 148950 | 0 | 0 | 0 | 0
65 | Non-DOT | BS441-443 | 1211324 | Crete | Nick Michaels | Survey, SUE Level A/B, Geotechnical | 2022-03-15 | 2022-03-18 | 2022-03-28 | 2022-06-24 | 2022-03-24 | 2022-04-13 | 2022-04-13 | 2022-04-26 | 2022-05-03 | X | 168777000.A.522 | 2022-06-24 | 2022-06-27 | 2022-06-27 |  | 2023-01-01 |  |  |  |  | X | 2022-03-21 | 108800 | 2022-05-09 |  | 2022-03-22 | 113570 | 2022-06-30 |  | 2022-03-21 | 128000 | 2022-06-02 | [12 empty] | DLZ | 108800 | 0 | 0 | 108800 | 0 | 0 | 0 | 0
74 | Non-DOT | BS381 | 1211334 | Loves Park | Nick Michaels | Survey, SUE Level B | 2022-05-04 | 2022-05-06 | 2022-05-13 | 2022-06-13 | 2022-05-12 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-16 | X | 168777000.A.030 | 2022-06-13 | 2022-06-15 | 2022-07-01 |  | 2023-01-01 |  |  |  |  | X | Declined |  |  | X | 2022-05-09 | $39700 $74500 | 6/14/22 6/24/22 | X | 2022-05-10 | $66400 $124830 | 7/1/22 7/22/22 | X | 2022-05-10 | 50300 | 4 wks from NTP | [8 empty] | Dawood | 50300 | 0 | 0 | 0 | 0 | 50300 | 0 | 0
77 | Non-DOT | MR1189 | 1211404 | Bedford Park | Nick Michaels | Survey, SUE Level B, Geotechnical | 2022-05-11 | 2022-05-13 | 2022-05-18 | 2022-06-06 | 2022-05-17 | 2022-05-18 | 2022-05-20 | 2022-05-25 | 2022-05-25 | X | 168777000.A.529 | 2022-06-13 | 2022-06-23 | 2022-07-01 |  | 2023-01-01 |  |  |  |  | X | 2022-05-17 | 42425 | 2022-06-08 | X | 2022-05-17 | 55800 | 2022-07-01 | X | No response | [14 empty] | DLZ | 42425 | 0 | 0 | 42425 | 0 | 0 | 0 | 0
80 | DOT | M13578 | 1211455 | Orland Park | Taylor Lierow | SUE Level A | 2022-05-17 | 2022-05-20 | 2022-05-27 | 2022-06-20 | 2022-05-23 | 2022-05-24 | 2022-05-24 | 2022-05-26 | 2022-05-31 | X | 168777000.A.533 | 2022-06-20 | 2022-06-16 | 2022-07-01 | N | 2023-01-01 |  |  |  |  | X | 2022-05-23 | 8375 | 2022-06-20 | X | No Response |  |  | X | No Reponse | [14 empty] | DLZ | 8375 | 0 | 0 | 8375 | 0 | 0 | 0 | 0
79 | CRA | RS991 | 1010976 | Schaumburg | Anna Yordan | Survey, SUE Level B | 2022-05-16 | 2022-05-18 | 2022-05-25 | 2022-06-15 | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-05-31 | 2022-05-31 | X | 168777000.A.534 | 2022-06-21 | 2022-06-16 | 2022-07-01 |  | 2023-01-01 |  |  |  |  | X | 2022-05-18 | 7900 | 2022-06-15 | X | 2022-05-19 | 8100 | 2022-06-15 | X | 2022-05-18 | 22830 | 2022-06-20 | X | 2022-05-18 | 10500 | 2022-06-15 | [8 empty] | DLZ | 7900 | 0 | 0 | 7900 | 0 | 0 | 0 | 0
84 | Non-DOT | MR1899 | 1211570 | Franklin Park | Mitch Pohlman | Survey, SUE Level A/B, Geotechnical | 2022-06-14 | 2022-06-16 | 2022-06-29 | 2022-07-29 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-06-30 | X | 168777000.A.035 | 2022-07-29 | 2022-07-27 | 2022-07-01 |  | 2023-01-01 | [5 empty] | 2022-06-22 | 92600 | 2022-08-16 | X | 2022-06-23 | 73650 | 2022-07-29 | [16 empty] | Helix | 73650 | 73650 | 0 | 0 | 0 | 0 | 0 | 0
86 | CRA | RS1011 | 1011552 | Mt. Prospect | Mark Stanley | Survey, SUE Level B | 2022-06-27 | 2022-06-29 | 2022-07-11 | 2022-08-01 | 2022-06-30 | 2022-06-30 | 2022-07-01 | 2022-07-07 | 2022-07-07 | X | 168777000.A.538 | 2022-08-01 | 2022-07-29 | 2022-07-01 |  | 2023-01-01 | X | 2022-06-29 | 12605 | 2022-08-01 | X | 2022-06-29 | 19100 | 2022-08-01 | X | 2022-06-29 | 10750 | 2022-08-01 | X | 2022-06-29 | 20770 | 2022-08-01 | X | 2022-06-29 | 8250 | 2 wks from NTP | [8 empty] | Dawood | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0
87 | CRA | RS1026 | 1011618 | Mt. Prospect | Alban Shehu | Survey, SUE Level B | 2022-06-27 | 2022-06-29 | 2022-07-11 | 2022-08-01 | 2022-06-30 | 2022-06-30 | 2022-07-01 | 2022-07-07 | 2022-07-07 | X | 168777000.A.537 | 2022-08-01 | 2022-07-29 | 2022-07-01 |  | 2023-01-01 | X | 2022-06-29 | 16975 | 2022-08-04 | X | 2022-06-29 | 21300 | 2022-08-01 | X | 2022-06-29 | 13900 | 2022-08-01 | X | 2022-06-29 | 19910 | 2022-08-01 | X | 2022-06-29 | 8250 | 2 wks from NTP | [8 empty] | Dawood | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 0
82 | Non-DOT | MR1892 | 1411473 | Fisher | Anna Yordan | Survey, SUE Level B, Geotechnical | 2022-05-27 | 2022-06-01 | 2022-06-08 | 2022-06-29 | 2022-06-02 | 2022-06-03 | 2022-06-03 | 2022-06-07 | 2022-06-07 | X | 168777000.A.042 | 2022-06-29 | 2022-06-26 | 2022-08-01 |  | 2023-01-01 |  |  |  |  | X | Declined |  |  | X | 2022-06-01 | 40000 | 2022-06-29 | X | 2022-06-02 | 33070 | 2022-06-29 | [12 empty] | Millennia | 33070 | 0 | 33070 | 0 | 0 | 0 | 0 | 0
83 | Non-DOT | NBA10005718 | 1911489 | Romeoville | Anna Yordan | Survey, SUE Level A/B | 2022-06-08 | 2022-06-13 | 2022-06-17 | 2022-07-13 | 2022-06-14 | 2022-06-15 | 2022-06-15 | 2022-06-16 | 2022-06-16 | X | 168777000.A.036 | 2022-07-08 | 2022-07-08 | 2022-08-01 |  | 2023-01-01 |  |  |  |  | X | 2022-06-13 | 91900 | 2022-07-22 | X | 2022-06-10 | 57650 | 2022-07-20 | X | No response |  |  | X | 2022-06-13 | 50300 | 3 wks from NTP | [8 empty] | Dawood | 50300 | 0 | 0 | 0 | 0 | 50300 | 0 | 0
81 | DOT | SC14346 (2) | 1311270 | Woodridge | Joey Betland | Survey, SUE Level B | 2022-05-18 | 2022-05-27 | 2022-06-02 | 2022-06-20 | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-06-28 | X | 168777000.A.519 | 2022-07-18 | 2022-07-15 | 2022-08-01 | N | 2023-01-01 | [28 empty] | DLZ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | CRA | RS1008 & RS1050 | 1011561 1011562 | Hebron | Marissa LaPorte | Survey, SUE Level B | 2022-06-27 | 2022-06-29 | 2022-07-06 | 2022-07-27 | 2022-06-30 | 2022-06-30 | 2022-07-06 | 2022-07-07 | 2022-07-07 | X | 168777000.A.539 | 2022-07-27 | 2022-07-29 | 2022-08-01 |  | 2023-01-01 | X | 2022-06-29 | 12998 | 2022-07-27 | X | 2022-06-29 | 11600 | 2022-07-27 | X | 2022-06-29 | 12980 | 2022-07-27 | X | 2022-06-29 | 18960 | 2022-07-27 | X | 2022-06-29 | 9300 | 2 wks from NTP | [8 empty] | Dawood | 9300 | 0 | 0 | 0 | 0 | 9300 | 0 | 0
88 | CRA | RS1053 | 1011565 | Peotone | Alban Shehu | Survey, SUE Level B | 2022-06-30 | 2022-07-05 | 2022-07-14 | 2022-08-04 | 2022-07-07 | 2022-07-07 | 2022-07-08 | 2022-07-12 | 2022-07-13 | X | 168777000.A.540 | 2022-08-04 | 2022-08-01 | 2022-08-01 |  | 2023-01-01 | X | 2022-07-05 | 12880 | 3 wks from NTP | X | 2022-07-01 | 33000 | 2022-08-04 | X | 2022-07-05 | 29600 | 2022-08-08 | X | 2022-07-05 | 21908 | 2022-08-05 | X | 2022-07-04 | 9450 | 2022-08-04 | [8 empty] | Dawood | 9450 | 0 | 0 | 0 | 0 | 9450 | 0 | 0
89 | Non-DOT | NBA10007422 | 1911611 | Plainfield | Nick Michaels | Survey, SUE Level B | 2022-07-07 | 2022-07-11 | 2022-07-18 | 2022-08-05 | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-14 | 2022-07-14 | X | 168777000.A.041 | 2022-08-05 | 2022-08-05 | 2022-08-01 |  | 2023-01-01 |  |  |  |  | X | 2022-07-12 | 52750 | 2022-08-12 | X | 2022-07-13 | 25150 | 2022-08-05 | X |  |  |  | X | 2022-07-12 | 26500 | 2022-08-08 | [8 empty] | Helix | 25150 | 25150 | 0 | 0 | 0 | 0 | 0 | 0
90 | CRA | RS1062 |  | Marengo | Marissa LaPorte | Survey, SUE Level B, Geotechnical | 2022-07-13 | 2022-07-15 | 2022-07-25 | 2022-08-15 | 2022-08-01 | 2022-08-01 | 2022-08-02 | 2022-08-08 | 2022-08-08 | X | 168777000.A.043 | 2022-08-25 | 2022-08-25 | 2022-08-01 |  | 2023-01-01 | X | 2022-07-15 | A - $6,480 | 2022-08-15 | X | 2022-07-15 | A - $10,225 B - $40,200 | 2022-08-12 | X | 2022-07-15 | 34250 | 2022-08-15 | X | 2022-07-15 | A - $10,420 B - $43,670 | 2022-08-15 | X | 2022-07-15 | A - $7,870 B - $11,200 | 2022-08-08 | [8 empty] | Helix | 34250 | 34250 | 0 | 0 | 0 | 0 | 0 | 0
91 | DOT | SC14346 (3) | 1311270 1111271 | Woodridge | Anna Yordan | Survey, SUE Level A/B | 2022-08-01 | 2022-08-03 | 2022-08-10 | 2022-08-31 | 2022-08-05 | 2022-08-08 | 2022-08-08 | 2022-08-12 | 2022-08-15 | X | 168777000.A.544 | 2022-08-31 | 2022-08-30 | 2022-09-01 | N | 2023-01-01 | X | 2022-08-03 | 23900 | 2022-08-31 | X | 2022-08-04 | 29400 | 8/31/2022 (Geotech 9/14) | X | 2022-08-03 | 21000 | 2023-10-25 | X | No Response |  |  | X | No response | [10 empty] | Helix | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0
94 | CRA | RS1075 | 1011716 | St. Anne | Marissa LaPorte | Survey, SUE Level B | 2022-08-24 | 2022-02-26 | 2022-09-02 | 2022-09-23 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 2022-09-06 | 2022-09-23 | X | 168777000.A046 | 2022-09-23 | 2022-09-23 | 2022-09-01 |  | 2023-01-01 | X | 2022-08-26 | 11500 | 2022-09-23 | X | 2022-09-26 | 16500 | 2022-09-23 | X | 2022-08-26 | 9250 | 2022-09-23 | X | No Response |  |  | X | 2022-08-25 | 9000 | 2022-09-23 | [8 empty] | Helix | 9250 | 9250 | 0 | 0 | 0 | 0 | 0 | 0
95 | CRA | RS956 | 1011722 | Aurora | Alban Shehu | Survey, SUE Level B | 2022-08-24 | 2022-08-26 | 2022-09-07 | 2022-09-28 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 2022-09-01 | 2022-09-01 | X | 168777000.A.545 | 2022-09-28 | 2022-09-28 | 2022-09-01 |  | 2023-01-01 | X | 2022-08-26 | 6500 | 2 wks from NTP | X | 2022-08-26 | 6400 | 2022-09-28 | X | 2022-08-26 | 6250 | 2022-09-28 | X | No Response | - | - | X | 2022-08-25 | 12980 | 2 wks from NTP | [8 empty] | Helix | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0
93 | Non-DOT | MR1049 | 140585 | Farmer City | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2022-08-24 | 2022-08-26 | 2022-09-09 | 2022-09-30 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 2022-09-01 | 2022-09-06 | X | 168777000.A.047 | 2022-09-30 | 2022-09-28 | 2022-09-01 |  | 2023-01-01 | [5 empty] | 2022-08-26 | 26950 | 2022-09-30 |  | 2022-08-26 | 28500 | 2022-09-30 | X | 2022-08-26 | 24850 | 2022-09-30 | [12 empty] | Millennia | 24850 | 0 | 24850 | 0 | 0 | 0 | 0 | 0
96 | Non-DOT | MR1928 | 1211740 | Chicago Heights | Mark Stanley | Survey, SUE Level B, Geotechnical | 2022-08-26 | 2022-08-31 | 2022-09-09 | 2022-09-30 | 2022-09-02 | 2022-09-06 | 2022-09-06 | 2022-09-08 | 2022-09-08 | X | 168777000.A.048 | 2022-10-28 | 2022-10-27 | 2022-09-01 |  | 2023-01-01 | X | 2022-08-31 | 19453 | 2022-09-30 | X | 2022-08-31 | 53200 | 2022-09-30 | X | 2022-08-31 | 63000 | 2022-10-05 | X | 2022-09-02 | 59234 | 2022-09-30 | X | 2022-08-30 | 42000 | 2022-09-30 | [8 empty] | DLZ | 53200 | 0 | 0 | 53200 | 0 | 0 | 0 | 0
92 | DOT | N14915 | 1211681 | Crystal Lake | Randy Castellon | Survey, SUE Level A/B | 2022-08-09 | 2022-08-11 | 2022-08-18 | 2022-09-01 | 2022-08-12 | 2022-08-15 | 2022-08-16 | 2022-08-16 | 2022-08-26 | X | 168777000.A.052 | 2022-08-29 | 2022-08-29 | 2022-10-01 | N | 2023-01-01 | X | 2022-08-11 | 17620 | 2022-09-01 | X | 2022-08-11 | 26500 | 2022-09-01 | X | No Reponse |  |  | X | No Reponse | [14 empty] | Atlas | 17620 | 0 | 0 | 0 | 17620 | 0 | 0 | 0
106 | DOT | SC21135-1 | 1111723 | Diamond | Tim Purtell | SUE Level A | 2022-08-15 | 2022-08-20 | 2022-08-25 | 2022-08-27 | 2022-09-01 | 2022-09-04 | 2022-09-07 | 2022-09-09 | 2022-09-12 | X | 168777000.A.553 | 2022-09-26 | 2022-09-26 | 2022-10-01 | N | 2023-01-01 | X | 2022-08-31 | 15500 | 2022-09-23 | X | 2022-08-30 | 16200 | 2022-09-16 | [20 empty] | DLZ | 16200 | 0 | 0 | 16200 | 0 | 0 | 0 | 0
97 | DOT | SC20084 | 1411802 | BOURBONNAIS | Anna Yordan | SUE Level A | 2022-09-01 | 2022-09-06 | 2022-09-13 | 2022-09-30 | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-09-13 | 2022-09-14 | X | 168777000.A.057 | 2022-09-30 | 2022-10-19 | 2022-10-01 | N | 2023-01-01 | X | 2022-09-07 | 26444 | 2022-10-07 | X | 2022-09-06 | 46400 | 2022-09-30 | X | 2022-09-07 | 34000 | 2022-09-30 | X | No response | [14 empty] | DLZ | 46400 | 0 | 0 | 46400 | 0 | 0 | 0 | 0 | 17620 | 19382
98 | Non-DOT | NBA10002073 | 1611416 | GENOA | Anna Yordan | Survey, SUE Level A/B, Geotechnical | 2022-09-08 | 2022-09-12 | 2022-09-19 | 2022-10-10 | 2022-09-20 | 2022-09-21 | 2022-09-21 | 2022-09-27 | 2022-09-27 | X | 168777000.A.054 | 2022-10-15 | 2022-10-15 | 2022-10-01 |  | 2023-01-01 | X | 2022-09-12 | 27120 | 2022-10-18 | X | N/A |  |  | X | N/A |  |  | X | N/A |  |  | X | 2022-09-20 | 35420 | 2022-10-15 | [8 empty] | Dawood | 35420 | 0 | 0 | 0 | 0 | 35420 | 0 | 0
99 | DOT | SC21460 | 1311845 | Oswego | Taylor Lierow | SUE Level A | 2022-09-20 | 2022-09-23 | 2022-09-30 | 2022-10-19 | 2022-09-26 | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-29 | X | 168777000.A.049 | 2022-10-19 | 2022-10-10 | 2022-10-01 | N | 2023-01-01 | X | 2022-09-23 | 18200 | 2022-10-14 | X | 2022-09-23 | 20300 | 2022-10-14 | X | 2022-09-23 | 26400 | 2022-10-16 | X | No response |  |  | X | No response | [10 empty] | DLZ | 20300 | 0 | 0 | 20300 | 0 | 0 | 0 | 0
100 | Non-DOT | BS435 | 1411801 | New Lenox | Alban Shehu | Survey, SUE Level B | 2022-09-26 | 2022-09-29 | 2022-10-10 | 2022-10-31 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-10-05 | 2022-10-05 | X | 168777000.A.050 | 2022-10-31 | 2022-10-31 | 2022-10-01 |  | 2023-01-01 | X | 2022-09-29 | 17530 | 3 wks from NTP | X | 2022-09-29 | 39100 | 2022-10-31 | X | 2022-09-30 | 19500 | 2022-10-31 | X | No Response | - | - | X | 2022-09-28 | 14010 | 2022-10-31 | [8 empty] | Helix | 19500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0
103 | CRA | RS1079 | 1011803 | Melrose Park | Marissa LaPorte | Survey, SUE Level B | 2022-10-03 | 2022-10-05 | 2022-10-12 | 2022-11-02 | 2022-10-06 | 2022-10-11 | 2022-10-11 | 2022-10-12 | 2022-10-12 | X | 168777000.A.051 | 2022-11-02 | 2022-10-27 | 2022-10-01 |  | 2023-01-01 | X | 2022-10-05 | 6667 | 2022-11-02 | X | 2022-10-05 | 6725 | 2022-11-02 | X | 2022-10-05 | 8250 | 2022-11-02 | X | 2022-10-05 | 14970 | 2022-11-02 | X | 2022-10-05 | 10761 | 2022-11-02 | [8 empty] | DLZ | 6725 | 0 | 0 | 6725 | 0 | 0 | 0 | 0
104 | CRA | RS1082 | 1011885 | Naperville | Marissa LaPorte | Survey, SUE Level B | 2022-10-06 | 2022-10-10 | 2022-10-17 | 2022-11-07 | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-18 | 2022-10-18 | X | 168777000.A.055 | 2022-11-07 | 2022-11-02 | 2022-10-01 |  | 2023-01-01 |  |  |  |  | X | 2022-10-10 | 7410 | 2022-11-07 | X | 2022-10-10 | 8150 | 2022-11-11 | X |  |  |  | X | 2022-10-10 | 7300 | 2022-11-07 | [8 empty] | DLZ | 7410 | 0 | 0 | 7410 | 0 | 0 | 0 | 0
105 | CRA | RS1083 | 1011869 | Naperville | Marissa LaPorte | Survey, SUE Level B | 2022-10-06 | 2022-10-10 | 2022-10-17 | 2022-11-07 | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-18 | 2022-10-18 | X | 168777000.A.056 | 2022-11-07 | 2022-11-07 | 2022-10-01 |  | 2023-01-01 |  |  |  |  | X | 2022-10-10 | 36385 | 2022-11-07 | X | 2022-10-10 | 18600 | 2022-11-11 | X |  |  |  | X | 2022-10-10 | 16593.75 | 2022-11-07 | [8 empty] | DLZ | 36385 | 0 | 0 | 36385 | 0 | 0 | 0 | 0
107 | CRA | RS1080 | 1011926 | Wilmington | Mitch Pohlman | Survey, SUE Level B | 2022-10-11 | 2022-10-13 | 2022-10-21 | 2022-11-11 | 2022-10-17 | 2022-10-18 | 2022-10-18 | 2022-10-25 | 2022-10-25 | X | 168777000.A.058 | 2022-11-15 | 2022-10-14 | 2022-11-01 |  | 2023-01-01 |  |  |  |  | X | 2022-10-13 | 5800 | 2022-11-11 |  | 2022-10-11 | 6000 | 2022-11-11 | [16 empty] | DLZ | 5800 | 0 | 0 | 5800 | 0 | 0 | 0 | 0
111 | CRA | RS940 | 1011912 | Rolling Meadows | Anna Yordan | SUE Level A | 2022-10-18 | 2022-10-20 | 2022-10-28 | 2022-11-18 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | X | 168777000.A.061 | 2022-11-18 | 2022-11-16 | 2022-11-01 |  | 2023-01-01 | X | 2022-10-20 | 8429 | 2022-11-18 | X | Decline |  |  | X | 2022-10-21 | 6250 | 2022-11-14 | X | N/A |  |  | X | 2022-10-22 | 9150 | 2022-11-18 | [8 empty] | Atlas | 8429 | 0 | 0 | 0 | 8429 | 0 | 0 | 0
113 | CRA | RS942 | 1011914 | Palatine | Mark Stanley | Survey, SUE Level A/B | 2022-10-20 | 2022-10-24 | 2022-11-01 | 2022-11-22 | 2022-10-25 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | X | 168777000.A.060 | 2022-11-22 | 2022-11-22 | 2022-11-01 |  | 2023-01-01 | X | 2022-10-24 | 18010 | 2022-11-22 | X | Decline | - | - | X | 2022-10-21 | 19750 | 2022-11-22 | X | No Response | - | - | X | 2022-10-24 | 12300 | 2022-11-17 | [8 empty] | Atlas | 18010 | 0 | 0 | 0 | 18010 | 0 | 0 | 0
112 | Non-DOT | NBA10006212-1 | 1511906 | Melrose Park | Mitch Pohlman | SUE Level A | 2022-10-18 | 2022-10-20 | 2022-10-28 | 2022-11-18 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-11-02 | 2022-11-02 | X | 168777000.A.064 | 2022-11-23 | 2022-11-28 | 2022-11-01 |  | 2023-01-01 | [5 empty] | Decline |  |  | X | 2022-10-21 | 40500 | 2022-11-18 |  | No Response | [14 empty] | Helix | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | 0
108 | Non-DOT | MR1913 | 1211933 | Des Plaines | Anna Yordan | Survey, SUE Level B | 2022-10-12 | 2022-10-17 | 2022-10-25 | 2022-11-21 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-31 | 2022-10-31 | X | 168777000.A.062 | 2022-11-28 | 2022-11-29 | 2022-11-01 |  | 2023-01-01 |  |  |  |  | X | Decline |  |  | X | 2022-10-21 | 24200 | 2022-11-21 | X | 2022-10-20 | 24580 | 2022-11-29 | X | No Response | [10 empty] | Helix | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 0
114 | CRA | RS941 | 1011913 | Mt Prospect | Mark Stanley | Survey, SUE Level B | 2022-10-27 | 2022-10-31 | 2022-11-08 | 2022-12-01 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-10 | 2022-11-10 | X | 168777000.A.067 | 2022-12-01 | 2022-11-27 | 2022-11-01 |  | 2023-01-01 | X | 2022-10-31 | 25985 | 2022-12-20 | X | Decline | - | - | X | No Response | - | - | X | No Response | - | - | X | 2022-10-31 | 15220 | 2022-12-01 | [8 empty] | Dawood | 15220 | 0 | 0 | 0 | 0 | 15220 | 0 | 0
115 | Non-DOT | BS209 | 1312009 | Naperville | Anna Yordan | Survey, SUE Level B | 2022-11-01 | 2022-11-03 | 2022-11-10 | 2022-12-02 | 2022-11-04 | 2022-11-07 | 2022-11-07 | 2022-11-10 | 2022-11-10 | X | 168777000.A.068 | 2022-12-02 | 2022-11-27 | 2022-11-01 |  | 2023-01-01 | X | 2022-11-03 | 14600 | 2022-12-08 | X | Declined | - | - | X | No Response | - | - | X | No Response | - | - | X | 2022-11-04 | 7770 | 2022-12-01 | [8 empty] | Dawood | 7770 | 0 | 0 | 0 | 0 | 7770 | 0 | 0
116 | CRA | RS1102 | 1011993 | Ludlow | Alban Shehu | Survey, SUE Level B | 2022-11-04 | 2022-11-08 | 2022-11-15 | 2022-12-06 | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | 2022-11-10 | X | 168777000.A.066 | 2022-12-06 | 2022-11-28 | 2022-11-01 |  | 2023-01-01 | X | 2022-11-08 | 12750 | 6 wks from NTP | X | 2022-11-07 | 7900 | 2022-12-06 | X | No Response | - | - | X | No Response | - | - | X | No Response | - | - | [8 empty] | DLZ | 7900 | 0 | 0 | 7900 | 0 | 0 | 0 | 0
102 | Non-DOT | MR1940 | 1211899 | Wheeling | Mark Stanley | Survey, SUE Level B, Geotechnical | 2022-09-29 | 2022-10-03 | 2022-10-12 | 2022-11-03 | 2022-10-10 | 2022-10-11 | 2022-10-11 | 2022-10-20 | 2022-10-20 | X | 168777000.A.059 | 2022-12-08 | 2022-11-29 | 2022-11-01 |  | 2023-01-01 | X | 2022-10-03 | 16140 | 2022-11-02 | X | 2022-10-03 | 49800 | 2022-11-03 | X | 2022-10-04 | 41000 | 2022-11-03 | X | No Response | - | - | X | 2022-10-03 | 34250 | 2022-11-23 | [8 empty] | DLZ | 49800 | 0 | 0 | 49800 | 0 | 0 | 0 | 0
109 | Non-DOT | MR1926 | 1211932 | Rosemont | Anna Yordan | Survey, SUE Level B, Geotechnical | 2022-10-12 | 2022-10-17 | 2022-10-25 | 2022-11-30 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-31 | 2022-10-31 | X | 168777000.A.063 | 2022-12-16 | 2022-12-19 | 2022-11-01 |  | 2023-01-01 |  |  |  |  | X | Decline |  |  | X | 2022-10-21 | 72800 | 2022-11-30 | X | 2022-10-20 | 89605 | 2022-12-21 | X | No Response | [10 empty] | Helix | 72800 | 72800 | 0 | 0 | 0 | 0 | 0 | 0
31 | Non-DOT | VW189 | 1210662 | Summit | Anna Yordan | Survey, SUE Level B, Geotechnical | 2021-09-23 | 2021-09-27 | 2021-10-25 | 2021-11-01 | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2021-10-11 | 2021-10-11 | X | 168777000.1.878 | 2021-11-08 | 2022-11-08 | 2022-11-08 |  | 2023-01-01 |  |  |  |  | X | 2021-09-28 | 130300 | 2021-11-01 |  |  |  |  | X | Declined | [14 empty] | DLZ | 130300 | 0 | 0 | 130300 | 0 | 0 | 0 | 0
124 | DOT | N15837 | 1211966 | Rockford | Randy Castellon | SUE Level A | 2022-10-11 | 2022-10-14 | 2022-11-15 | 2022-11-15 | 2022-10-20 | 2022-10-21 | 2022-10-26 | 2022-10-26 | 2022-10-11 | X | 168777000.A.073 | 2022-11-16 | 2022-12-13 | 2022-11-16 | N | 2023-01-01 | X | Decline |  |  | X | Decline |  |  | X | 2022-10-18 | 37800 | 2022-11-16 | X |  |  |  | N | [11 empty] | Helix | 37800 | 37800 | 0 | 0 | 0 | 0 | 0 | 0
35 | Non-DOT | BS260 | 1210721 | Lake Zurich | Anna Yordan | Survey, SUE Level B | 2021-10-14 | 2021-10-18 | 2021-10-25 | 2021-11-17 | 2021-10-19 | 2021-10-20 | 2021-10-20 | 2021-10-27 | 2021-10-27 | X | 168777000.1.882 | 2021-11-17 | 2022-11-23 | 2022-11-23 |  | 2023-01-01 |  |  |  |  | X | Declined |  |  | X | 2021-10-18 | 29800 | 2021-11-17 | X | Declined | [14 empty] | Helix | 29800 | 29800 | 0 | 0 | 0 | 0 | 0 | 0
39 | CRA | RS926 | 1010733 | Homewood | Matt Crescenti |  | 2021-10-22 | 2021-10-26 | 2021-11-02 | 2021-11-23 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-11-02 | 2021-11-02 | X | 168777000.A.012 | 2021-11-23 | 2022-11-28 | 2022-11-28 |  | 2023-01-01 | X | 2021-10-27 | 21300 | - | - | - | - | - | X | 2021-10-27 | 23250 | 2021-11-23 | X | Declined | - | - | [12 empty] | Helix | 23250 | 23250 | 0 | 0 | 0 | 0 | 0 | 0
125 | CRA | RS960 | 1011937 | Lyndon | Randy Castellon | Survey | 2022-10-25 | 2022-10-27 | 2022-11-04 | 2022-11-28 | 2022-10-28 | 2022-10-28 | 2022-10-28 | 2022-11-01 | 2022-11-01 | X | 168777000.A.074 | 2022-11-28 | 2022-11-28 | 2022-11-28 |  | 2023-01-01 | [8 empty] | X | 2022-10-27 | 5000 | 2022-11-28 | [16 empty] | Helix | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0
123 | DOT | N15332 | 1211954 | Rockford | Randy Castellon | SUE Level A | 2022-10-11 | 2022-10-14 | 2022-10-25 | 2022-11-30 | 2022-10-17 | 2022-10-19 | 2022-10-20 | 2022-10-25 | 2022-10-25 | X | 168777000.A.072 | 2022-11-30 | 2022-11-17 | 2022-11-30 | N | 2023-01-01 | X | Decline | - | - | X | 2022-10-19 | 21500 | 2022-11-30 | x | 2022-10-18 | 19850 | 2022-11-30 | X | No Response | - | - | x | No Response | - | - | [8 empty] | DLZ | 21500 | 0 | 0 | 21500 | 0 | 0 | 0 | 0
33 | Non-DOT | BS208 | 1410691 | Joliet | Mitch Pohlman | Survey, SUE Level B | 2021-10-13 | 2021-10-15 | 2021-10-22 | 2021-11-12 | 2021-10-21 | 2021-10-25 | 2021-10-25 | 2021-10-27 | 2021-10-27 | X | 168777000.A.013 | 2021-12-03 | 2022-12-06 | 2022-12-06 |  | 2023-01-01 |  | 2021-10-15 | 40125 | 2021-11-12 |  | 2021-10-22 | 105600 | 2021-12-28 |  |  |  |  | X | 2021-10-17 | 113517 | 2021-12-03 | [12 empty] | Millennia | 113517 | 0 | 113517 | 0 | 0 | 0 | 0 | 0
120 | CRA | RS1093 | 1012008 | Ottawa | Mark Stanley | SUE Level A | 2022-11-11 | 2022-11-15 | 2022-11-29 | 2022-12-20 | 2022-11-16 | 2022-12-29 | 2022-11-30 | 2022-11-30 | 2022-11-30 | X | 168777000.A.079 | 2022-12-20 | 2022-12-20 | 2022-12-20 |  | 2023-01-01 | X | Decline |  |  | X | 2022-11-14 | 13400 | 2022-12-20 | X | 2022-11-15 | 11350 | 2022-12-20 | X | No Response | - | - | X | No Response | - | - | [8 empty] | Helix | 11350 | 11350 | 0 | 0 | 0 | 0 | 0 | 0
118 | CRA | RS1098 | 1011934 | Grant Park | Marissa LaPorte | Survey, SUE Level B | 2022-11-07 | 2022-11-09 | 2022-11-16 | 2022-12-07 | 2022-11-10 | 2022-11-11 | 2022-11-14 | 2022-11-30 | 2022-11-30 | X | 168777000.A.077 | 2022-12-21 | 2022-12-19 | 2022-12-21 |  | 2023-01-01 | X | 2022-11-09 | 12750 | 6 wks from NTP | X | 2022-11-08 | 5700 | 2022-12-07 | X | 2022-11-09 | 3350 | 2022-12-07 | X | No Response | - | - | X | 2022-11-09 | 5700 | 2022-12-07 | [8 empty] | Dawood | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 0
119 | CRA | RS1099 | 1012003 | Paxton | Marissa LaPorte | Survey, SUE Level B | 2022-11-07 | 2022-11-09 | 2022-11-16 | 2022-12-07 | 2022-11-10 | 2022-11-11 | 2022-11-14 | 2022-11-30 | 2022-11-30 | X | 168777000.A.078 | 2022-12-21 | 2022-12-19 | 2022-12-21 |  | 2023-01-01 | X | no response | - | - | X | 2022-11-08 | 8500 | 2022-12-07 | X | 2022-11-09 | 5500 | 2022-12-07 | X | No response | 14950 | 2022-12-12 | X | 2022-11-09 | 8815 | 2022-12-07 | [8 empty] | Dawood | 8815 | 0 | 0 | 0 | 0 | 8815 | 0 | 0
122 | Non-DOT | BS388 | 1212044 | Rockford | Taylor Lierow | Survey | 2022-11-14 | 2022-11-16 | 2022-11-22 | 2022-12-16 | 2022-11-18 | 2022-11-18 | 2022-11-21 | 2022-11-22 | 2022-11-22 | X | 168777000.A.075 | 2022-12-23 | 12/27/2022 1/20/2023 | 2022-12-23 | N | 2023-01-01 | X | 2022-11-17 | 18550 | 2023-01-17 | X | 2022-11-16 | 54500 | 2022-12-20 | X | 2022-11-16 | 25800 | 2022-12-23 | X | Decline | - | - | X | No Response | - | - | [8 empty] | Helix | 25800 | 25800 | 0 | 0 | 0 | 0 | 0 | 0
126 | CRA | RS1091 | 1011994 | Bloomington | Alban Shehu | Survey, SUE Level B | 2022-11-16 | 2022-11-18 | 2022-12-02 | 2022-12-23 | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2022-11-22 | 2022-11-22 | X | 168777000.A.071 | 2022-12-23 | 2022-12-19 | 2022-12-23 |  | 2023-01-01 | X | No Response | - | - | X | 2022-11-17 | 17200 | 2022-12-23 | X | No Response | - | - | X | No Response | - | - | X | No Response | - | - | [8 empty] | DLZ | 17200 | 0 | 0 | 17200 | 0 | 0 | 0 | 0
121 | Non-DOT | BS402 | 1412040 | Park Forest | Alban Shehu | Survey, SUE Level B | 2022-11-15 | 2022-11-17 | 2022-11-24 | 2022-12-15 | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2022-11-22 | 2022-11-22 | X | 168777000.A.069 | 2022-12-27 | 2022-12-28 | 2022-12-27 |  | 2023-01-01 | X | 2022-11-17 | 21300 | 2022-01-13 | X | Decline | - | - | X | 2022-11-18 | 16100 | 2022-12-27 | X | No Response | - | - | X | No Response | - | - | [8 empty] | Helix | 16100 | 16100 | 0 | 0 | 0 | 0 | 0 | 0
133 | CRA | RS1031 | 102169 | Binghampton | Marissa LaPorte | Survey, SUE Level B | 2022-11-28 | 2022-11-30 | 2022-12-07 | 2023-01-04 | 2022-12-01 | 2022-12-02 | 2022-12-02 | 2022-12-07 | 2022-12-07 | X | 168777000.A.081 | 2023-01-04 | 2023-01-04 | 2022-12-30 |  | 2023-01-01 | X | declined |  |  | X | 2022-11-30 | 8500 | 2023-01-04 | X |  |  |  | X | Declined |  |  | X | 2022-11-30 | 9985 | 2022-01-13 | [8 empty] | DLZ | 8500 | 0 | 0 | 8500 | 0 | 0 | 0 | 0
134 | CRA | RS944 | 1011916 | Arlington Heights | Marissa LaPorte | Survey, SUE Level B | 2022-12-01 | 2022-12-05 | 2022-12-13 | 2023-01-10 | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2022-12-08 | X | 168777000.A.084 | 2023-01-10 | 2023-01-10 | 2022-12-30 |  | 2023-01-01 |  |  |  |  | X | 2022-01-05 | 13100 | 2023-01-10 | X | 2022-12-06 | 5750 | 2023-01-10 |  |  |  |  | X | 2022-12-05 | 11500 | 2023-01-10 | [8 empty] | Helix | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0
110 | Non-DOT | VW50 | 1211924 | Rosemont | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2022-10-12 | 2022-10-17 | 2022-10-25 | 2023-01-06 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-11-01 | 2022-11-01 | X | 168777000.A.065 | 2023-01-11 | 2023-01-26 | 2022-12-30 |  | 2023-01-01 | [5 empty] | Decline |  |  |  | 2022-10-17 | 136140 | 2023-01-20 | X | 2022-10-18 | 221610 | 2022-01-06 | X | No response | [10 empty] | Millennia | 221610 | 0 | 221610 | 0 | 0 | 0 | 0 | 0
117 | Non-DOT | BS631 | 1312007 | Geneva | Mark Stanley | Survey, SUE Level B, Geotechnical | 2022-11-08 | 2022-11-16 | 2022-11-28 | 2022-12-30 | 2022-11-15 | 2022-11-18 | 2022-11-18 | 2022-11-22 | 2022-11-22 | X | 168777000.A.070 | 2023-01-13 | 2023-01-17 | 2022-12-30 |  | 2023-01-01 | X | 2022-11-14 | 69885 | 2023-02-17 | X | 2022-11-11 | 160750 | 2023-02-20 | X | 2022-11-10 | 75500 | 2023-01-13 | X | No Response | - | - | X | 2022-11-10 | 79600 | 2022-12-30 | [8 empty] | Helix | 75500 | 75500 | 0 | 0 | 0 | 0 | 0 | 0
142 | DOT | N13606 | 1211967 | Stockton | Randy Castellon | SUE Level A | 2022-11-08 | 2022-11-11 | 2022-11-17 | 2022-12-13 | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2022-11-22 | 2022-11-22 | X | 168777000.A.089 | 2022-12-23 | 2023-01-27 | 2022-12-31 | N | 2023-01-01 | X | Declined |  |  | X | Declined |  |  | X | 2022-11-15 | 73440 | 2022-12-23 | X | No Resposne |  |  | X | No Response | [10 empty] | Helix | 73440 | 73440 | 0 | 0 | 0 | 0 | 0 | 0
130 | Non-DOT | BS249 | 1212063 | Marengo | Mitch Pohlman | Survey, SUE Level B | 2022-11-30 | 2022-12-02 | 2022-12-14 | 2023-01-11 | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-14 | 2022-12-14 | X | 168777000.A.086 | 2023-01-11 | 2023-01-11 | 2022-12-31 |  | 2023-01-01 |  |  |  |  | X | 2022-12-02 | 42600 | 2023-01-11 |  | 2022-12-06 | 27000 | 2022-01-30 | [16 empty] | DLZ | 42600 | 0 | 0 | 42600 | 0 | 0 | 0 | 0
127 | CRA | RS1081 | 1011925 | Crest Hill | Alban Shehu | Survey, SUE Level B | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2023-01-02 | 2022-11-29 | 2022-11-29 | 2022-11-30 | 2022-11-30 | 2022-11-30 | X | 168777000.A.080 | 2023-01-02 | 2023-01-11 | 2023-01-23 | N | 2023-01-01 | X | 2022-11-28 | 25195 | 4 wks NTP | X | 2022-11-28 | 54500 | 2023-01-02 | X | 2022-11-29 | 29970 | 2023-01-20 | X | No Response | - | - | X | 2022-11-28 | 27000 | 2023-01-09 | [8 empty] | Atlas | 25195 | 0 | 0 | 0 | 25195 | 0 | 0 | 0
132 | CRA | RS1079 | 1011803 | Melrose Park | Marissa LaPorte | Survey, SUE Level B | 2022-11-28 | 2022-11-30 | 2022-12-07 | 2023-01-04 | 2022-12-01 | 2022-12-02 | 2022-12-02 | 2022-12-07 | 2022-12-07 | X | 168777000.A.082 | 2023-01-04 | 2022-12-19 | 2023-01-23 | N | 2023-01-01 |  |  |  |  | X | 2022-11-30 | 3250 | 2023-01-04 | [20 empty] | DLZ | 3250 | 0 | 0 | 3250 | 0 | 0 | 0 | 0
135 | CRA | MR1966 | 3212113 | Palatine | Conner Chamernik | Survey, SUE Level B | 2022-12-03 | 2022-12-06 | 2022-12-12 | 2023-01-10 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-14 | 2022-12-14 | X | 168777007.Z.002 | 2023-01-10 | 2023-01-11 | 2023-01-23 | N | 2023-01-01 | X | 2022-11-06 | 4850 | 6 weeks NTP | X | 2022-12-06 | 6900 | 2023-01-10 | X | 2022-12-06 | 4250 | 2023-01-10 |  |  |  |  | X | 2022-12-04 | 11000 | [9 empty] | DLZ | 6900 | 0 | 0 | 6900 | 0 | 0 | 0 | 0 | 2020-06-18
139 | CRA | MR1965 | 3212117 | Mt Prospect | Brady Lane | Survey, SUE Level B | 2022-12-03 | 2022-12-06 | 2022-12-12 | 2023-01-10 | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-14 | 2022-12-14 | X | 168777000.Z.737 | 2023-01-12 | 2023-01-12 | 2023-01-23 | N | 2023-01-01 | X | 2022-12-06 | 10600 | 6 weeks NTP | X | 2022-12-06 | 10500 | 2023-01-10 | [8 empty] | X | 2022-12-04 | 10000 | 2023-01-10 | [8 empty] | DLZ | 10500 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 1909-11-08
131 | DOT | N13676 | 1212065 | Richmond | Tim Purtell | Survey, SUE Level B | 2022-11-18 | 2022-11-22 | 2022-11-30 | 2023-01-13 | 2022-11-22 | 2022-11-22 | 2022-11-28 | 2022-11-30 | 2022-11-30 | X | 168777000.A.576 | 2023-01-13 | 2023-01-13 | 2023-01-23 | N | 2023-01-01 | X |  | 19030 | 3 weeks NTP | X | Declined |  |  | X | Declined |  |  | X |  | 6220 | 2022-01-13 | [12 empty] | Millennia | 6220 | 0 | 6220 | 0 | 0 | 0 | 0 | 0 | 1947-12-29
143 | CRA | RS959 | 1011935 | Geneseo | Marissa LaPorte | Survey, SUE Level B | 2022-12-09 | 2022-12-13 | 2022-12-20 | 2023-01-18 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2022-12-19 | 2022-12-20 | X | 168777007.Z.500 | 2023-01-18 | 2023-01-19 | 2023-01-23 | N | 2023-01-01 | X | declined |  |  | X | 2022-12-12 | 15950 | 2023-01-18 | X | 2022-12-14 | 12270 | 2023-01-18 | [16 empty] | Helix | 12270 | 12270 | 0 | 0 | 0 | 0 | 0 | 0 | 1961-08-07
129 | Non-DOT | BS340 | 1212067 | McHenry | Camille Corbi | Survey, SUE Level B | 2022-11-28 | 2022-12-01 | 2022-12-08 | 2023-01-13 | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2022-12-08 | 2022-12-08 | X | 168777000.A.085 | 2023-01-20 | 2023-01-23 | 2023-02-01 | N | 2023-01-01 |  |  |  |  | X | Declined |  |  | X | 2022-12-01 | 21000 | 2023-01-20 | X | Response |  |  | X | 2022-11-29 | 21080 | 2023-01-13 | [8 empty] | Dawood | 21080 | 0 | 0 | 0 | 0 | 21080 | 0 | 0 | 1906-11-04
141 | CRA | RS1119 | 1012097 | Fox Lake | Marissa LaPorte | Survey, SUE Level B | 2022-12-07 | 2022-12-09 | 2022-12-16 | 2023-01-13 | 2022-12-12 | 2022-12-13 | 2022-12-13 | 2022-12-13 | 2022-12-13 | X | 168777007.Z.501 | 2023-01-20 | 2023-01-16 | 2023-02-01 | N | 2023-01-01 |  |  |  |  | X | declined |  |  | X | 2022-12-12 | 6800 | 2023-01-20 |  |  |  |  | X | 2022-12-08 | 16775 | 2023-02-01 | [8 empty] | Helix | 6800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 1944-08-16 | 6900 | 7590
128 | Non-DOT | BS187 | 1212064 | Arlington Heights | Anna Yordan | Survey, SUE Level B | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | 2022-12-06 | 2022-12-06 | X | 168777000.A.083 | 2023-01-27 | 2023-01-26 | 2023-02-01 | N | 2023-01-01 | X | 2022-11-28 | 68985 | 2023-01-16 | X | Declined |  |  | X | 2022-11-29 | 68000 | 2023-02-06 | X | Declined |  |  | X | 2022-11-28 | 44000 | 2023-01-15 | X | 2023-11-28 | 198588.4 | 2023-01-06 |  |  |  |  | Dawood | 44000 | 0 | 0 | 0 | 0 | 44000 | 0 | 0
137 | CRA | MR1963 | 3212101 | Rockford | Alban Shehu | Survey | 2022-12-05 | 2022-12-07 | 2022-12-14 | 2023-01-11 | 2022-12-08 | 2022-12-09 | 2022-12-12 | 2023-01-05 | 2023-01-06 | X | 168777007.Z.003 | 2023-01-27 | 2023-01-27 | 2023-02-01 | N | 2023-01-01 | X | 2022-12-07 | 7530 | 6 wks from NTP | X | 2022-12-06 | 10800 | 2023-01-11 | X | 2022-12-07 | 3600 | 2023-01-13 | X | No Response | - | - | X | 2022-12-07 | 8500 | 2023-01-11 | [8 empty] | Helix | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0
136 | CRA | RS1123 | 1212088 | Wauconda | Alban Shehu | Survey | 2022-12-05 | 2022-12-07 | 2022-12-14 | 2023-01-11 | 2022-12-08 | 2022-12-09 | 2022-12-12 | 2023-01-09 | 2023-01-09 | X | 168777007.Z.004 | 2023-01-30 | 2023-02-01 | 2023-02-01 | N | 2023-01-01 | X | 2022-12-07 | 17530 | 7 wks from NTP | X | Declined | - | - | X | 2023-12-08 | 18350 | 2023-01-30 | X | No Response | - | - | X | 2022-12-07 | 25000 | 2023-01-25 | [8 empty] | Atlas | 17530 | 0 | 0 | 0 | 17530 | 0 | 0 | 0
144 | Non-DOT | MR1984 | 1412200 | Kankakee | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2023-01-05 | 2023-01-09 | 2023-01-18 | 2023-02-08 | 2023-01-15 | 2023-01-16 | 2023-01-16 | 2023-01-17 | 2023-02-17 | X | 168777007.Z.006 | 2023-02-08 | 2023-04-18 | 2023-02-01 | N | 2023-01-01 | [5 empty] | 2023-01-10 | 44200 | 2023-01-10 | X` | 2023-01-11 | 22500 | 2023-02-08 | [16 empty] | Helix | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0
145 | CRA | RS1124 | 1212090 | Volo | Mark Stanley | Survey, SUE Level B | 2023-01-11 | 2023-01-13 | 2023-01-23 | 2023-02-14 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-19 | 2023-01-19 | X | 168777007.Z.507 | 2023-02-14 | 2023-02-07 | 2023-02-01 | N | 2023-01-01 | X | 2023-01-13 | 7200 | 2023-02-20 | X | 2023-01-12 | 8700 | 2023-02-14 | X | 2023-01-13 | 2500 | 2023-02-14 | X | No Response |  |  | X | 2023-01-14 | 5000 | 2023-02-14 | X | 2023-01-13 | 20029.15 | 2023-02-14 |  |  |  |  | Helix | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0
150 | DOT | N15164 | 1212276 | Sterling | Randy Castellon | SUE Level A | 2023-01-19 | 2023-01-23 | 2023-01-27 | 2023-02-17 | 2023-01-23 | 2023-01-25 | 2023-01-25 | 2023-01-30 | 2023-01-30 | X | 168777007.Z.008 | 2023-02-17 | 2023-02-14 | 2023-02-01 | N | 2023-01-01 | X | NO RESPONSE | - | - | X | 2023-01-23 | 16300 | 2023-02-17 | X | No response |  |  | X | No response |  |  | X | No Response | [10 empty] | DLZ | 16300 | 0 | 0 | 16300 | 0 | 0 | 0 | 0
147 | Non-DOT | BS111 | 1212254 | Northbrook | Anna Yordan | Survey, SUE Level B, Geotechnical | 2023-01-18 | 2023-01-20 | 2023-01-27 | 2023-02-17 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-30 | X | 168777007.Z.009 | 2023-02-20 | 2023-02-20 | 2023-03-01 | N | 2023-01-01 | X |  |  |  | X | Declined |  |  | X | 2023-01-21 | 48500 | 2023-02-17 | X | No response |  |  | X | 2023-01-20 | 77075 | 2023-02-22 | X | 2023-01-23 | 51100 | 2023-03-03 |  |  |  |  | Helix | 48500 | 48500 | 0 | 0 | 0 | 0 | 0 | 0
148 | CRA | RS943 | 1011915 | Arlington Heights | Marissa LaPorte | Survey, SUE Level B | 2023-02-02 | 2023-02-06 | 2023-02-13 | 2023-03-06 | 2023-02-07 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-09 | X | 168777007.Z.510 | 2023-03-06 | 2023-03-06 | 2023-03-01 | N | 2023-01-01 |  |  |  |  | X | 2023-02-06 | 10790 | 2023-03-06 | X | 2023-02-06 | 6800 | 2023-03-06 | X | 2023-02-06 | 16520 | 2023-03-06 | [12 empty] | DLZ | 10790 | 0 | 0 | 10790 | 0 | 0 | 0 | 0
101 | CRA | RS991 | 1010976 | Rolling Meadows | Anna Yordan | Survey, SUE Level B, Geotechnical | 2023-01-30 | 2023-02-01 | 2023-02-10 | 2023-03-03 | 2023-02-03 | 2023-02-03 | 2023-02-06 | 2023-02-14 | 2023-02-14 | X | 168777007.Z.513 | 2023-03-07 | 2023-03-17 | 2023-03-01 | N | 2023-01-01 | X | 2023-02-02 | 42720 | 2023-03-17 | X | 2023-02-01 | 76850 | 2023-03-21 | X | 2023-02-01 | 47200 | 2023-03-03 | X | 2023-02-01 | 47230 | 2023-03-03 | X | 2023-02-02 | 42942 | 2023-03-10 | N/A | [7 empty] | Millennia | 47230 | 0 | 47230 | 0 | 0 | 0 | 0 | 0
146 | Non-DOT | BS455 | 1412328 | Sun River Terrace | Mark Stanley | Survey, SUE Level B | 2023-02-07 | 2023-02-09 | 2023-02-17 | 2023-03-13 | 2023-02-09 | 2023-02-10 | 2023-02-10 | 2023-02-21 | 2023-02-21 | X | 168777007.Z.011 | 2023-03-15 | 2023-03-15 | 2023-03-01 | N | 2023-01-01 | X | 2023-02-09 | 21142 | 2023-03-10 | X | 2023-02-09 | 34300 | 2023-03-17 | X | 2023-02-09 | 9000 | 2023-03-13 | X | No Response | - | - | X | No Response | - | - | X | 2023-02-09 | 20972 | 2023-03-15 |  |  |  |  | Accurate | 20972 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | Non-DOT | BS187 | 1212064 | Arlington Heights | Anna Yordan | Survey | 2023-02-21 | 2023-02-22 | 2023-02-27 | 2023-03-15 | 2023-02-22 | 2023-02-22 | 2023-02-22 | 2023-02-27 | 2023-02-27 | X | 168777007.Z.022 | 2023-03-15 | 2023-03-15 | 2023-03-01 | N | 2023-01-01 | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | X | 2023-02-21 | 2000 | 2023-03-15 | N/A | [7 empty] | Dawood | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0
161 | Non-DOT | MR1899 | 1211570 | Franklin Park | Mitch Pohlman | Geotechnical, SUE A | 2023-01-17 | 2023-01-21 | 2023-01-25 | 2023-03-17 | 2023-01-25 | 2023-01-25 | 2023-02-25 | 2023-02-06 | 2023-02-06 | X | 168777007.Z.014 | 2023-03-17 | 2023-03-17 | 2023-03-01 | N | 2023-01-01 | [8 empty] | X | 2023-01-21 | 22250 | 2023-03-17 | [16 empty] | Helix | 22250 | 22250 | 0 | 0 | 0 | 0 | 0 | 0
152 | CRA | RS1136 | 1212383 | Bensenville | Alban Shehu | Survey, SUE Level B | 2023-02-20 | 2023-02-22 | 2023-03-01 | 2023-03-22 | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-02-26 | 2023-02-27 | X | 168777007.Z.512 | 2023-03-22 | 2023-03-14 | 2023-03-01 | N | 2023-01-01 | X | 2023-02-22 | 10550 | 15 days from NTP | X | 2023-02-21 | 17500 | 2023-03-22 | X | 2023-02-22 | 10700 | 2023-03-22 | X | No Response | - | - | X | 2023-02-21 | 18560 | 2023-03-22 | X | 2023-02-22 | 26238.8 | 2023-03-22 |  |  |  |  | Helix | 10700 | 10700 | 0 | 0 | 0 | 0 | 0 | 0
151 | Non-DOT | BS520 | 1312367 | Woodridge | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2023-02-02 | 2023-02-07 | 2023-02-17 | 2023-03-10 | 2023-02-22 | 2023-02-22 | 2023-02-22 | 2023-02-28 | 2023-02-28 | x | 168777007.Z.015 | 2023-03-24 | 2023-03-24 | 2023-03-01 | N | 2023-01-01 | [5 empty] | 2023-02-06 | 82850 | 2023-03-17 |  | 2023-02-07 | 49500 | 2023-03-10 | X | 2023-02-07 | 30550 | 2023-03-17 | [12 empty] | MIllennia | 30550 | 0 | 30550 | 0 | 0 | 0 | 0 | 0
155 | CRA | RS928/RS668 | 103074 | Burnham | Marissa LaPorte | Survey, SUE Level B | 2023-02-22 | 2023-02-24 | 2023-03-03 | 2023-03-24 | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-06 | 2023-03-06 | X | 168777007.Z.516 | 2023-03-24 | 2023-03-22 | 2023-03-01 | N | 2023-01-01 |  |  |  |  | X | 2023-02-23 | 15700 | 2023-03-24 | X | 2023-02-24 | 9000 | 2023-03-24 | X | Declined | [14 empty] | DLZ | 15700 | 0 | 0 | 15700 | 0 | 0 | 0 | 0
153 | CRA | RS500 | 102083 | Deer Park | Alban Shehu | Survey, SUE Level B, Geotechnical | 2023-02-21 | 2023-02-23 | 2023-03-02 | 2023-03-23 | 2023-02-24 | 2023-02-24 | 2023-02-27 | 2023-03-07 | 2023-03-08 | X | 168777007.Z.517 | 2023-03-29 | 2023-03-29 | 2023-03-01 | N | 2023-01-01 | X | 2023-02-23 | 35100 | 5 wks from NTP | X | 2023-02-23 | 65050 | 3/29/2023 5 wks NTP | X | 2023-02-22 | 30900 | 3/22/2023 TBD Geotech | X | No Response | - | - | X | No Response | - | - | X | 2023-02-22 | 67458 | 2023-04-28 |  |  |  |  | Helix | 30900 | 30900 | 0 | 0 | 0 | 0 | 0 | 0
168 | DOT | SC20527 | 1411266 | Joliet | Randy Castellon | SUE Level A | 2022-04-01 | 2022-04-04 | 2022-09-13 | - | 2022-04-06 | 2022-04-08 | 2022-04-09 | 2022-09-12 | 2022-09-13 | X | 168777007.Z.005 | 2022-09-26 | 2022-12-05 | 2023-04-01 | N | 2023-01-01 | N |  |  |  | X | 2022-04-04 | 32650 | 2-3 wks NTP | N |  |  |  | X | No Response |  |  | N | [11 empty] | DLZ | 32650 | 0 | 0 | 32650 | 0 | 0 | 0 | 0
169 | DOT | N14915 | 1211681 | Crystal Lake | Randy Castellon | Survey | 2023-02-03 | 2023-02-07 | 2023-02-10 | 2023-03-03 | 2023-02-07 | 2023-02-08 | 2023-02-08 | 2023-02-09 | 2023-02-09 | X | 168777007.Z.524 | 2023-03-03 | 2023-02-27 | 2023-04-01 | N | 2023-01-01 | X | 2023-02-07 | 6900 | 25 days NTP | X | 2023-02-03 | 10400 | 2023-03-03 | X | 2023-02-07 | 6900 | 2023-03-02 | X | No Response |  |  | X | 2023-02-17 | 8250 | 2023-02-17 | X | No response | [6 empty] | DLZ | 10400 | 0 | 0 | 10400 | 0 | 0 | 0 | 0
158 | CRA | RS1138 | 1010016 | Oak Brook | Marissa LaPorte | Survey, SUE Level B | 2023-03-02 | 2023-03-06 | 2023-03-13 | 2023-04-03 | 2023-03-08 | 2023-03-09 | 2023-03-13 | 2023-03-13 | 2023-03-13 | X | 168777007.Z.019 | 2023-04-03 | 2023-03-31 | 2023-04-01 | N | 2023-01-01 | - | - | - | - | X | 2023-03-06 | 9600 | 2023-04-03 | X | 2023-03-06 | 4800 | 2023-04-03 | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  |  | Helix | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
162 | CRA | RS1144 | 1212430 | Lake Villa | Madie Roman | Survey, SUE Level B | 2023-03-03 | 2023-03-08 | 2023-03-15 | 2023-04-05 | 2023-03-10 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-03-14 | X | 168777007.Z.518 | 2023-04-05 | 2023-04-05 | 2023-04-01 | N | 2023-01-01 | X | 2023-03-08 | 6800 | 3 wks from NTP | X | 2023-03-06 | 5900 | 2023-04-05 | X | 2023-03-08 | 4000 | 2023-04-05 | X | 2023-03-09 | 9890 | 2023-04-05 | X | 2023-03-07 | 5460 | 2023-04-05 | X | 2023-03-06 | 19431.7 | 2023-04-06 |  |  |  |  | Helix | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
163 | CRA | RS1128 | 1412438 | Momence | Madie Roman | Survey, SUE Level B | 2023-03-07 | 2023-03-10 | 2023-03-17 | 2023-04-07 | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-20 | 2023-03-20 | X | 168777007.Z.523 | 2023-04-10 | 2023-04-17 | 2023-04-01 | N | 2023-01-01 | X | 2023-03-10 | 8500 | 3 wks from NTP | X | 2023-03-09 | 13600 | 2023-04-07 | X | 2023-03-10 | 5880 | 2023-04-07 | X | No Response | - | - | X | 2023-03-09 | 13450 | 2023-04-07 | X | 2023-03-09 | 26033 | 2023-04-07 |  |  |  |  | Atlas | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 0
157 | Non-DOT | NBA10005440 | 1612421 | Machesney Park | Camille Corbi | Survey, SUE Level B, Geotechnical | 2023-02-28 | 2023-03-02 | 2023-03-07 | 2023-04-14 | 2023-03-03 | 2023-03-03 | 2023-03-06 | 2023-03-14 | 2023-03-14 | X | 168777007.Z.020 | 2023-04-14 | 2023-04-17 | 2023-04-01 | N | 2023-01-01 | N/A |  |  |  | X | 2023-03-03 | 80550 | 2023-04-14 | X | 2023-03-02 | 52000 | 4/14/2023 TBD Geotech | X | No Reponse |  |  | X | 2023-03-02 | 43750 | 24 days after NTP | N/A | [7 empty] | Helix | 52000 | 52000 | 0 | 0 | 0 | 0 | 0 | 0
159 | CRA | RS1142 | 1412418 | Frankfort | Alban Shehu | Survey, SUE Level B, Geotechnical | 2023-03-06 | 2023-03-08 | 2023-03-15 | 2023-04-05 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-14 | 2023-03-14 | X | 168777007.Z.021 | 2023-04-14 | 2023-04-14 | 2023-04-01 | N | 2023-01-01 | X | 2023-03-08 | 40440 | 5 wks from NTP | X | 2023-03-08 | 69100 | 2-3 wks NTP | X |  |  |  | X | No Response | - | - | X | 2023-03-08 | 46250 | 3 wks from NTP | X | 2023-03-08 | 61418.6 | 2023-03-29 |  |  |  |  | DLZ | 69100 | 0 | 0 | 69100 | 0 | 0 | 0 | 0
173 | Non-DOT | MR1984 | 1412200 | Kankakee | Mitch Pohlman | Survey, SUE Level B, Geotechnical | 2023-04-06 | 2023-04-10 | 2023-04-13 | 2023-04-20 | 2023-04-10 | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-12 | X | 168777007.Z.533 | 2023-04-20 | 2023-04-20 | 2023-05-01 | N | 2023-01-01 | N/A |  |  |  | N/A |  |  |  | X | 2023-04-10 | 2800 | 2023-04-20 | N/A |  |  |  | N/A |  |  |  | N/A | [7 empty] | Helix | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0
165 | CRA | RS988 | 1010960 | Hawthorn Woods | Alban Shehu | Survey, SUE Level B | 2023-03-31 | 2023-04-04 | 2023-04-11 | 2023-05-02 | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-11 | 2023-04-11 | X | 168777007.Z.525 | 2023-05-02 | 2023-04-28 | 2023-05-01 | N | 2023-01-01 | X | 2023-04-05 | 6100 | 3 wks from NTP | X | 2023-04-04 | 11250 | 2023-05-02 | X | 2023-04-04 | 6750 | 2023-05-02 | X | 2023-04-04 | 12980 | 2023-05-01 | X | No Response |  |  | X | 2023-04-04 | 19645.7 | 2023-05-02 |  |  |  |  | Helix | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0
171 | CRA | RS1151 | 1012573 | West Chicago | Madie Roman | Survey, SUE Level B | 2023-04-04 | 2023-04-06 | 2023-04-12 | 2023-05-03 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-03-17 | 2023-03-17 | X | 168777007.Z.528 | 2023-05-08 | 2023-05-03 | 2023-05-01 | N | 2023-01-01 | X | 2023-03-06 | 6400 | 3 wks from NTP | X | 2023-03-05 | 11700 | 2023-05-03 | X | 2023-04-05 | 4500 | 2023-05-03 | X | No Response | - | - | X | 2023-04-06 | 6300 | 2023-05-04 | X | 2023-04-04 | 23919.8 | 2023-05-03 |  |  |  |  | Helix | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
167 | DOT | N14359 | 1212385 | Barrington | Randy Castellon | Survey, SUE Level A/B | 2023-04-04 | 2023-04-06 | 2023-04-13 | 2023-05-04 | 2023-04-10 | 2023-04-10 | 2023-04-11 | 2023-04-17 | 2023-04-17 | X | 168777007.D.021 | 2023-05-12 | 2023-05-16 | 2023-05-01 | N | 2023-01-01 | X | Declined |  |  | X | 2023-04-11 | 38250 | 2023-05-08 | X | No Response |  |  | X | 2023-04-05 | 46690 | 2023-05-08 | X | 2023-04-07 | 25180 | 2023-05-19 | X | 2023-04-06 | 74302.8 | 2023-06-08 |  |  |  |  | Millennia | 46690 | 0 | 46690 | 0 | 0 | 0 | 0 | 0
166 | DOT | SC22186 | 1412627 | Morris | Eric Dina | SUE Level A | 2023-04-03 | 2023-04-05 | 2023-04-13 | 2023-05-04 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 2023-04-26 | 2023-04-27 | X | 168777007.Z.030 | 2023-05-19 | 2023-05-18 | 2023-05-01 | N | 2023-01-01 | X | No Response |  |  | X | 2023-04-04 | 13600 | 2023-05-04 | X | 2023-04-05 | 10000 | 2023-05-04 | X | No Response |  |  | X | Declined |  |  | X | 2023-04-05 | 18352 | 2023-04-25 |  |  |  |  | Helix | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
164 | Non-DOT | VW240/ VW241-1 | 1212584 | Niles | Mark Stanley | Survey, SUE Level A/B | 2023-04-03 | 2023-04-05 | 2023-04-14 | 2023-05-19 | 2023-04-06 | 2023-04-06 | 2023-04-06 | 2023-04-11 | 2023-04-11 | X | 168777007.Z.026 | 2023-05-23 | 2023-05-23 | 2023-05-01 | N | 2023-01-01 | X | 2023-04-05 | 39800 | 2023-05-05 | X | 2023-04-05 | 132000 | 2023-06-09 | X | 2023-04-05 | 72250 | 2023-05-19 | X | No Response |  |  | X | 2023-04-05 | 44810 | 2023-05-19 | X | 2023-04-05 | 97609.2 | 2023-05-19 |  |  |  |  | Atlas | 39800 | 0 | 0 | 0 | 39800 | 0 | 0 | 0
174 | Non-DOT | BS520 | 1312367 | Woodridge | Mitch Pohlman | Boundary Survey | 2023-04-13 | 2023-04-15 | 2023-05-01 | 2023-05-19 | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | 2023-05-04 | X | 168777007.Z.534 | 2023-05-24 | 2023-05-25 | 2023-05-01 | N | 2023-01-01 | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | X | 2023-04-27 | 8820 | 2023-05-19 | N/A |  |  |  | N/A | [7 empty] | Millennia | 8820 | 0 | 8820 | 0 | 0 | 0 | 0 | 0
170 | DOT | N13257 | 129256 | Elgin | Anna Yordan | Survey | 2023-04-19 | 2023-04-25 | 2023-05-02 | 2023-05-31 | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-05-02 | 2023-05-02 | X | 168777007.Z.031 | 2023-06-02 | 2023-05-30 | 2023-05-01 | N | 2023-01-01 |  |  |  |  | X | 2023-04-25 | 8800 | 2023-05-31 | [20 empty] | DLZ | 8800 | 0 | 0 | 8800 | 0 | 0 | 0 | 0
172 | Non-DOT | NBA10010269 | 1612618 | Belvidere | Camille Corbi | Survey, SUE Level B | 2023-04-24 | 2023-04-27 | 2023-05-04 | 2023-06-02 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-05-08 | 2023-05-08 | X | 168777007.Z.032 | 2023-06-05 | 2023-05-30 | 2023-06-01 | N | 2023-01-01 | N/A |  |  |  | X | 2023-04-25 | 20500 | 6/2/2023 (20 days from NTP) | X |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A | [7 empty] | DLZ | 20500 | 0 | 0 | 20500 | 0 | 0 | 0 | 0
160 | Non-DOT | BS588 | 1212413 | Cicero | Mark Stanley | Survey, SUE Level B, Geotechnical | 2023-03-07 | 2023-03-13 | 2023-04-14 | 2023-06-09 | 2023-04-06 | 2023-04-10 | 2023-04-10 | 2023-04-21 | 2023-04-21 | X | 168777007.Z.029 | 2023-06-16 | 2023-10-25 | 2023-06-01 | N | 2023-01-01 | X | 2023-03-13 | 220491 | 2023-07-05 | X | Declined |  |  | X | 2023-04-06 | 173500 | 2023-06-09 | X | No Response |  |  | X | 2023-03-11 | 274700 | 2023-05-09 | X | 2023-03-10 | 709137.6 | 2023-08-23 |  |  |  |  | Helix | 173500 | 173500 | 0 | 0 | 0 | 0 | 0 | 0
177 | Non-DOT | MR2027 | 1212818 | Rockford | Anna Yordan | Survey, SUE Level B | 2023-05-24 | 2023-05-24 | 2023-05-30 | 2023-06-20 | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-05-30 | X | 168777007.Z.037 | 2023-06-27 | 2023-06-19 | 2023-06-01 | N | 2023-01-01 |  |  |  |  | X | 2023-05-25 | 21750 | 2023-06-21 | [20 empty] | DLZ | 21750 | 0 | 0 | 21750 | 0 | 0 | 0 | 0
176 | Non-DOT | MR2027 | 1212818 | Rockford | Anna Yordan | Geotechnical | 2023-05-24 | 2023-05-25 | 2023-05-30 | 2023-06-27 | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-06-05 | 2023-06-05 | X | 168777007.Z.036 | 2023-07-25 | 2023-07-24 | 2023-06-01 | N | 2023-01-01 |  |  |  |  | X | 2023-05-25 | 12800 | 2023-06-27 | [20 empty] | DLZ | 12800 | 0 | 0 | 12800 | 0 | 0 | 0 | 0
178 | DOT | M13735 | 1212842 | Oak Lawn | Anna Yordan | SUE Level A | 2023-06-01 | 2023-06-02 | 2023-06-07 | 2023-06-21 | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-06-09 | X | 168777007.Z.035 | 2023-07-07 | 2023-07-06 | 2023-07-01 | N | 2023-01-01 |  |  |  |  | X | 2023-06-01 | 21900 | 10 business days from permit approval | [20 empty] | DLZ | 21900 | 0 | 0 | 21900 | 0 | 0 | 0 | 0
179 | CRA | RS1157 | 1412858 | Joliet | Madie Roman | Survey, SUE Level B | 2023-06-15 | 2023-06-19 | 2023-06-26 | 2023-07-10 | 2023-06-20 | 2023-06-21 | 2023-06-21 | 2023-06-26 | 2023-06-26 | X | 168777007.Z.039 | 2023-07-10 | 2023-07-10 | 2023-07-01 | N | 2023-01-01 | [8 empty] | X | 2023-06-19 | 19790 | 2023-07-10 | X | 2023-06-19 | 29620 | 2023-07-17 | [12 empty] | Helix | 19790 | 19790 | 0 | 0 | 0 | 0 | 0 | 0
175 | DOT | M12980 | 1212831 | LaGrange Park | Randy Castellon | SUE Level A | 2023-05-25 | 2023-05-31 | 2023-06-05 | 2023-06-21 | 2023-05-31 | 2023-05-31 | 2023-05-31 | 2023-06-26 | 2023-06-26 | X | 168777007.Z.038 | 2023-07-13 | 2023-07-06 | 2023-07-01 | N | 2023-01-01 | N/A | - | - | - | X | 2023-05-30 | 14600 | 6/23/2023 (15 days from NTP) | X | 2023-05-31 | 8250 | 2023-06-21 | N/A | - | - | - | N/A |  |  |  | N/A | [7 empty] | Helix | 8250 | [5 empty] | 0 | 0
180 | Non-DOT | BS361 | 1212906 | Round Lake | Camille Corbi | Survey, SUE Level B | 2023-06-28 | 2023-07-03 | 2023-07-10 | 2023-07-31 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-12 | 2023-07-12 | X | 168777007.Z.040 | 2023-08-02 | 2023-08-02 | 2023-07-01 | N | 2023-01-01 |  |  |  |  | X | 2023-06-29 | 39000 | 2023-07-31 | X` | 2023-07-03 | 20750 | 2023-07-31 | [16 empty] | Helix | 20750 | 20750 | 0 | 0 | 0 | 0 | 0 | 0
149 | DOT | N15837 | 1211966 | Rockford (Amendment) | Randy Castellon | SUE Level A | NA | NA | NA | NA | NA | NA | NA | 2023-07-11 | NA | NA | 168777007.X.501 | NA | NA | 2023-07-01 | N | 2023-01-01 | [8 empty] | NA | NA | 22000 | NA | [8 empty] | X | 2023-11-08 | 75797.9 | 2023-11-15 |  |  |  |  | Helix | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0
181 | CRA | RS1180 | 1012908 | St. Charles | Madie Roman | Survey, SUE Level B | 2023-07-13 | 2023-07-17 | 2023-07-21 | 2023-08-08 | 2023-07-18 | 2023-07-18 | 2023-07-19 | 2023-07-25 | 2023-07-25 | X | 168777007.Y.500 | 2023-08-08 | 2023-08-16 | 2023-08-01 | N | 2023-01-01 | [12 empty] | X | 2023-06-17 | 18840 | 2023-08-08 | [12 empty] | Millennia | 18840 | 0 | 18840 | 0 | 0 | 0 | 0 | 0
182 | CRA | RS1173 | 1012913 | Downers Grove | Marissa LaPorte | Survey, SUE Level B | 2023-07-17 | 2023-07-19 | 2023-07-26 | 2023-08-11 | 2023-07-20 | 2023-07-24 | 2023-07-24 | 2023-07-25 | 2023-07-25 | X | 168777007.Z.541 | 2023-08-11 | 2023-08-11 | 2023-08-01 | N | 2023-01-01 |  |  |  |  | X | 2023-07-19 | 17150 | 2023-08-11 | X | 2023-07-19 | 7950 | 2023-08-11 | X | 2023-07-19 | 18930 | 2023-08-11 | [12 empty] | DLZ | 17150 |  |  | 17150 |  |  | 0 | 0
184 | Non-DOT | MR2030 | 1213045 | Schaumburg | Mark Stanley | Survey, SUE Level B | 2023-08-16 | 2023-08-16 | 2023-08-18 | 2023-09-01 | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-17 | X | 168777007.Z.042 | 2023-09-01 | 2023-09-01 | 2023-08-01 | N | 2023-01-01 | [8 empty] | X | 2023-08-16 | 21500 | 2023-09-01 | [16 empty] | Helix | 21500 | 21500 | 0 | 0 | 0 | 0 | 0 | 0
183 | DOT | N16541 | 1213072 | Rockford | Randy Castellon | SUE Level A | 2023-07-13 | 2023-07-17 | 2023-08-28 | 2023-08-11 | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-08-24 | X | 168777007.X.004 | 2023-09-15 | 2023-10-03 | 2023-09-23 | N | 2023-01-01 | X | Declined |  |  | X | Declined |  |  | X | Declined |  |  | X | 2023-08-23 | 58383 | 2023-09-15 | [12 empty] | Millennia | 58383 | 0 | 58383 | 0 | 0 | 0 | 0 | 0
188 | TIMP | TP534 | 1113122 | Wilmington | Mitchell Pohlman | Easement Staking | 2023-09-13 | 2023-09-18 | 2023-09-22 | 2023-09-28 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-25 | 2023-09-25 | X | 168777008.Z.500 | 2023-09-28 | 2023-09-26 | 2023-10-01 | N | 2023-01-01 | [8 empty] | x | 2023-09-18 | 3000 | 2023-09-28 | [16 empty] | Helix | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0
192 | DOT | N13592 | 1212874 | Johnsburg | Tim Purtell | SUE Level A | 2023-09-15 | 2023-09-19 | 2023-09-22 | 2023-10-13 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-26 | 2023-09-26 | X | 168777007.X.005 | 2023-10-13 | 2023-10-09 | 2023-10-01 | N | 2023-01-01 | [8 empty] | X | 2023-09-19 | 17300 | [17 empty] | Helix | 17300 | 17300 | 0 | 0 | 0 | 0 | 0 | 0
193 | DOT | N15462 | 1212832 | Lake In The Hills | Taylor Lierow | Survey, SUE Level B | 2023-09-18 | 2023-09-20 | 2023-09-25 | 2023-10-16 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-26 | 2023-09-26 | X | 168777007.X.006 | 2023-10-16 | 2023-10-13 | 2023-10-01 | N | 2023-01-01 | - | - | - | - | X | 2023-09-19 | 9850 | 2023-10-16 | X | 2023-09-20 | 4000 | 2023-10-16 | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  |  | DLZ | 9850 | 0 | 0 | 9850 | 0 | 0 | 0 | 0
197 | DOT | M10160-1 | 1213127 | Robbins | Randy Castellon | SUE Level A | 2023-10-10 | 2023-10-13 | 2023-10-17 | 2023-10-31 | 2023-10-13 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-17 | X | 168777007.X.007 | 2023-10-31 | 2023-10-26 | 2023-10-01 | N | 2023-01-01 | N/A |  |  |  | X | 2023-10-12 | 7600 | 2023-10-31 | N/A | [7 empty] | N/A |  |  |  | N/A | [7 empty] | DLZ | 7600 | 0 | 0 | 7600 | 0 | 0 | 0 | 0
189 | TR | STA 215 | 1213225 | Bensenville | Mitchell Pohlman | Survey, SUE Level B, Geotechnical | 2023-03-19 | 2023-03-23 | 2023-04-15 | 2023-07-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-09-22 | 2023-09-25 | X | 168777008.Z.501 | 2023-11-21 | 2023-12-31 | 2024-01-31 | N | 2023-12-01 | - | - | - | - | [12 empty] | X | 2023-04-28 | 56775 | [9 empty] | Dawood | 56775 | 0 | 0 | 0 | 0 | 56775 | 0 | 0
199 | Non-DOT | MR1C15323_C15324 | 1213263 | Northlake | Marissa LaPorte | Survey, SUE Level B, Geotechnical | 2023-10-19 | 2023-10-23 | 2023-10-27 | 2023-12-11 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-12-21 | 2023-12-21 | X | 168777007.Z.543 | 2024-01-30 | 2024-01-30 | 2024-02-01 | N | 2024-03-29 | - | - | - | - | X |  |  |  | X | 2023-10-23 | 65810 | 2023-11-30 | X | 2023-10-23 | 219330 | 11/29/2023 12/27/23 | [12 empty] | Helix | 65810 | 65810 | 0 | 0 | 0 | 0 | 0 | 0
204 | DOT | SC18611 | 1413358 | Normal | Camille Corbi | Survey, SUE Level B | 2023-12-20 | 2023-12-26 | 2024-01-04 | 2024-01-25 | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2024-01-17 | 2024-01-17 | X | 168777007.X.009 | 2024-02-07 | 2024-02-01 | 2024-02-01 | N | 2024-03-20 | - | - | - | - | X | 2023-12-22 | 5950 | 2024-01-26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  |  | DLZ | 5950 | 0 | 0 | 5950 | 0 | 0 | 0 | 0
196 | DOT | N14793 | 1213270 | Woodstock | Camille Corbi | Survey, SUE Level B | 2023-12-13 | 2023-12-15 | 2023-12-20 | 2023-01-19 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2024-01-11 | 2024-01-11 | X | 168777007.X.008 | 2024-02-09 | 2024-02-09 | 2024-02-01 | N | 2024-04-01 | - | - | - | - | X | 2023-10-26 | 34150 | 11/21/2023 11/30/2023 | X | 2023-10-26 | 13500 | 2023-11-21 | X | 10/26/2023 12/15/2023 | 36270 | 2024-02-09 | [12 empty] | Millennia | 36270 | 0 | 36270 | 0 | 0 | 0 | 0 | 0
204 | DOT | N14793 | 1213270 | Woodstock | Camille Corbi | Geotechnical | 2023-12-13 | 2023-12-15 | 2023-12-20 | 2024-01-29 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2024-01-11 | 2024-01-11 | X | 168777007.X.008 | 2024-02-22 | 2024-02-22 | 2024-02-01 | N | 2024-04-01 |  |  |  |  | - | - | - | - | - | - | - | - | X | 2024-12-15 | 17680 | 2024-02-22 | [12 empty] | Millennia | 17680 | 0 | 17680 | 0 | 0 | 0 | 0 | 0
211 | CRA | RS1202 | 1013480 | WHEELING | Marissa LaPorte | Survey, SUE Level B | 2024-01-17 | 2024-01-18 | 2024-01-26 | 2024-02-23 | 2024-01-22 | 2024-01-22 | 2024-01-23 | 2024-01-29 | 2024-01-29 | X | 168777007.Y.002 | 2024-02-23 | 2024-02-22 | 2024-02-01 | N | 2024-05-09 | - | - | - | - | X | 2024-01-19 | 13380 | 2024-02-23 | X | 2024-01-19 | 6980 | 2024-02-23 | X | 2024-01-19 | 17500 | 2024-02-23 | [12 empty] | DLZ | 13380 | 0 | 0 | 13380 | 0 | 0 | 0 | 0
208 | CRA | RS1200 | 1013482 | Elmhurst | Marissa LaPorte | Survey, SUE Level B | 2024-01-15 | 2024-01-17 | 2024-01-24 | 2024-02-21 | 2024-01-18 | 2024-01-19 | 2024-01-22 | 2024-01-29 | 2024-01-29 | X | 168777007.Y.003 | 2024-02-26 | 2024-02-21 | 2024-02-01 | N | 2024-05-09 | - | - | - | - | X | 2024-01-16 | 14900 | 2024-02-21 | X | 2024-01-17 | 5980 | 2024-02-21 | X | 2024-01-17 | 12100 | 2024-02-21 | [12 empty] | Millennia | 12100 | 0 | 12100 | 0 | 0 | 0 | 0 | 0
209 | CRA | RS1201 | 1013481 | Willow Springs | Marissa LaPorte | Survey, SUE Level B | 2024-01-15 | 2024-01-17 | 2024-01-24 | 2024-02-21 | 2024-01-18 | 2024-01-19 | 2024-01-22 | 2024-01-29 | 2024-01-29 | X | 168777007.Y.001 | 2024-02-26 | 2024-02-26 | 2024-02-01 | N | 2024-05-09 | - | - | - | - | X | 2024-01-16 | 13590 | 2024-02-21 | X | 2024-01-17 | 6530 | 2024-02-21 | [16 empty] | DLZ | 13590 | 0 | 0 | 13590 | 0 | 0 | 0 | 0
212 | DOT | SC21051 | 1213617 | OLYMPIA FIELDS | Taylor Lierow | Survey, SUE Level B | 2024-02-29 | 2024-03-04 | 2024-03-07 | 2024-03-28 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-07 | 2024-03-07 | X | 168777007.X.011 | 2024-03-28 | 2024-03-27 | 2024-04-01 | N | 2024-05-01 |  |  |  |  | X | 2024-03-01 | 20300 | 2024-03-28 | [20 empty] | DLZ | 20300 | 0 | 0 | 20300 | 0 | 0 | 0 | 0
217 | DOT | N16431 | 1213707 | Rock Falls | Conner Chamernik | Survey, SUE Level B | 2024-03-11 | 2024-03-12 | 2024-03-18 | 2024-04-08 | 2024-03-14 | 2024-03-15 | 2024-03-15 | 2024-03-21 | 2024-03-22 | X | 168777007.X.512 | 2024-04-12 | 2024-03-29 | 2024-04-01 | N | 2024-05-01 | - | - | - | - | X | 2024-03-14 | 17900 | 2024-04-08 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  |  | DLZ | 17900 | 0 | 0 | 17900 | 0 | 0 | 0 | 0
220 | DOT | N14915 | 1211681 | Crystal Lake | Randy Castellon | Survey | 2024-04-08 | 2024-04-10 | 2024-04-11 | 2028-04-24 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-11 | 2024-04-11 | X | 168777007.X.013 | 2024-04-24 | 2024-04-24 | 2024-04-01 |  | 2024-05-01 | [8 empty] | X` | 2024-04-10 | 4100 | 2024-04-24 | [16 empty] | Helix | 4100 | 4100 | 0 | 0 | 0 | 0 | 0 | 0
218 | CRA | RS989 | 1010985 | Willow Springs | Marissa LaPorte | Plat Survey for Easements | 2024-02-05 | 2024-02-07 | 2024-02-12 | 2024-05-03 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | X | 168777007.Y.004 | 2024-05-03 | 2024-04-26 | 2024-04-01 |  | 2024-05-24 |  |  |  |  | X |  | 30900 | 2024-05-03 | [20 empty] | DLZ | 30900 | 0 | 0 | 30900 | 0 | 0 | 0 | 0
221 | DOT | SC20556 | 1413864 | Bloomington | Eric Dina/Ethan Ekstrom | SUE Level A | 2024-03-27 | 2024-04-01 | 2024-04-03 | 2024-04-26 | 2024-04-08 | 2024-04-09 | 2024-04-24 | 2024-04-30 | 2024-04-10 | X | 168777007.X.015 | 2024-05-06 | 2024-05-07 | 2024-05-01 | N | 2024-05-01 | [12 empty] | X | 2024-04-09 | 6905 | 2024-04-15 | [12 empty] | Millennia | 6905 | 0 | 6905 | 0 | 0 | 0 | 0 | 0
219 | DOT | M15635 | 1213810 | Bridgeview | Randy Castellon | SUE Level A | 2024-04-05 | 2024-04-09 | 2024-04-10 | 2024-05-20 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-11 | 2024-04-11 | X | 168777007.X.014 | 2024-05-20 | 2024-05-17 | 2024-05-01 |  | 2024-07-01 | [8 empty] | X` | 2024-04-10 | 37330 | 2024-05-20 | [16 empty] | Helix | 37330 | 37330 | 0 | 0 | 0 | 0 | 0 | 0
215 | DOT | N14793 | 1213270 | Woodstock | Camille Corbi | Survey, SUE Level B | 2024-03-11 | 2024-03-13 | 2024-03-18 | 2024-04-08 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-07-02 | 2024-07-02 | X | 168777007.X.017 | 2024-07-24 | 2024-07-24 | 2024-07-31 |  | 2024-11-01 | [12 empty] | X | 2024-03-13 | 36400 | 2024-04-08 | [12 empty] | Millennia | 36400 | 0 | 36400 | 0 | 0 | 0 | 0 | 0
207 | DOT | N16379-T | N/A | Chicago | Mitchell Pohlman | SUE Level A | 2023-12-07 | 2023-01-02 | 2024-01-07 | 2024-02-09 | 2024-01-02 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-11 | X | 168777007.X.010 | 2024-08-05 | 2024-08-02 | 2024-07-31 | N | 2024-08-01 | - | - | - | - | [24 empty] | Dawood | 50049 | 0 | 0 | 0 | 0 | 50049 | 0 | 0
217 | DOT | N10173 | 128466 | Hawthorn Woods | Randy Castellon | SUE Level A | 2024-06-05 | 2024-06-10 | 2024-06-13 | 2024-08-01 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-18 | 2024-06-19 | X | 168777007.X.016 | 2024-09-19 | 2024-09-19 | 2024-07-31 |  | 2024-11-01 | [8 empty] | X | 2024-06-07 | 15760 | 7-8 wks | [16 empty] | Helix | 15760 | 15760 | 0 | 0 | 0 | 0 | 0 | 0
219 | DOT | M11560 | 1214095 | Northlake | Conner Chamernik | SUE Level A | 2024-07-10 | 2024-07-11 | 2024-07-24 | 2024-08-07 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-23 | 2024-07-24 | X | 168777007.X.018 | 2024-07-31 | 2024-07-31 | 2024-08-01 | N | 2024-10-01 |  |  |  |  | X | Declined | [6 empty] | X | 2024-07-19 | 16050 | [13 empty] | Millennia | 16050 | 0 | 16050 | 0 | 0 | 0 | 0 | 0
218 | CRA | RS1234 | 1014093 | Dixon | Marissa LaPorte | Survey, SUE Level B | 2024-07-10 | 2024-07-12 | 2024-07-19 | 2024-08-09 | 2024-07-15 | 2024-07-15 | 2024-07-16 | 2024-07-22 | 2024-07-22 | X | 168777007.Y.005 | 2024-08-09 | 2024-08-07 | 2024-08-24 |  | 2024-11-01 |  |  |  |  | X | 2024-07-12 | 18500 | 2024-08-09 | X | 2024-07-12 | 16500 | 2024-08-09 | [16 empty] | Helix | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0
220 | CRA | RS1237 | 1014094 | Sterling | Marissa LaPorte | Survey, SUE Level B | 2024-07-17 | 2024-07-19 | 2024-07-26 | 2024-08-16 | 2024-07-22 | 2024-07-22 | 2024-07-23 | 2024-07-30 | 2024-07-30 | X | 168777007.Y.006 | 2024-08-16 | 2024-08-07 | 2024-08-24 |  | 2024-11-01 |  |  |  |  | X | 2024-07-18 | 9500 | 2024-08-16 | X | 2024-07-18 | 4400 | 2024-08-16 | [16 empty] | DLZ | 9500 | 0 | 0 | 9500 | 0 | 0 | 0 | 0
225 | CRA | RS1252 | 1014137 | Marengo | Madie Roman | Survey, SUE Level B | 2024-07-30 | 2024-08-01 | 2024-08-08 | 2024-08-29 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2024-08-06 | 2024-08-07 | X | 168777007.Y.007 | 2024-08-29 | 2024-08-28 | 2024-08-24 |  | 2024-11-01 |  |  |  |  | X | 2024-07-30 | 7750 | 2024-08-29 | X | 2024-08-01 | 3750 | 2024-08-29 | [16 empty] | Helix | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0
224 | Non-DOT | MR2160 | 1414140 | Bolingbrook | Camille Corbi | Survey, Level SUE B | 2024-07-24 | 2024-07-26 | 2024-08-09 | 2024-09-04 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-13 | 2024-08-13 | X | 168777007.X.019 | 2024-09-09 | 2024-09-09 | 2024-09-01 |  | 2024-11-15 |  |  |  |  | X | 2024-07-30 | 94700 | 2024-09-16 | X | 2024-08-07 | 24660 | 2024-09-04 | [16 empty] | Helix | 24660 | 24660 | 0 | 0 | 0 | 0 | 0 | 0
226 | CRA | RS1238 | 1014138 | Mt Morris | Madie Roman | Survey, SUE Level B, Geotechnical | 2024-08-13 | 2024-08-15 | 2024-08-22 | 2024-09-12 | 2024-08-19 | 2024-08-19 | 2024-08-20 | 2024-08-20 | 2024-08-21 | X | 168777007.Y.009 | 2024-09-12 | 2024-09-09 | 2024-09-09 |  | 2024-11-01 |  |  |  |  | X | 2024-08-15 | 28900 | 2024-09-12 | X | 2024-08-15 | 13350 | 2024-09-12 | [16 empty] | DLZ | 28900 | 0 | 0 | 28900 | 0 | 0 | 0 | 0
228 | CRA | RS1233 | 1014092 | Stillman Valley | Marissa LaPorte | Survey, SUE Level B | 2024-08-13 | 2024-08-15 | 2024-08-22 | 2024-09-12 | 2024-08-20 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | X | 168777007.Y.008 | 2024-09-12 | 2021-09-10 | 2024-09-16 |  | 2024-12-01 |  |  |  |  | X | 2024-08-14 | 10450 | 2024-09-12 | X | 2024-08-15 | 4000 | [17 empty] | DLZ | 10450 | 0 | 0 | 10450 | 0 | 0 | 0 | 0
221 | CRA | RS1244 | 1014110 | Plato Center | Marissa LaPorte | Survey, SUE Level B | 2024-07-23 | 2024-07-25 | 2024-08-02 | 2024-08-23 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-30 | 2024-08-06 | X | 168777007.Y.012 | 2024-08-23 | 2024-08-22 | 2024-09-24 |  | 2024-11-01 |  |  |  |  | X | 2024-07-25 | 8740 | 2024-08-23 | X | 2024-07-25 | 4400 | 2024-08-23 | [16 empty] | DLZ | 8740 | 0 | 0 | 8740 | 0 | 0 | 0 | 0
229 | TR | TWS119 | 1014188 | Kings | Nick Watt | Survey, SUE Level B, Geotechnical | 2024-07-31 | 2024-08-05 | 2024-08-19 | 2024-09-09 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-16 | 2024-08-19 | X | 168777008.Z.503 | 2024-09-09 | 2024-10-01 | 2024-10-01 | N | 2024-10-31 |  |  |  |  | X | 2024-08-05 | 24850 | 2024-09-09 | [9 empty] | 2024-08-01 | 10000 | 2024-08-30 | [8 empty] | DLZ | 24850 | 0 | 0 | 24850 | 0 | 0 | 0 | 0
230 | TR | TC628 | 1014207 | Lake Bloomington | Mitchell Pohlman | Survey, SUE Level B, Geotechnical | 2024-08-07 | 2024-08-12 | 2024-08-21 | 2024-09-11 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-23 | 2024-08-23 | X | 168777008.Z.504 | 2024-09-11 | 2024-10-15 | 2024-10-01 | N | 2024-12-01 | [5 empty] | 2024-08-12 | 19800 | 2024-09-11 | [20 empty] | DLZ | 19800 | 0 | 0 | 19800 | 0 | 0 | 0 | 0
231 | CRA | RS959 | 1011935 | Geneseo | Madie Roman | Survey, SUE Level B | 2024-08-22 | 2024-08-26 | 2024-09-03 | 2024-09-24 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-28 | 2024-08-28 | X | 168777007.Y.010 | 2024-09-24 | 2024-09-24 | 2024-10-01 |  | 2024-12-01 |  |  |  |  | X | 2024-08-23 | 8650 | 2024-09-24 | X | 2024-08-26 | 4900 | 2024-09-24 | [16 empty] | Helix | 4900 | 4900 | 0 | 0 | 0 | 0 | 0 | 0
233 | CRA | RS1267 | 1014228 | Woodstock | Marissa LaPorte | Survey, Level SUE B | 2024-08-27 | 2024-08-29 | 2024-09-06 | 2024-09-27 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-09-16 | 2024-09-13 | X | 168777007.Y.013 | 2024-10-04 | 2024-09-30 | 2024-10-01 |  | 2024-12-01 |  |  |  |  | X | 2024-08-29 | 13850 | 2024-09-27 | x | 2024-08-29 | 6900 | 2024-09-27 | [16 empty] | DLZ | 13850 | 0 | 0 | 13850 | 0 | 0 | 0 | 0
234 | CRA | RS1265 | 1014227 | Watseka | Madie Roman | Survey, Level SUE B | 2024-08-29 | 2024-09-03 | 2024-09-10 | 2024-10-09 | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-18 | 2024-09-18 | X | 168777007.Y.011 | 2024-10-09 | 2024-10-04 | 2024-10-01 |  | 2024-12-01 |  |  |  |  | X | 2024-09-03 | 10980 | 2024-10-01 | x | 2024-09-03 | 6825 | 2024-10-01 | [16 empty] | DLZ | 10980 | 0 | 0 | 10980 | 0 | 0 | 0 | 0
232 | TR | TP605 | 1014212 | Rockford | Mitchell Pohlman | Survey, SUE Level B | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-09-27 | 2024-08-26 | 2024-08-26 | 2024-08-27 | 2024-09-06 | 2024-09-06 | X | 168777008.Z.505 | 2024-10-14 | 2024-10-11 | 2024-10-01 | N | 2024-12-01 | [8 empty] | X | 2024-08-23 | 25150 | 2024-10-14 | [16 empty] | Helix | 25150 | 25150 | 0 | 0 | 0 | 0 | 0 | 0
232 | TR | TP605A | 1014268 | Rockford | Mitchell Pohlman | Survey, SUE Level B | 2024-08-20 | 2024-08-22 | 2024-08-27 | 2024-09-27 | 2024-08-26 | 2024-08-26 | 2024-08-27 | 2024-09-06 | 2024-09-06 | X | 168777008.Z.506 | 2024-10-14 | 2024-10-11 | 2024-10-01 | N | 2024-12-01 | [8 empty] | X | 2024-08-23 | 29400 | 2024-10-14 | [16 empty] | Helix | 29400 | 29400 | 0 | 0 | 0 | 0 | 0 | 0
235 | CRA | RS1266 | 1014237 | Elgin | Madie Roman | Survey, Level SUE B | 2024-09-05 | 2024-09-09 | 2024-09-16 | 2024-10-07 | 2024-09-09 | 2024-09-10 | 2024-09-10 | 2024-09-24 | 2024-09-24 | X | 168777007.Y.014 | 2024-10-15 | 2024-10-11 | 2024-10-01 |  | 2024-12-01 |  |  |  |  | X | 2024-09-06 | 10800 | 2024-10-07 | X | 2024-09-09 | 5750 | 2024-10-07 | [16 empty] | DLZ | 10800 | 0 | 0 | 10800 | 0 | 0 | 0 | 0
227 | Non-DOT | NBA10015039 | 1614145 | Elk Grove Village | Camille Corbi | Survey, SUE Level B | 2024-08-12 | 2024-08-14 | 2024-09-02 | 2024-09-30 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-09-05 | 2024-09-11 | X | 168777007.Z.045 | 2024-10-15 | 2024-10-10 | 2024-11-01 |  | 2024-12-24 |  |  |  |  | X | [7 empty] | X | 8/28/2024 (Survey) 8/28/2024 (Potholes) | 59665 | 2024-09-30 | [12 empty] | Millennia | 59665 | 0 | 59665 | 0 | 0 | 0 | 0 | 0
239 | Non-DOT | NBA10015039 | 1614145 | Elk Grove Village | Camille Corbi | SUE Level A | 2024-09-18 | 2024-09-20 | 2024-09-25 | 2024-10-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-08 | 2024-10-08 | X | 168777007.Z.048 | 2024-10-18 | 2024-10-22 | 2024-11-01 |  | 2024-12-24 | [12 empty] | X | 2024-10-03 | 42200 | 2024-10-18 | [12 empty] | Millennia | 42200 | 0 | 42200 | 0 | 0 | 0 | 0 | 0
222 | Non-DOT | NBA10013465 | 1914022 | Gilman | Nick Michaels | Survey, SUE Level A & B, Geotechnical | 2024-08-19 | 2024-08-22 | 2024-09-05 | 2024-10-22 | 2024-09-11 | 2024-09-12 | 2024-09-12 | 2024-09-18 | 2024-09-18 | X | 168777007.Z.046 | 2024-10-22 |  | 2024-11-01 |  | 2025-02-28 |  |  |  |  | X | 2024-08-30 | 223020 | 2024-11-24 | X | 2024-08-23 | 117590 | 2024-10-22 | X | 2024-08-21 | 131875 | 2024-10-29 | [12 empty] | Helix | 117590 | 117590 | 0 | 0 | 0 | 0 | 0 | 0
232 | Non-DOT | MR2160 | 1414140 | Bolingbrook | Camille Corbi | SUE Level A | 2024-08-27 | 2024-08-28 | 2024-09-02 | 2024-10-30 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-09-03 | 2024-09-03 | X | 168777007.Z.044 | 2024-10-30 | 2024-10-31 | 2024-11-01 |  | 2024-11-24 | [8 empty] | X | 2024-08-28 | 34035 | 2024-10-30 | [16 empty] | Helix | 34035 | 34035 | 0 | 0 | 0 | 0 | 0 | 0
240 | CRA | RS940 | 1011912 | Rolling Meadows | Marissa LaPorte | Survey, SUE Level B | 2024-09-23 | 2024-09-25 | 2024-10-02 | 2024-10-23 | 2024-09-27 | 2024-09-27 | 2024-09-30 | 2024-10-03 | 2024-10-04 | X | 168777007.Y.015 | 2024-10-25 | 2024-10-23 | 2024-11-24 |  | 2025-01-31 |  |  |  |  | X | 2024-09-25 | 10290 | 2024-10-23 | X | 2024-09-25 | 6580 | 2024-10-23 | [16 empty] | Helix | 6580 | 6580 | 0 | 0 | 0 | 0 | 0 | 0
235 | CRA | RS1276 | 1014369 | Woodstock | Marissa LaPorte | Survey, SUE Level B | 2024-10-16 | 2024-10-21 | 2024-10-28 | 2024-11-15 | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-11-05 | 2024-11-05 | X | 168777007.Y.016 | 2024-11-22 | 2024-11-05 | 2024-12-01 |  | 2025-01-31 |  |  |  |  | X | 2024-10-21 | 6300 | 2024-11-15 | X | 2024-10-21 | 4500 | 2024-11-22 | [16 empty] | Helix | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
238 | Non-DOT | MR2197 | 1214525 | Round Grove | Mark Stanley/Tom McTigue | Survey, SUE Level B | 2024-11-14 | 2024-11-18 | 2024-11-25 | 2024-12-10 | 2024-11-18 | 2024-11-20 | 2024-11-20 | 2024-11-22 | 2024-11-22 | X | 168777007.Z.051 | 2024-12-10 | 2024-12-10 | 2024-12-01 |  | 2024-12-31 | [8 empty] | X | 2024-11-15 | 12600 | 2024-12-10 | [16 empty] | Helix | 12600 | 12600 | 0 | 0 | 0 | 0 | 0 | 0
235 | Non-DOT | MR2192 | 1414512 | Kankakee | Nick Michaels/Tom McTigue | Survey, SUE Level B, Geotechnical | 2024-11-06 | 2024-11-07 | 2024-11-14 | 2020-12-14 | 2024-11-07 | 2024-11-08 | 2024-11-08 | 2024-11-12 | 2024-11-12 | X | 168777007.Z.049 | 2024-12-14 | 2024-11-22 | 2024-12-01 |  | 2025-01-01 | [8 empty] | X | 2024-11-07 | 17850 | 2024-12-14 | [16 empty] | Helix | 17850 | 17850 | 0 | 0 | 0 | 0 | 0 | 0
236 | Non-DOT | MR2203 | 1414506 | Wilmington | Camille Corbi/Tom McTigue | Survey, SUE Level B, Geotechnical | 2024-11-08 | 2024-11-12 | 2024-11-19 | 2024-12-18 | 2024-11-13 | 2024-11-14 | 2024-11-14 | 2024-11-15 | 2024-11-15 | X | 168777007.Z.050 | 12/5/2024 12/19/2024 | 2024-12-06 | 2024-12-01 |  | 2025-01-25 |  |  |  |  | X | 2024-11-12 | 40400 | 2024-12-18 | X | 2024-11-12 | 19400 | 12/5/2024 12/19/2024 | [16 empty] | Helix | 19400 | 19400 | 0 | 0 | 0 | 0 | 0 | 0
241 | CRA | RS940 | 1011912 | Rolling Meadows | Marissa LaPorte | Survey, SUE Level B | 2024-11-25 | 2024-11-27 | 2024-12-06 | 2024-01-03 | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-03 | 2024-12-05 | X | 168777007.Y.016 | 2025-01-03 | 2025-01-03 | 2025-01-01 |  | 2025-03-01 | [8 empty] | X | 2024-12-02 | 9290 | 2025-01-03 | [16 empty] | Helix | 9290 | 9290 | 0 | 0 | 0 | 0 | 0 | 0
243 | CRA | RS1278 | 1014641 | Norridge | Marissa LaPorte | Survey, SUE Level B | 2024-12-04 | 2024-12-06 | 2024-12-13 | 2025-01-10 | 2024-12-09 | 2024-12-09 | 2024-12-10 | 2024-12-12 | 2024-12-12 | X | 168777007.Y.022 | 2025-01-10 | 2025-01-06 | 2025-01-01 |  | 2025-02-21 |  |  |  |  | X | 2024-12-05 | 11100 | 2025-01-10 | X | 2024-12-06 | 7590 | 2025-01-10 | [16 empty] | DLZ | 11100 | 0 | 0 | 11100 | 0 | 0 | 0 | 0
233 | CRA | RS1271 | 1014367 | Woodstock | Marissa LaPorte | Survey, SUE Level B | 2024-10-16 | 2024-10-21 | 2024-10-28 | 2024-11-22 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-18 | 2024-12-18 | X | 168777007.Y.018 | 2025-01-10 | 2025-01-10 | 2025-01-01 |  | 2025-03-01 |  |  |  |  | X | 2024-10-21 | 26950 | 2024-11-22 | X | 2024-10-21 | 5935 | 2024-11-22 | [16 empty] | Helix | 5935 | 5935 | 0 | 0 | 0 | 0 | 0 | 0
245 | COR | COR1059 | 1214705 | Glenwood | Madie Roman | Survey, SUE Level B | 2024-12-20 | 2024-12-26 | 2025-01-03 | 2025-01-21 | 2024-12-30 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | X | 168777007.Y.019 | 2025-01-24 | 2025-01-24 | 2025-01-01 |  | 2025-02-14 |  |  |  |  | X | 2024-12-26 | 8450 | 2025-01-23 | X | 2024-12-26 | 5900 | 2025-01-21 | [16 empty] | Helix | 5900 | 5900 | 0 | 0 | 0 | 0 | 0 | 0
246 | COR | COR1062 | 1214646 | Glenwood | Madie Roman | Survey, SUE Level B | 2024-12-20 | 2024-12-26 | 2025-01-03 | 2025-01-21 | 2024-12-30 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | X | 168777007.Y.020 | 2025-01-24 | 2025-01-24 | 2025-01-01 |  | 2025-02-14 |  |  |  |  | X | 2024-12-26 | 7400 | 2025-01-23 | X | 2024-12-26 | 4340 | 2025-01-21 | [16 empty] | Helix | 4340 | 4340 | 0 | 0 | 0 | 0 | 0 | 0
247 | COR | COR1064 | 1214707 | Crestwood | Madie Roman | Survey, SUE Level B | 2024-12-20 | 2024-12-26 | 2025-01-03 | 2025-01-21 | 2024-12-30 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | X | 168777007.Y.021 | 2025-01-24 | 2025-01-24 | 2025-01-01 |  | 2025-02-14 |  |  |  |  | X | 2024-12-26 | 4300 | 2025-01-23 | X | 2024-12-26 | 3920 | 2025-01-21 | [16 empty] | Helix | 3920 | 3920 | 0 | 0 | 0 | 0 | 0 | 0
250 | NBA | NBA10015039 | 1614145 | Elk Grove Village | Camille Corbi | SUE Level A | 2024-12-23 | 2025-01-02 | 2025-01-08 | 2025-02-07 | 2025-01-02 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-07 | X | 168777007.Z.052 | 2025-02-08 | 2025-01-27 | 2025-01-01 |  | 2024-12-23 | [8 empty] | X | 2025-01-02 | 11500 | 2025-02-07 | [16 empty] | Helix | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 0
252 | DOT | N17865-T | 1214786 | Elk Grove Village | Conner Chamernik | SUE Level A | 2025-01-07 | 2025-01-14 | 2025-01-17 | 2025-02-05 | 2025-01-16 | 2025-01-16 | 2025-01-17 | 2025-01-21 | 2025-01-22 | X | 168777007.X.024 | 2025-02-05 | 2025-02-12 | 2025-02-01 | N | 2025-02-01 | [24 empty] | X | 2025-01-05 | 17000 |  | LWS | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 17000
251 | DOT | N17865-T | 1214786 | Elk Grove Village | Conner Chamernik | SUE Level A | 2025-01-07 | 2025-01-14 | 2025-01-17 | 2025-02-05 | 2025-01-16 | 2025-01-16 | 2025-01-17 | 2025-01-21 | 2025-01-22 | X | 168777007.X.023 | 2025-02-05 | 2025-02-12 | 2025-02-01 | N | 2025-02-01 | [24 empty] | X | 2025-01-05 | 30500 |  | LWS | 30500 | 0 | 0 | 0 | 0 | 0 | 0 | 30500
248 | TIMP | TP631 | 1114742 | Matteson | Mitchell Pohlman | Survey, SUE Level B | 2025-01-03 | 2025-01-07 | 2025-01-14 | 2025-02-05 | 2025-01-07 | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-15 | X | 168777008.Z.507 | 2025-02-13 | 2025-01-31 | 2025-02-01 | N | 2025-05-01 |  |  |  |  | X | 2025-01-06 | 6670 | 2025-02-05 |  | 2025-01-07 | 5470 | 2025-02-05 |  | 2025-01-07 | 10500 | 2025-02-05 | [12 empty] | DLZ | 6670 | 0 | 0 | 6670 | 0 | 0 | 0 | 0
239 | DOT | N16744 | 1214571 | Crystal Lake | Mark Stanley | SUE Level A | 2024-11-14 | 2024-11-19 | 2024-11-26 | 2024-12-20 | 2024-11-20 | 2024-11-20 | 2024-11-21 | 2024-11-26 | 2024-11-26 | X | 168777007.X.020 | 2025-02-14 | 2025-02-05 | 2025-02-01 | N | 2025-02-01 |  |  |  |  | X | Declined | [6 empty] | X | 2024-11-19 | 20450 | [13 empty] | Millennia | 20450 | 0 | 20450 | 0 | 0 | 0 | 0 | 0
249 | Non-DOT | MR2216 | 1214785 | FREEPORT | Mark Stanley | Survey, SUE Level B | 2025-01-07 | 2025-01-10 | 2025-01-21 | 2025-02-18 | 2025-01-16 | 2025-01-16 | 2025-01-17 | 2025-11-21 | 2025-11-21 | X | 168777007.Z.053 | 2025-02-18 | 2025-02-18 | 2025-02-01 |  | 2025-04-08 |  |  |  |  | X | 2025-01-10 | 43800 | 2025-02-11 | X | 2025-01-10 | 16695 | 2025-02-18 | X | No Response | [14 empty] | Helix | 16695 | 16695 | 0 | 0 | 0 | 0 | 0 | 0
242 | CRA | RS1280 | 1014643 | Streamwood | Madie Roman | Survey, SUE Level B | 2024-11-26 | 2024-12-02 | 2024-12-06 | 2024-01-03 | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2025-01-02 | 2025-01-03 | X | 168777007.Y.023 | 2025-01-31 | 2025-02-11 | 2025-02-25 |  | 2025-03-28 |  |  |  |  | X | 2024-11-27 | 28700 | 2025-01-03 | X | 2024-12-02 | 11200 | 2024-01-03 | [16 empty] | Helix | 11200 | 11200 | 0 | 0 | 0 | 0 | 0 | 0
253 | COR | COR1073 | 1214777 | Des Plaines | Madie Roman | Survey, SUE level B | 2025-01-20 | 2025-01-22 | 2025-01-29 | 2025-02-17 | 2025-01-27 | 2025-01-27 | 2025-01-30 | 2025-02-04 | 2025-02-05 | X | 168777007.Y.026 | 2025-02-19 | 2025-02-19 | 2025-02-25 |  | 2025-02-28 | [8 empty] | X | 2025-01-23 | 3890 | 2025-02-19 | [16 empty] | Helix | 3890 | 3890 | 0 | 0 | 0 | 0 | 0 | 0
254 | COR | COR1071 | 1314774 | Glen Ellyn | Madie Roman | Survey, SUE level B | 2025-01-21 | 2025-01-24 | 2025-01-31 | 2025-02-19 | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-02-04 | 2025-02-06 | X | 168777007.Y.024 | 2025-02-24 | 2025-02-24 | 2025-02-25 |  | 2025-03-07 |  |  |  |  | X |  |  |  | X |  | 2200 | [17 empty] | Helix | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0
260 | COR | COR1072 | 1314775 | Glen Ellyn | Madie Roman | Survey, SUE level B | 2025-01-21 | 2025-01-24 | 2025-01-31 | 2025-02-19 | 2025-01-30 | 2025-01-31 | 2025-01-31 | 2025-02-05 | 2025-02-06 | X | 168777007.Y.025 | 2025-02-25 | 2025-02-25 | 2025-02-25 |  | 2025-03-07 | [8 empty] | X |  | 2000 | [17 empty] | Helix | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
235 | DOT | N14793 | 1213270 | Woodstock | Camille Corbi | MOT | 2024-09-03 | 2024-10-21 | 2024-10-25 | 2024-12-30 | 2024-10-23 | 2024-10-23 | 2024-10-24 | 2024-10-24 | 2024-10-24 | X | 168777007.X.017 | 2025-01-21 | 2025-01-31 | 2025-03-01 | N | 2025-03-01 | [12 empty] | X | 2024-10-21 | 73400 | 2024-12-20 | [12 empty] | Millennia | 66130 | 0 | 66130 | 0 | 0 | 0 | 0 | 0
240 | DOT | SC19879 | 1412412 | Joliet | Eric Dina | SUE Level A | 2024-11-25 | 2024-12-03 | 2024-12-05 | TBD | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-05 | X | 168777007.X.021 | 2025-02-05 | N/A | 2025-03-01 | N | 2025-03-01 |  |  |  |  | X | Declined |  |  | X | 2024-12-03 | 10380 | 2 weeks post IDOT permit | X | 2024-12-03 | 22200 | not listed | [12 empty] | Helix | 2715 | 2715 | 0 | 0 | 0 | 0 | 0 | 0
244 | DOT TR | N16379-T | 1213225 | Chicago | Mitchell Pohlman | SUE Level A | 2024-12-02 | 2024-12-04 | 2024-12-09 | 2025-01-18 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-11 | X | 168777007.X.022 | 2025-03-07 | 2025-03-30 | 2025-03-01 | N | 2025-03-01 | [8 empty] | X | 2024-12-04 | 39600 | 2024-01-18 | [16 empty] | Helix | 39600 | 39600 | 0 | 0 | 0 | 0 | 0 | 0
257 | Non-DOT | MR2BID9647-3 | 1214992 | Hometown | Camille Corbi | Survey, SUE level B | 2025-02-07 | 2025-02-11 | 2025-02-18 | 2025-03-14 | 2025-02-14 | 2025-02-14 | 2025-02-17 | 2025-02-18 | 2025-02-18 | X | 168777007.Z.054 | 2025-03-14 | 2025-03-16 | 2025-03-01 |  | 2025-05-01 | [8 empty] | X | 2025-02-12 | 23400 | 2025-03-14 | [16 empty] | Helix | 23400 | 23400 | 0 | 0 | 0 | 0 | 0 | 0
258 | Non-DOT | MR2BID9834-1 | 1214925 | Hometown | Tom McTigue | Survey, SUE level B & Geotechnical | 2025-02-07 | 2025-02-14 | 2025-02-19 | 2025-03-14 | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-18 | 2025-02-18 | X | 168777007.Z.057 | 2025-03-14 | 2025-03-14 | 2025-03-01 |  | 2025-06-01 |  |  |  |  | X | 2025-02-11 | 107100 | 2025-03-28 | X | 2025-02-14 | 38500 | 3/14/2025 4/14/2025 | [16 empty] | Helix | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0
259 | Non-DOT | MR2BID9834-2 | 1214993 | Hometown | Tom McTigue | Survey, SUE level B | 2025-02-07 | 2025-02-14 | 2025-02-19 | 2025-03-14 | 2025-02-17 | 2025-02-17 | 2025-02-17 | 2025-02-18 | 2025-02-18 | X | 168777007.Z.058 | 2025-03-14 | 2025-03-14 | 2025-03-01 |  | 2025-05-01 | [8 empty] | X | 2025-02-14 | 11100 | 2025-03-14 | [16 empty] | Helix | 11100 | 11100 | 0 | 0 | 0 | 0 | 0 | 0
255 | Non-DOT | MR2BID9647-1 | 1214924 | Hometown | Camille Corbi | Survey, SUE level B | 2025-02-07 | 2025-02-11 | 2025-02-18 | 2025-03-21 | 2025-02-14 | 2025-02-14 | 2025-02-17 | 2025-02-18 | 2024-02-18 | X | 168777007.Z.055 | 2025-03-21 | 2025-03-30 | 2025-03-01 |  | 2025-07-01 |  |  |  |  | X | No Response |  |  | X | 2025-02-12 | 18100 | 2025-03-21 | [16 empty] | Helix | 18100 | 18100 | 0 | 0 | 0 | 0 | 0 | 0
256 | Non-DOT | MR2BID9647-2 | 1214991 | Hometown | Camille Corbi | Survey, SUE level B | 2025-02-07 | 2025-02-11 | 2025-02-18 | 2025-03-28 | 2025-02-14 | 2025-02-14 | 2025-02-17 | 2025-02-18 | 2025-02-18 | X | 168777007.Z.056 | 2025-03-28 | 2025-03-24 | 2025-03-01 |  | 2025-07-01 | [8 empty] | X | 2025-02-12 | 32400 | 2025-03-28 | [16 empty] | Helix | 32400 | 32400 | 0 | 0 | 0 | 0 | 0 | 0
262 | DOT | N16744 | 1214571 | Crystal Lake | Mark Stanley | Survey, SUE Level B | 2025-03-28 | 2025-04-02 | 2025-04-15 | 2025-04-30 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-15 | 2025-04-15 | X | 168777007.X.026 | 2025-04-30 | 2025-04-29 | 2025-05-01 | N | 2025-05-01 |  |  |  |  | X | 2025-03-31 | 7530 | 2025-04-29 | X | 2025-04-02 | 4900 | 2025-04-30 | X | 2025-04-02 | 16850 | 2025-05-15 | [12 empty] | Helix | 4900 | 4900 | 0 | 0 | 0 | 0 | 0 | 0
264 | CRA | RS1280 | 1014643 | Streamwood | Madie Roman | Survey, SUE Level B | 2025-04-17 | 2025-04-21 | 2025-04-28 | 2025-05-19 | 2025-04-18 | 2025-04-21 | 2025-04-22 | 2025-04-22 | 2025-04-23 | X | 168777007.Y.028 | 2025-05-14 | 2025-05-16 | 2025-05-01 | N | 2025-07-01 | [8 empty] | X | 2025-04-18 | 3400 | 2025-05-19 | [16 empty] | Helix | 3400 | 3400 | 0 | 0 | 0 | 0 | 0 | 0
265 | CRA | RS1213 | 1015226 | Elburn | Julia Holstead | Survey, SUE Level B | 2025-04-15 | 2025-04-17 | 2025-04-24 | 2025-05-15 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-22 | 2025-04-23 | X | 168777007.Y.027 | 2025-05-15 | 2025-05-15 | 2025-05-01 | N | 2025-07-01 | [8 empty] | X | 2025-04-17 | 15900 | 2025-05-15 | [16 empty] | Helix | 15900 | 15900 | 0 | 0 | 0 | 0 | 0 | 0
269 | CRA | MR2259 | 1215296 | Kinsman | Tom McTigue | Survey, SUE level B & Geotechnical | 2025-04-24 | 2025-04-28 | 2025-05-09 | 2025-05-23 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-09 | 2025-05-09 | X | 168777007.Y.029 | 2025-05-23 | 2025-05-20 | 2025-05-01 | N | 2025-08-01 |  |  |  |  | x | 2025-05-02 | 21050 | 2025-05-23 | X | 2025-05-02 | 14250 | 2025-05-23 | [16 empty] | Helix | 14250 | 14250 | 0 | 0 | 0 | 0 | 0 | 0
270 | CRA | MR2261 | 1415304 | Saunmin | Conner Chamernik | Survey, SUE level B & Geotechnical | 2025-05-02 | 2025-05-05 | 2025-05-14 | 2025-05-23 | 2025-05-02 | 2025-05-05 | 2025-05-05 | 2025-05-13 | 2025-05-14 | X | 168777007.Y.030 | 2025-05-23 | 2025-05-29 | 2025-05-01 | N | 2025-08-01 |  |  |  |  | X | 2025-04-28 | 19130 | 2025-05-23 | X | 2025-05-02 | 13950 | 2025-05-23 | [16 empty] | Helix | 13950 | 13950 | 0 | 0 | 0 | 0 | 0 | 0
272 | CRA | RS1302 | 1014897 | Davis Junction | Madie Roman | Survey, SUE Level B | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-27 | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | X | 168777007.Y.032 | 2025-05-28 | 2025-05-28 | 2025-05-01 | N | 2025-08-01 | [8 empty] | X | 2025-04-27 | 15985 | 2025-05-27 | [16 empty] | Helix | 15985 | 15985 | 0 | 0 | 0 | 0 | 0 | 0
266 | CRA | RS1218 | 1015225 | Elburn | Madie Roman | Survey, SUE Level B | 2025-04-16 | 2025-04-18 | 2025-04-25 | 2025-05-16 | 2025-04-17 | 2025-04-17 | 2025-04-18 | 2025-05-12 | 2025-05-13 | X | 168777007.Y.031 | 2025-06-03 | 2025-05-30 | 2025-05-01 | N | 2025-07-01 | [8 empty] | X | 2025-04-17 | 12770 | 2025-05-16 | [16 empty] | Helix | 12770 | 12770 | 0 | 0 | 0 | 0 | 0 | 0
260 | DOT | N18492 | 1214923 | Long Grove | Taylor Lierow | SUE Level A | 2025-03-13 | 2025-03-20 | 2025-03-28 | 2025-05-20 | 2025-04-02 | 2025-04-06 | 2025-04-07 | 2025-04-15 | 2025-04-15 | X | 168777007.X.025 | 2025-05-20 | 2025-06-09 | 2025-06-01 | N | 2025-07-25 | [8 empty] | X | 2025-03-27 | 8965 | 2025-05-13 | X | N/A | N/A | N/A | [8 empty] | X | 2025-03-20 | 30930 | 2025-05-02 | Helix | 8965 | 8965 | 0 | 0 | 0 | 0 | 0 | 0
268 | Non-DOT | MR2219-1 | 1314926 | Aurora | Camille Corbi | Survey, SUE Level B | 2025-04-22 | 2025-04-24 | 2025-04-29 | 2025-06-03 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-06 | 2025-05-06 | X | 168777007.Z.059 | 2025-06-03 | 2025-06-03 | 2025-06-01 | N | 2025-08-01 | [8 empty] | X | 2025-04-24 | 32470 | 2025-04-24 | [16 empty] | Helix | 32470 | 32470 | 0 | 0 | 0 | 0 | 0 | 0
271 | Non-DOT | MR2277 | 1215381 | Lansing | Tom McTigue | Survey, SUE Level B | 2025-05-12 | 2025-05-14 | 2025-05-20 | 2025-06-10 | 2025-05-13 | 2025-05-14 | 2025-05-14 | 2025-05-19 | 2025-05-19 | X | 168777007.Z.060 | 2025-06-10 | 2025-06-10 | 2025-06-01 | N | 2025-06-25 |  |  |  |  | X | 2025-05-13 | 18950 | 2025-06-10 | [20 empty] | DLZ | 18950 | 0 | 0 | 18950 | 0 | 0 | 0 | 0
274 | CRA | RS1279 | 1014642 | Elgin | Madie Roman | Survey, SUE Level B, & Geotechnical | 2025-05-13 | 2025-05-15 | 2025-05-21 | 2025-06-11 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-27 | 2025-05-27 | X | 168777007.Y.033 | 2025-06-20 | 2025-06-23 | 2025-06-01 |  | 2025-08-01 | [8 empty] | X | 2025-05-15 | 28800 | 2025-06-11 | [16 empty] | Helix | 28800 | 28800 | 0 | 0 | 0 | 0 | 0 | 0
273 | TIMP | TP659 | 1015283 | Rockford | Mitchell Pohlman | Survey, SUE Level B | 2025-05-12 | 2025-05-14 | 2025-05-23 | 2025-06-20 | 2025-05-16 | 2025-05-23 | 2025-05-23 | 2025-05-27 | 2025-05-27 | X | 168777008.Z.509 | 2025-06-20 | 2025-06-23 | 2025-07-01 | N | 2025-07-01 |  |  |  |  | X | 2025-05-13 | 31000 | 2025-06-20 |  | 2025-05-14 | 28900 | 2025-06-20 |  | 2025-05-14 | 77000 | 2025-06-20 | [12 empty] | DLZ | 31000 | 0 | 0 | 31000 | 0 | 0 | 0 | 0
276 | CRA | RS1317 | 1015488 | Hinsdale | Julia Holstead | Survey, SUE Level B | 2025-06-24 | 2025-06-26 | 2025-07-03 | 2025-07-30 | 2025-06-30 | 2025-07-25 | 2025-07-01 | 2025-07-08 | 2025-07-08 | 2025-07-08 | 168777007.Y.034 | 2025-07-30 | 2025-07-30 | 2025-07-01 | [10 empty] | X | 2025-06-26 | 12200 | 2025-07-30 | [16 empty] | Helix | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0
264 | CRA | RS1318 | 1015485 | Niles | Marissa LaPorte | Survey, SUE Level B | 2025-06-17 | 2025-06-19 | 2025-06-27 | 2025-07-18 | 2025-06-30 | 2025-07-02 | 2025-07-03 | 2025-07-14 | 2025-07-17 | 2025-07-17 | 168777007.Y.035 | 2025-08-04 | 2025-08-04 | 2025-07-01 | [10 empty] | X | 2025-06-30 | 13960 | 2025-07-30 | [16 empty] | Helix | 13960 | 13960 | 0 | 0 | 0 | 0 | 0 | 0
261 | TR | TWS121 | 1015081 | Woodbine | Nick Watt | Survey, SUE Level B, & Geotechnical | 2025-03-24 | 2025-03-26 | 2025-04-28 | 2025-05-28 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-08 | 2025-05-08 | X | 168777008.Z.508 | 2025-07-23 | 2025-08-11 | 2025-08-01 | N | 2025-08-01 |  |  |  |  | X | 2025-03-26 | 18350 |  | X | 2025-03-26 | 14480 |  | X | Declined | [14 empty] | Helix | 14480 | 14480 | 0 | 0 | 0 | 0 | 0 | 0
279 | CRA | RS1331 | 1015588 | Goodfield | Camille Corbi | Survey, Level SUE B | 2025-07-11 | 2025-07-15 | 2025-07-18 | 2025-08-01 | 2025-07-15 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | X | 168777007.Y.039 | 2025-08-08 | 2025-08-08 | 2025-08-01 | N | 2025-10-01 | [8 empty] | X | 2025-07-15 | 8900 | 2025-08-05 | [16 empty] | Helix | 8900 | 8900 | 0 | 0 | 0 | 0 | 0 | 0
277 | CRA | RS1321 | 1015615 | Rochelle | Marissa LaPorte | Survey, Level SUE B | 2025-07-09 | 2025-07-11 | 2025-07-18 | 2025-08-01 | 2025-07-14 | 2025-07-21 | 2025-07-21 | 2025-07-29 | 2025-07-29 | X | 168777007.Y.037 | 2025-08-12 | 2025-08-12 | 2025-08-01 | N/A | [9 empty] | X | 2025-07-11 | 12740 | 2025-08-01 | [16 empty] | Helix | 12740 | 12740 | 0 | 0 | 0 | 0 | 0 | 0
281 | CRA | RS1249 | 1014139 | Roselle | Madie Roman | Survey, Level SUE B | 2025-07-17 | 2025-07-21 | 2025-07-28 | 2025-08-18 | 2025-07-21 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | X | 168777007.Y.036 | 2025-08-18 | 2025-08-18 | 2025-08-01 |  | 2025-10-01 | [8 empty] | X | 2025-07-21 | 5930 | 2025-08-18 | [16 empty] | Helix | 5930 | 5930 | 0 | 0 | 0 | 0 | 0 | 0
138 | CRA | MR1968 | 3212115 | Prospect Heights | Madie Roman | Survey, SUE Level B | 2022-12-03 | 2022-12-06 | 2022-12-12 | 2023-01-10 | 2022-12-09 | 2022-12-09 | 2022-12-10 | Denied | N/A | N/A | N/A | 2023-01-10 | N/A | Denied | N/A | 2023-01-01 | X | 2022-12-06 | 13400 | 6 weeks NTP (1/23/2023) | X | 2022-12-06 | 15850 | 2023-01-10 | X | 2022-12-06 | 8500 | 2023-01-17 | X | No Response |  |  | X | 2022-12-06 | 12000 | 2023-01-10 | [9 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | Non-DOT | PRIM718 | 1315392 | Glendale Heights | Conner Chamernik | Survey, SUE Level B | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-06-06 | 2025-05-20 | 2025-05-20 | 2025-05-21 | Denied |  |  |  | 2025-06-06 |  | Denied | [10 empty] | X | [20 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | CRA | MR1840 | 3210897 | Western Springs | Tim Purtell | Survey, SUE Level B | 2022-01-19 | 2022-01-21 | 2022-01-24 | 2022-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Denied | N/A | 2023-01-01 | [29 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | CRA | MR1964 | 3212094 | Lake Zurich | Mark Stanley | Survey, SUE Level B | 2022-12-07 | 2022-12-09 | 2022-12-19 | 2023-01-10 | 2022-12-12 | 2022-12-13 | 2022-12-13 | Denied | N/A | N/A | N/A | N/A | N/A | Denied | N/A | 2023-01-01 | X | 2022-12-09 | 6690 | 2023-01-30 | X | 2022-12-08 | 6700 | 2023-01-10 | X | 2022-12-12 | 4000 | 2023-01-17 | X | No Response | - | - | X | 2022-12-08 | 8200 | 2023-01-13 | X | 2022-12-08 | 25955.9 | 2023-01-10 | [5 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | CRA | RS1218 | 1015225 | Elburn | Madie Roman | Survey, SUE Level B & Geotechnical | 2025-06-13 | 2025-06-17 | 2025-06-24 | 2025-07-15 | 2025-06-23 | 2025-06-25 | 2025-06-26 | Denied | N/A | N/A | N/A | N/A | N/A | Denied | [10 empty] | X | 2025-06-17 | 15325 | 2025-07-15 | [17 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | CRA | TW3601350 | 1014895 | E Dubuque | Julia Holstead | Survey, SUE Level B | 2025-04-22 | 2025-04-24 | 2025-05-01 | 2025-05-22 | 2025-04-25 | 2025-04-25 | 2025-02-25 | Denied | N/A | N/A | N/A | N/A | N/A | Denied | N | 2025-07-01 | [8 empty] | X | 2025-04-25 | 6490 | [17 empty] | Helix | 6490 | 6490 | 0 | 0 | 0 | 0 | 0 | 0
180 | CRA | RS1180 | 1012908 | St. Charles | Madie Roman | Survey, SUE Level B | 2023-06-28 | 2023-06-30 | 2023-07-10 | 2023-07-24 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | NA | NA | N/A | Denied | N/A | 2023-01-01 | - | - | - | - |  |  |  |  | X | 2023-07-03 | 12400 | 2023-07-24 | X | 2023-06-30 | 12250 | 2023-07-24 | [13 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | CRA | TW1501117 |  | Ottawa | Madie Roman | Survey, SUE Level B | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-27 | 2025-05-02 | 2025-05-02 | 2025-05-04 | Denied | [5 empty] | Denied |  | 2025-08-01 | [8 empty] | X | 2025-04-27 | 7000 | 2025-05-27 | [17 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | CRA | RS1308 | 1015189 | Kingston | Tom McTigue | Survey, Level SUE B | 2025-07-25 | 2025-07-29 | 2025-08-04 | 2025-08-18 | 2025-07-29 | 2025-07-29 | 2025-07-30 | Denied | [5 empty] | Denied | [10 empty] | X | 2025-07-28 | 8680 | 2025-08-18 | [16 empty] | Helix | 8680 | 8680 | 0 | 0 | 0 | 0 | 0 | 0
278 | CRA | RS1333 | 1015589 | Harrison | Camille Corbi | Survey, Level SUE B | 2025-07-10 | 2025-07-14 | 2025-07-17 | 2025-07-31 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-29 | 2025-07-29 | X | 168777007.Y.038 | 2025-08-19 | 2025-08-19 | TBD | N | 2025-10-01 | [8 empty] | X | 2025-07-15 | 9900 | 2025-08-05 | [16 empty] | Helix | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0
275 | TR | TC638 | 1115481 | Crystal Lake | Nick Watt | Geotechnical | 2025-06-25 | 2025-06-30 | 2025-07-07 | 2025-08-21 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-07-22 | 2025-07-22 | X | 168777008.Z.510 | 2025-09-10 | 2025-09-10 | TBD | N | 2025-09-01 |  |  |  |  | X | 2025-06-30 | 21850 |  | X | 2025-06-30 | 8000 | 2025-07-22 | X | 2025-06-30 | 15670 | [13 empty] | Helix | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
280 | TIMP | TP658 | 1115512 | Elgin | Nick Watt | SUE Level A | 2025-07-21 | 2025-07-25 | 2025-08-01 | 2025-09-01 | 2025-07-28 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | X | 168777008.Z.511 | 2025-09-04 | 2025-09-03 | TBD | N | 2025-10-01 |  |  |  |  | X | Declined |  |  | X | 2025-07-28 | 10695 |  | X | 2025-07-25 | 20700 | [9 empty] | X | 2025-07-31 | 72671 |  | Helix | 10695 | 10695 | 0 | 0 | 0 | 0 | 0 | 0
283 | DOT | N19472 | 1315531 | Hanover Park | Caroline Kulach | SUE Level A | 2025-07-28 | 2025-07-30 | 2025-07-30 | 2025-09-04 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-11 | 2025-08-11 | X | 168777007.E.105 | 2025-09-19 | 2025-09-05 | 2025-10-01 | N | 2025-10-01 | [8 empty] | X | 2025-07-30 | 10665 | 2-3 weeks post county permits | X | Declined | N/A | N/A | X | Declined | N/A | N/A | [8 empty] | HELIX | 10665 | 10665 | 0 | 0 | 0 | 0 | 0 | 0
263 | TR | TWS122 | 1015156 | Galena | Mitchell Pohlman | Survey, SUE level B & Geotechnical | [13 empty] | TBD | N | 2025-08-01 | [29 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | Non-DOT | MR1796 | 1910690 | Summit | Mark Stanley | Survey, SUE Level B | 2025-08-07 | 2025-08-27 | 2025-09-12 | 2026-02-13 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-17 | 2025-09-17 | X | 168777007.Z.xxx | 2026-01-30 | [8 empty] | X | Declined |  |  | X | 2025-08-15 | 95435 | 2026-02-13 | X | Declined | [10 empty] | X | Declined |  |  | Helix | 95435 | 95435 | 0 | 0 | 0 | 0 | 0 | 0
283 | Non-DOT | MR2321 | 1215731 | Country Club Hills | Tom McTigue | Survey, Level SUE B | 2025-08-19 | 2025-08-21 | 2025-08-29 | 2025-09-15 | 2025-09-02 | 2025-09-02 | 2025-09-03 | [6 empty] | TBD | N | 2025-11-25 | [8 empty] | X | 9/2/250 | 16535 | 2025-09-22 | [17 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | CRA | RS1300 | 1014890 | Winnebago | Tom McTigue | Survey, Level SUE B | 2025-08-21 | 2025-08-25 | 2025-08-29 | 2025-09-26 | 2025-08-27 | 2025-08-28 | 2025-09-03 | 2025-09-16 | 2025-09-16 | X | 168777007.Y.041 | 2025-09-30 |  | TBD | N | 2025-11-25 | [8 empty] | X | 2025-08-26 | 7700 | 2025-09-16 | [17 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | Non-DOT | NBA10019119 | 1615675 | Elk Grove Village | Camille Corbi | Survey, SUE Level B | 2025-09-04 | 2025-09-10 | 2025-09-17 | 2025-10-08 | 2025-09-10 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 | X |  | 2025-10-15 |  | TBD | N | TBD |  |  |  |  | X | No Proposal |  |  | X | 2025-09-12 | 70470 | 2025-10-15 | [12 empty] | X | 2025-09-08 | 168640 |  | Helix | 70470 | 70470 | 0 | 0 | 0 | 0 | 0 | 0
286 | Non | MR2328 | 1215809 | BEDFORD PARK | Tom McTigue | Survey, SUE Level A & B, Geotechnical | 2022-08-15: 2025-09-10; 2022-08-20: 2025-09-12; 2022-08-25: 2025-09-18; 2022-08-27: 2025-10-09 |  |  |  |  | TBD | N | 2025-12-25 | [29 empty] | NO SELECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | CRA | RS1316 | 1015489 | GLEN ELLYN | Madie Roman | Survey, Level SUE B | 2025-08-19 | 2025-08-21 | 2025-08-28 | 2025-09-12 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-09-09 | 2025-09-09 | X | 168777007.Y.040 | [13 empty] | X | 2025-08-26 | 9940 | 2025-09-19 | [16 empty] | helix | 9940 | 9940 | 0 | 0 | 0 | 0 | 0 | 0
29935
Formulas:
Schedule AEG = Table13[[#This Row],[Planned NTP]]+21
Schedule AEG = 21+Table13[[#This Row],[Actual NTP]]
Billed/ Reported to Nicor? = Table13[[#This Row],[Current Expected Compl]]
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Subcoord and subconsultant tasks should be opened once we provide NTP and have both executed IPO and WO Forms
Note on U2: Whitson, Bryan: KH Cost = Not being billed to Nicor TBD = Ready to bill to Nicor or will be ready to bill Nicor by invoicing time N = Hold off on billing to Nicor - include note as to why we are holding on billing DATE = Month it was billed to Nicor (to be updated by Bryan)
Note on V2: Betland, Joseph: Y = KH Pays For Service (i.e. locates for DOT projects) N = Nicor Pays For Service (i.e. survey, soil bores, etc.)
Note on W2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Michaels, Nick @Purtell, Tim @Dina, Eric @Pohlman, Mitchell wondering if we get rid of this column to avoid confusion, and potentially column V as well since I bleieve that we’re putting KH-incurred survey over in the Field Noting tab. Thoughts? Reply: @Betland, Joseph I agree Reply: I agree. I think we should add a Billed Y/N column similar to the other sheets and remove the 2 columns that you suggested. Reply: Completely agree Reply: Can we delete this then?
Note on R64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yordan, Anna could you help me out and update this Reply: @Betland, Joseph FYI there seems to be two tasks for this one (i put both) since the 12" and 36" potholes were two separate tasks Reply: perfect, thanks!
Note on C74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Michaels, Nick - please update
Note on D76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Whitson, Bryan: There is a note in completed tab for T. Lierow to close this WO out with Nicor.
Note on Z87: LaPorte, Marissa: Did not give an Option B Proposal on time
Note on AP87: LaPorte, Marissa: Did not include soil bores in Option B
Note on AD100: LaPorte, Marissa: This is the discount cost if awarded RS1083 too
Note on AH100: LaPorte, Marissa: If combined with RS1083 then total cost is $22,500
Note on AD101: LaPorte, Marissa: This is the discount cost if awarded RS1082 too
Note on AH101: LaPorte, Marissa: If combined with RS1082 then total cost is $22,500
Note on AH166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost was $12,000 for original scope. Scope was reduced and cost was reduced to $10,000. Other sub costs reflect original scope.
Note on AP171: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Including rock adder for entirety of all bores.
Note on AR178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy why are these in here? did we ever get quotes from accurate? Reply: we got quotes from them, but at the time it was too expensive and they were new. i can remove but i added since we got that info Reply: @Castellon, Randy can these be unhighlighted?
Note on AL188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: =Survey+Geotech Updated Geotech quote pending
Note on AM188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Survey Geotech
Note on AD190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Price for 1 RR Crossing - Survey & Geotech. Selected Millennia for scope expansion.
Note on AH190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Price for 1 RR Crossing - Survey & Geotech. Selected Millennia for scope expansion.
Note on V195: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Castellon, Randy @Chamernik, Conner @Ekstrom, Ethan @Pohlman, Mitchell @Corbi, Camille @Lierow, Taylor please update red cells to note if this is KH cost or Nicor
Note on AE222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 80 days from NTP
Note on AI222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depending on crop harvest
Note on AK222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: -8/21/24: Geotech
Note on AL222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: -$57,875 for geotech
Note on AM222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: -10/29/24: geotech Reply: 6-8 weeks from NTP for survey Reply: Depending on crop harvest
Note on T227: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Michaels, Nick @McTigue, Thomas do we have this yet? Reply: @Betland, Joseph - have survey but pending final geotech report (due by 12/31). still plan to bill in dec Reply: Pending final geotech
Note on T228: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille - Are we waiting on anything for this one still? Reply: Geotech
Note on U236: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric - Can we bill this month? Reply: We haven't received an invoice yet, so I'd wait until March. Reply: This is typical for nicor initiated projects, so let's bill this
Note on U237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric - Can we bill this month? Reply: We haven't received an invoice yet, so I'd wait until March. Reply: This is typical for nicor initiated projects, so let's bill this
Note on U239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric - Can we bill this month? Reply: It doesn't appear that we've received an invoice yet, so I would hold until March. @Betland, Joseph let me know if you disagree. Reply: Agreed Reply: Sorry, I didn't realize that this was in reference to a nicor initiated spend. i think we should bill this month
Note on AD240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $5800 for traffic control only if boring in roadway.
Note on AE240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Survey 2/11/25, Geotech 4-8 weeks from NTP
Note on AI240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Survey 2/18/25, Geotech 3/7/25
Note on L241: LaPorte, Marissa: 12/16/24 - rescoped per Nicor
Note on U245: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dina, Eric /@Betland, Joseph - can we bill this month? Reply: yes - please note that it's going to not be the full amount though. full amount is listed in the 2025 3rd party review tracker
Note on BA245: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Bruce, Logan please verify this number. Can you please make sure that printing is included here, as well as in our 2025 3rd party tracker? Reply: Millennia has billed $68,080. With our Mark up that would be $74,888.00. Shactee has billed 2,327.96 for N14793, but not sure if that is related as it referenced .E.082. $1,367.76 in Direct Expense printing. How do you want the expenses to show in 3rd party tracker? Reply: Shactee is different altogether. I'm assuming that the printing expense came from millenia? so that would be added to the 68080, then 10% on top of the whole thing is our bill, which would be $76,392.54? Or do we not get a markup on the expenses? Reply: @Bruce, Logan based on the invoice that was created, it appears that the printing fees aren't subject to the 10% markup. Can you confirm that?
Note on BA246: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bruce, Logan we are only being billed partially for this amount - can you update this to the $2700 or so that we were invoiced? Reply: this is the correct amount that was just submitted.
Note on U247: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pohlman, Mitchell - Can we bill this month? Reply: nope Reply: @Pohlman, Mitchell still nothing?
Note on C249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas - can you split this up for each quote?
Note on AE249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3/7/2025 for Metra Geotech 2-4 weeks from NTP
Note on AI249: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Geotech 4/14/2025
Note on W250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas @Michaels, Nick should this be March? Reply: @Betland, Joseph - no this isnt when the 3rd party spend was billed to nicor this is when the project will be billed to nicor. Which is tracking for May.
Note on C251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille - can you split this up for each separate quote?
Note on S253: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Stanley, Mark @Castellon, Randy is this still on track? If so, can we bill? Reply: still expected on the 30th.
Note on W254: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Purtell, Tim shouldn’t these all be May? Reply: @Betland, Joseph Isn't this column anticipated billing month for the project? Reply: well if it's Nicor initiated shouldn't we have already reported it and billed it, as we note two columns to the left?
Note on AD257: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There could be an additional $5,800 added based on traffic control fee
Note on S260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lierow, Taylor what's our anticipated date for this? Can we bill this month? Reply: Updated Reply: Did we get this yet?
Note on W260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lierow, Taylor is this going to be july or August now? Reply: Most likely July
Note on W262: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @McTigue, Thomas I’d recommend entering June here if we think we’re going to get this by 6/10
Note on AH263: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $19,550 for SUE B
Note on BA267: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Watt, Nick I assume this is selected now? Reply: correct
Note on U281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Watt, Nick have we received these deliverables yet? If so, can we invoice these and report this to Nicor as DBE spend? @Michaels, Nick Reply: @Betland, Joseph negative, these aren't yet back from Helix. They weren't able to schedule Potholes until 8/22.
Note on AD281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $5,000 and $2,200 in variable costs. As low as $14,650
Note on I284: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pohlman, Mitchell what’s going on with this one? Reply: project on hold
Note on F288: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Corbi, Camille - please fill out

## DBE Summary
DOT |  |  |  |  | DOT-TR |  |  |  |  | Combined DOT & DOT-TR
| Staffing | Field Noting | Nicor Initiated | Total |  | Staffing | Field Noting | Nicor Initiated | Total |  | Staffing | Field Noting | Nicor Initiated | Total
2025-02-25 | 28544.25 | 13625 | 0 | 42169.25
2025-03-25 | 49136.26 | 53605 | 68845 | 171586.26 | 2025-03-25 | 0 | 0 | 0 | 0 | 2025-03-25 | 49136.26 | 53605 | 68845 | 171586.26
2025-04-25 | 25829.97 | 32863.72 | 0 | 58693.69 | 2025-04-25 | 0 | 11000 | 0 | 11000 | 2025-04-25 | 25829.97 | 43863.72 | 0 | 69693.69
2025-05-25 | 750.58 | 8300 | 4900 | 13950.58 | 2025-05-25 | 0 | 0 | 0 | 0 | 2025-05-25 | 750.58 | 8300 | 4900 | 13950.58
2025-06-25 | 8490.03 | 52536.79 | 0 | 61026.82 | 2025-06-25 | 0 | 0 | 0 | 0 | 2025-06-25 | 8490.03 | 52536.79 | 0 | 61026.82
2025-07-25 | 80128.56 | 94337.63 | 0 | 174466.19 | 2025-07-25 | 0 | 0 | 0 | 0 | 2025-07-25 | 80128.56 | 94337.63 | 0 | 174466.19
2025-08-25 | 27226.83 | 64925 | 0 | 92151.83 | 2025-08-25 | 0 | 6250 | 0 | 6250 | 2025-08-25 | 27226.83 | 71175 | 0 | 98401.83
2025-09-25 | 44000 | 42068.71 | 0 | 86068.71 | 2025-09-25 | 0 | 4700 | 0 | 4700 | 2025-09-25 | 44000 | 46768.71 | 0 | 90768.71
2025-10-25 | 26419.23 | 78753.85 | 10665 | 115838.08 | 2025-10-25 | 0 | 4750 | 0 | 4750 | 2025-10-25 | 26419.23 | 83503.85 | 10665 | 120588.08
2025-11-25 | 51632.55 | 151825 | 0 | 203457.55 | 2025-11-25 | 0 | 2500 | 0 | 2500 | 2025-11-25 | 51632.55 | 154325 | 0 | 205957.55
2025-12-25 | 64742.46 | 55370 | 0 | 120112.46 | 2025-12-25 | 0 | 0 | 0 | 0 | 2025-12-25 | 64742.46 | 55370 | 0 | 120112.46
Formulas:
Staffing = SUMIFS(Table5[Anticipated Fee],Table5[Project Type],"DOT",Table5[Anticipated Nicor Report Month],">="&EOMONTH([DOT],-1)+1, Table5[Anticipated Nicor Report Month],"<="&EOMONTH([DOT],0))
Staffing = SUMIFS(Table5[Anticipated Fee],Table5[Project Type],"DOT-TR",Table5[Anticipated Nicor Report Month],">="&EOMONTH([DOT],-1)+1, Table5[Anticipated Nicor Report Month],"<="&EOMONTH([DOT],0))
Field Noting = SUMIFS(Table3[[ Amount ]],Table3[Project Type],"DOT", Table3[Anticipated Nicor Report Month],">="&EOMONTH([DOT],-1)+1, Table3[Anticipated Nicor Report Month],"<="&EOMONTH([DOT],0))
Field Noting = SUMIFS(Table3[[ Amount ]],Table3[Project Type],"DOT-TR", Table3[Anticipated Nicor Report Month],">="&EOMONTH([DOT],-1)+1, Table3[Anticipated Nicor Report Month],"<="&EOMONTH([DOT],0))
Nicor Initiated = SUMIFS(Table13[Amount],Table13[Project Type],"DOT",Table13[Anticipated Billing Month],"="&EOMONTH([DOT],-1)+1)
Nicor Initiated = SUMIFS(Table13[Amount],Table13[Project Type],"DOT-TR",Table13[Anticipated Billing Month],"="&EOMONTH([DOT],-1)+1)